## Sheet1
Activity ID | Activity Name | Remaining Duration | Start | Finish
Frame 6B Power Group Project |  | 120 | 20-Jul-25 A | 2026-03-20
General Milestones |  | 142 | 21-Jul-25 A | 2026-03-18
GN-1000 | Project Award | 0 | 21-Jul-25 A
GN-1010 | Disconnect Complete (iMTT) | 0 |  | 25-Jul-25 A
GN-1085 | RIGGS Agreement and Task Order #1 | 0 |  | 27-Aug-25 A
GN-1120 | Mobilize Sitework Contractors and Temp Facillities to Site (Construction Notice to Proceed) | 0 | 01-Oct-25 A
GN-1140 | Disassembly Complete (excludes ST) | 0 |  | 01-Nov-25*
GN-1030 | Transportation Complete | 0 |  | 2025-11-14
GN-1020 | Disassembly Complete (ST) | 0 |  | 2025-12-10
GN-1095 | HRSG Inspection / Disassembly | 74 | 20-Sep-25 A | 2025-12-29
GN-1090 | Permit to Construct | 0 |  | 15-Jan-26*
GN-1050 | Pipe Fabrication Complete | 0 |  | 2026-01-23
GN-1060 | Construction Complete | 0 |  | 2026-02-09
GN-1040 | Refurbishment Complete (On Site) | 0 |  | 2026-02-26
GN-1070 | Testing and Commissioning Complete GT #1 | 0 |  | 2026-03-03
GN-1080 | First Fire GT #1 | 0 |  | 05-Mar-26*
GN-1135 | On Line Testing and Commercial Operation GT #1 | 0 |  | 2026-03-09
GN-1100 | Testing and Commissioning Complete GT #2 | 0 |  | 2026-03-12
GN-1105 | Testing and Commissioning Complete GT #3 | 0 |  | 2026-03-12
GN-1110 | First Fire GT #2 | 0 |  | 14-Mar-26*
GN-1115 | First Fire GT #3 | 0 |  | 14-Mar-26*
GN-1125 | On Line Testing and Commercial Operation GT #2 | 0 |  | 2026-03-18
GN-1130 | On Line Testing and Commercial Operation GT #3 | 0 |  | 2026-03-18
Interface Milestones |  | 139 | 2025-10-03 | 2026-03-14
IM-1035 | Stormwater / Erosion / Site Grading Plans (Red Tree IFC) | 0 |  | 2025-10-03
IM-1040 | Construction access to 6B Power block available - Security / Fencing / Roads | 0 |  | 2025-10-03
IM-1045 | Selection of Metering Equipment and Reporting equipment install - XCEL and 6B Power | 0 |  | 2025-10-03
IM-1050 | Controls and Metering from SEL to utility and back to Frame 6B control house and Fermi Admin | 0 |  | 2025-10-03
IM-1055 | Water (Potable Process, Firewater) available from SGT-800 power block (Red Tree) | 0 |  | 2025-10-03
IM-1060 | Construction water available at Frame 6B power block laydown area (Parkhill) | 0 |  | 2025-10-03
IM-1065 | Process water discharge tie-point available at Frame 6B power block (Parkhill) | 0 |  | 2025-10-03
IM-1010 | Pre-Construction grading in power block complete (Red Tree IFC design) | 0 |  | 2026-01-15
IM-1000 | City of Amarillo water (Potable & Process) available at Frame 6B tie-point | 0 |  | 06-Feb-26*
IM-1020 | High Pressure fuel gas ready for tie in (PERC) | 0 |  | 06-Feb-26*
IM-1025 | 115 kV Dead End Structure in Power Block ready for tie-in (Dashiel) | 0 |  | 06-Feb-26*
IM-1005 | 115 kV System Ready to Deliver and Accept Power | 0 |  | 14-Mar-26*
IM-1030 | High Pressure fuel gas supply commissioning complete to tie-in point | 0 |  | 14-Mar-26*
IMTT Faciltiy |  | 74 | 21-Jul-25 A | 2025-12-29
Disconnect |  | 0 | 21-Jul-25 A | 25-Jul-25 A
DC-1000 | Disconnect Components - Make Safe | 0 | 21-Jul-25 A | 25-Jul-25 A
Disassembly |  | 74 | 23-Jul-25 A | 2025-12-29
General |  | 0 | 23-Jul-25 A | 26-Sep-25 A
DA-2025 | General Assessment - 3D Scanning and Equipment Assessment | 0 | 23-Jul-25 A | 16-Aug-25 A
DA-2255 | Riggs Agreement Finalized | 0 | 27-Aug-25 A | 27-Aug-25 A
DA-2260 | Riggs Letter of Credit Accepted | 0 | 27-Aug-25 A | 27-Aug-25 A
DA-2045 | Riggs Mobilize and Begin Disassembly | 0 | 28-Aug-25 A | 02-Sep-25 A
DA-2265 | NAES Copies of all documentation, manuals, drawings, equipment O&M Manuals and distribute | 0 | 28-Aug-25 A | 26-Sep-25 A
Assessments |  | 0 | 06-Sep-25 A | 12-Sep-25 A
GT #3 Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2100 | GT#3 Inspection - Borescope | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2105 | GT#3 Inspection - Bearing Inspection | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #3 Generator Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2110 | GT#3 Generator Inspection - Stator Electrical Testing (megger tests / visual inspections / busings / insulators) | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2115 | GT#3 Generator Inspection - Field Electrical Testing (megger / visual) | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #2 Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2120 | GT#2 Inspection - Borescope | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2125 | GT#2 Inspection - Bearing Inspection | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #2 Generator Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2130 | GT#2 Generator Inspection - Stator Electrical Testing (megger tests / visual inspections / busings / insulators) | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2135 | GT#2 Generator Inspection - Field Electrical Testing (megger / visual) | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #1 Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2140 | GT#1 Inspection - Borescope | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2145 | GT#1 Inspection - Bearing Inspection | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #1 Generator Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2150 | GT#1 Generator Inspection - Stator Electrical Testing (megger tests / visual inspections / busings / insulators) | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2155 | GT#1 Generator Inspection - Field Electrical Testing (megger / visual) | 0 | 06-Sep-25 A | 10-Sep-25 A
Steam Generator Inspection |  | 0 | 09-Sep-25 A | 12-Sep-25 A
DA-2160 | Steam Turbine Generator Inspection - Continuity / Megger test | 0 | 09-Sep-25 A | 12-Sep-25 A
Site Prep |  | 1 | 06-Sep-25 A | 2025-10-04
DA-2190 | Prep Site Construction Trailers and Temporary Facilities | 0 | 06-Sep-25 A | 25-Sep-25 A
DA-2180 | Prep Site Roads (for heavy Equipment) | 1 | 20-Sep-25 A | 2025-10-04
DA-2185 | Prep Site Laydown Areas (Demo / Fence relocation) | 1 | 06-Sep-25 A | 2025-10-04
GT #1 Main Unit |  | 9 | 02-Sep-25 A | 2025-10-14
A1010 | CT #1 - Work ubolting internal piping, bearings, and expansion joints | 0 | 02-Sep-25 A | 06-Sep-25 A
A1060 | CT #1 - Remove inlet duct | 0 | 05-Sep-25 A | 06-Sep-25 A
A1000 | CT #1 - Clean out 2 CT Bldgs - removel debris, 3 center skids, 2 acid tanks, center platform and eyewash station | 0 | 03-Sep-25 A | 20-Sep-25 A
A1030 | CT #1 - Remove Large outlet ducts @ HRSG | 0 | 15-Sep-25 A | 20-Sep-25 A
A1040 | CT #1 - Remove all wanted piping on both sides | 0 | 03-Sep-25 A | 20-Sep-25 A
A1050 | CT #1 - Remove Inlet Air Duct Steel | 0 | 02-Sep-25 A | 20-Sep-25 A
A1180 | CT #1 - Disconnect all electrical, panel misc. wiring | 0 | 02-Sep-25 A | 20-Sep-25 A
A1565 | CT #1 - Remove cover on Gear Box / Excitor Cover | 0 | 19-Sep-25 A | 20-Sep-25 A
A1570 | CT #1 - Re-Install Turbine Doors | 0 | 22-Sep-25 A | 22-Sep-25 A
A1020 | CT #1 - Un-bolt and/ or cut inlet duct, heat recovery duct and outlet duct | 0 | 19-Sep-25 A | 03-Oct-25 A
A1070 | CT #1 - Remove all Turine cat walks | 0 | 20-Sep-25 A | 03-Oct-25 A
A1080 | CT #1 - Remove all floor grating and tanks | 0 | 02-Oct-25 A | 03-Oct-25 A
A1090 | CT #1 - Demo and clean vault area | 0 | 02-Oct-25 A | 03-Oct-25 A
A1100 | CT #1 - Fill pit area with materials (sand or other) in order to support heavy rigging equipment, gantries and tracks | 5 | 2025-10-04 | 2025-10-09
A1110 | CT #1 - Move in and set up heavy rigging gantries | 5 | 2025-10-06 | 2025-10-10
A1120 | CT #1 - Remove overhead roll-up door and make opening taller | 5 | 2025-10-06 | 2025-10-10
A1130 | CT #1 - Remove first section (Switch gear control box) 21' XLBS to SPMT and move to outside crane | 1 | 2025-10-11 | 2025-10-11
A1140 | CT #1 - Remove 2nd section (Main Generator) 15' estimated 200k lbs to SPT and move to outside crane | 1 | 2025-10-13 | 2025-10-13
A1150 | CT #1 - Remove 3rd section (Heat recovery and gear box) 10' weight? To SPT and move to outside crane | 1 | 2025-10-14 | 2025-10-14
A1160 | CT #1 - Remove 4th (Turbine Skid) 38' weight? To SPT and move to outside crane | 1 | 2025-10-14 | 2025-10-14
A1170 | CT #1 - Transport to Barge (UTC Scope) duration TBD | 1 | 2025-10-14 | 2025-10-14
GT #3 Main Unit |  | 25 | 15-Sep-25 A | 2025-11-01
A1190 | CT #3 - Clean out 2 CT Bldgs - removel debris, 3 center skids, 2 acid tanks, center platform and eyewash station | 0 | 15-Sep-25 A | 20-Sep-25 A
A1200 | CT #3 - Remove inlet duct | 0 | 22-Sep-25 A | 26-Sep-25 A
A1230 | CT #3 - Remove Inlet Air Duct Steel | 2 | 2025-10-04 | 2025-10-06
A1270 | CT #3 - Un-bolt and/ or cut inlet duct, heat recovery duct and outlet duct | 2 | 2025-10-10 | 2025-10-11
A1260 | CT #3 - Remove overhead roll-up door and make opening taller | 4 | 2025-10-09 | 2025-10-13
A1210 | CT #3 - Work ubolting internal piping, bearings, and expansion joints | 9 | 18-Sep-25 A | 2025-10-14
A1240 | CT #3 - Remove Lage outlet ducts @ HRSG | 5 | 2025-10-09 | 2025-10-14
A1250 | CT #3 - Remove all wanted piping on both sides | 5 | 2025-10-09 | 2025-10-14
A1280 | CT #3 - Remove all Turine cat walks | 2 | 2025-10-15 | 2025-10-16
A1290 | CT #3 - Remove all floor grating and tanks | 2 | 2025-10-15 | 2025-10-16
A1310 | CT #3 - Demo and clean vault area | 2 | 2025-10-17 | 2025-10-18
A1220 | CT #3 - Disconnect all electrical, panel misc. wiring | 15 | 15-Sep-25 A | 2025-10-21
A1320 | CT #3 - Fill pit area with materials (sand or other) in order to support heavy rigging equipment, gantries and tracks | 3 | 2025-10-21 | 2025-10-23
A1300 | CT #3 - Move in and set up heavy rigging gantries | 3 | 2025-10-24 | 2025-10-27
A1330 | CT #3 - Remove first section (Switch gear control box) 21' XLBS to SPMT and move to outside crane | 1 | 2025-10-28 | 2025-10-28
A1340 | CT #3 - Remove 2nd section (Main Generator) 15' estimated 200k lbs to SPT and move to outside crane | 1 | 2025-10-29 | 2025-10-29
A1350 | CT #3 - Remove 3rd section (Heat recovery and gear box) 10' weight? To SPT and move to outside crane | 1 | 2025-10-30 | 2025-10-30
A1370 | CT #3 - Remove 4th (Turbine Skid) 38' weight? To SPT and move to outside crane | 1 | 2025-10-31 | 2025-10-31
A1360 | CT #3 - Transport to Barge (UTC Scope) duration TBD | 1 | 2025-11-01 | 2025-11-01
GT #2 Main Unit |  | 16 | 04-Sep-25 A | 2025-10-22
A1380 | CT #2 - Clean out 2 CT Bldgs - removel debris, 3 center skids, 2 acid tanks, center platform and eyewash station | 0 | 04-Sep-25 A | 20-Sep-25 A
A1400 | CT #2 - Work ubolting internal piping, bearings, and expansion joints | 0 | 04-Sep-25 A | 20-Sep-25 A
A1390 | CT #2 - Remove inlet duct | 0 | 16-Sep-25 A | 20-Sep-25 A
A1410 | CT #2 - Disconnect all electrical, panel misc. wiring | 0 | 04-Sep-25 A | 20-Sep-25 A
A1430 | CT #2 - Remove Large outlet ducts @ HRSG | 0 | 20-Sep-25 A | 25-Sep-25 A
A1420 | CT #2 - Remove Inlet Air Duct Steel | 0 | 23-Sep-25 A | 25-Sep-25 A
A1440 | CT #2 - Remove all wanted piping on both sides | 0 | 16-Sep-25 A | 26-Sep-25 A
A1460 | CT #2 - Un-bolt and/ or cut inlet duct, heat recovery duct and outlet duct | 0 | 17-Sep-25 A | 03-Oct-25 A
A1480 | CT #2 - Remove all floor grating and tanks | 0 | 02-Oct-25 A | 03-Oct-25 A
A1500 | CT #2 - Demo and clean vault area | 0 | 02-Oct-25 A | 03-Oct-25 A
A1510 | CT #2 - Fill pit area with materials (sand or other) in order to support heavy rigging equipment, gantries and tracks | 1 | 30-Sep-25 A | 2025-10-04
A1450 | CT #2 - Remove overhead roll-up door and make opening taller | 1 | 02-Oct-25 A | 2025-10-04
A1470 | CT #2 - Remove all Turbine cat walks | 2 | 2025-10-04 | 2025-10-06
A1575 | CT #2 - Re-install Turbine Doors | 4 | 2025-10-04 | 2025-10-08
A1490 | CT #2 - Move in and set up heavy rigging gantries | 3 | 2025-10-15 | 2025-10-17
A1520 | CT #2 - Remove first section (Switch gear control box) 21' XLBS to SPMT and move to outside crane | 1 | 2025-10-18 | 2025-10-18
A1530 | CT #2 - Remove 2nd section (Main Generator) 15' estimated 200k lbs to SPT and move to outside crane | 1 | 2025-10-20 | 2025-10-20
A1540 | CT #2 - Remove 3rd section (Heat recovery and gear box) 10' weight? To SPT and move to outside crane | 2 | 2025-10-21 | 2025-10-22
A1560 | CT #2 - Remove 4th (Turbine Skid) 38' weight? To SPT and move to outside crane | 3 | 2025-10-20 | 2025-10-22
A1550 | CT #2 - Transport to Barge (UTC Scope) duration TBD | 4 | 2025-10-18 | 2025-10-22
Building (Steam Turbine Generator) |  | 4 | 2025-11-04 | 2025-11-07
DA-2000 | Disassemble Steam Turbine Generator Building | 4 | 2025-11-04 | 2025-11-07
Steam Turbine Generator |  | 61 | 22-Sep-25 A | 2025-12-13
Scaffolding |  | 49 | 22-Sep-25 A | 2025-11-29
DA-3000 | Erect Scaffolding | 1 | 22-Sep-25 A | 2025-10-04
EN-ST-455 | Scaffolding Modifications | 24 | 2025-10-06 | 2025-11-01
EN-ST-460 | Scaffolding Breakdowns | 24 | 2025-11-03 | 2025-11-29
Support Services |  | 58 | 27-Sep-25 A | 2025-12-10
DA-3010 | Insulation Removal (Pipe) | 18 | 27-Sep-25 A | 2025-10-24
DA-3015 | Insulation Removal (Tubing) | 12 | 2025-10-25 | 2025-11-07
DA-3005 | Crane / Equipment Support | 58 | 29-Sep-25 A | 2025-12-10
Pipefitter |  | 61 | 27-Sep-25 A | 2025-12-13
DA-3030 | Assure 30T OH Crane is certified for use, load test if req'd | 0 | 29-Sep-25 A | 30-Sep-25 A
DA-3025 | Trace fire suppressiono / sprinkler piping and mark for demo / reloaiton / refeed | 0 | 27-Sep-25 A | 03-Oct-25 A
DA-3045 | Remove 3 tanks and all utilities to allow access for flatbed trailers as req'd | 5 | 01-Oct-25 A | 2025-10-09
DA-3020 | Trace out Piping systems for demo or refeed | 6 | 27-Sep-25 A | 2025-10-10
DA-3040 | Remove chemical treatment skid to allow access for flatbed trailers as req'd | 6 | 01-Oct-25 A | 2025-10-10
DA-3035 | Remove all req'd utilities from in / out building wall to be removed | 12 | 2025-10-04 | 2025-10-17
DA-3050 | Cut out welded valves, transport to laydown, store until shipment (est. 30) | 20 | 2025-10-10 | 2025-11-01
DA-3055 | Cap & blind existing piping and modify for reconnection | 12 | 2025-10-27 | 2025-11-08
DA-3060 | Remove all CVs and instrumentation, transport to laydown, store for shipment | 12 | 2025-11-03 | 2025-11-15
DA-3065 | Demo all steam, cond., cooling water & Treatment piping | 12 | 2025-11-17 | 2025-11-29
DA-3075 | Remove piping and wiring from the lube oil skid & prepare the skid unit for shipping | 6 | 2025-12-01 | 2025-12-06
DA-3080 | Remove clean oil storage tank and prepare for shipping | 3 | 2025-12-08 | 2025-12-10
DA-3070 | Install Blinds, caps, plugs, etc. as req'd for shipping | 12 | 2025-12-01 | 2025-12-13
Electrical |  | 55 | 22-Sep-25 A | 2025-12-06
EN-ST-465 | Trace electrical & instrumentation conduits and mark for demo / relocation / refeed | 1 | 22-Sep-25 A | 2025-10-04
EN-ST-470 | Demo cable tray and wiring to MCC Enclosure near turbine deck | 14 | 2025-10-10 | 2025-10-25
EN-ST-500 | Disconnect the MCC Enclosure from the load side and pack for shipping | 12 | 2025-10-27 | 2025-11-08
EN-ST-505 | Disassembly of Generator and Turbine electrical components | 24 | 2025-11-10 | 2025-12-06
EN-ST-510 | Disassembly of all cable tray, misc. wiring / conduit, and terminatons | 24 | 2025-11-10 | 2025-12-06
Millwright |  | 50 | 2025-10-11 | 2025-12-08
DA-2005 | Steam Turbine - Drain all casings of any fluids | 2 | 2025-10-11 | 2025-10-13
DA-2010 | Steam Turbine - Disconnect and remove turbine casings tops | 4 | 2025-10-14 | 2025-10-17
DA-2015 | Steam Turbine - Extract rotor and bearings per manufacturer's specifications | 6 | 2025-10-18 | 2025-10-24
DA-2020 | Steam Turbine - Removal & storage of all valving components on & in the turbine | 12 | 2025-10-25 | 2025-11-07
DA-3085 | Steam Turbine - Removal of gearbox | 6 | 2025-11-01 | 2025-11-07
DA-3090 | Steam Turbine - Removal of bottom casing of turbine | 6 | 2025-11-08 | 2025-11-14
DA-3095 | Generator - Drain all casings of any fluid | 2 | 2025-11-15 | 2025-11-17
DA-3100 | Generator - Remove doghouse from generator to allow access to rotor | 4 | 2025-11-18 | 2025-11-21
DA-3105 | Generator - Remove generator end bell tops | 4 | 2025-11-22 | 2025-11-26
DA-3110 | Generator - Lift rotor and safe off to remove bearings and end bell lowers | 4 | 2025-11-27 | 2025-12-01
DA-3115 | Generator - Rig out rotor per manufacturer's specifications | 4 | 2025-12-02 | 2025-12-05
DA-3120 | Generator - Set rotor on 12"x12" oak crigging and strap down for shipping | 2 | 2025-12-06 | 2025-12-08
Boilermaker |  | 30 | 2025-10-04 | 2025-11-07
EN-ST-475 | Platform / Casing Scope layout | 6 | 2025-10-04 | 2025-10-10
EN-ST-515 | Remove condenser section / requires disassembly of channel boxes / feedwater piping | 6 | 2025-10-11 | 2025-10-17
EN-ST-520 | Demo condenser assembly (cut existing welds to break into pieces) | 6 | 2025-10-18 | 2025-10-24
EN-ST-525 | Remove guillotine valve section (12'wx2'lx18'h) | 6 | 2025-10-25 | 2025-10-31
EN-ST-530 | Rig and remove remaining pieces of equipment from steam turbine area | 6 | 2025-11-01 | 2025-11-07
Insulation |  | 24 | 2025-10-04 | 2025-10-31
EN-ST-535 | Layout and match marking of removed components | 6 | 2025-10-04 | 2025-10-10
EN-ST-540 | Remove / un-bolt platforms and grating | 12 | 2025-10-11 | 2025-10-24
EN-ST-545 | Remove / un-bolt ladders, support steel and stairs | 6 | 2025-10-25 | 2025-10-31
HRSG #3 |  | 62 | 20-Sep-25 A | 2025-12-15
DA-2030 | HRSG #3 - Inspection / Testing | 0 | 20-Sep-25 A | 25-Sep-25 A
DA-2090 | HRSG #3 - Analyze Reports | 0 | 26-Sep-25 A | 2025-10-04
DA-2095 | HRSG #3 - Agreemnt (Fermi and iMTT) | 5 | 2025-10-04 | 2025-10-09
DA-1815 | HRSG #3 - Disassemble | 48 | 2025-10-10 | 2025-12-04
DA-1825 | HRSG #3 - Pack | 8 | 2025-12-05 | 2025-12-13
DA-1835 | HRSG #3 - Load | 8 | 2025-12-06 | 2025-12-15
HRSG #2 |  | 68 | 20-Sep-25 A | 2025-12-22
DA-2035 | HRSG #2 - Inspection / Testing | 0 | 20-Sep-25 A | 25-Sep-25 A
DA-2075 | HRSG #2 - Analyze Reports | 0 | 26-Sep-25 A | 2025-10-04
DA-2080 | HRSG #2 - Agreemnt (Fermi and iMTT) | 5 | 2025-10-04 | 2025-10-09
DA-1855 | HRSG #2 - Disassemble | 48 | 2025-10-17 | 2025-12-11
DA-1865 | HRSG #2 - Pack | 8 | 2025-12-12 | 2025-12-20
DA-1875 | HRSG #2 - Load | 8 | 2025-12-13 | 2025-12-22
HRSG #1 |  | 74 | 20-Sep-25 A | 2025-12-29
DA-2040 | HRSG #1 - Inspection / Testing | 0 | 20-Sep-25 A | 25-Sep-25 A
DA-2060 | HRSG #1 - Analyze Reports | 0 | 26-Sep-25 A | 2025-10-04
DA-2065 | HRSG #1 - Agreemnt (Fermi and iMTT) | 5 | 2025-10-04 | 2025-10-09
DA-1895 | HRSG #1 - Disassemble | 48 | 2025-10-24 | 2025-12-18
DA-1905 | HRSG #1 - Pack | 8 | 2025-12-19 | 2025-12-27
DA-1915 | HRSG #1 - Load | 8 | 2025-12-20 | 2025-12-29
CEMS Building |  | 7 | 2025-10-04 | 2025-10-11
DA-1935 | CEMS Building - Disassemble | 4 | 2025-10-04 | 2025-10-08
DA-1945 | CEMS Building - Pack | 2 | 2025-10-09 | 2025-10-10
DA-1955 | CEMS Building - Load | 1 | 2025-10-11 | 2025-10-11
Water System |  | 6 | 2025-10-06 | 2025-10-11
DA-1975 | Water System - Disassemble | 3 | 2025-10-06 | 2025-10-08
DA-1985 | Water System - Pack | 2 | 2025-10-09 | 2025-10-10
DA-1995 | Water System - Load | 1 | 2025-10-11 | 2025-10-11
Transportation |  | 40 | 2025-10-15 | 2025-11-29
Permitted Loads |  | 40 | 2025-10-15 | 2025-11-29
TR-1030 | GT #1 Main Unit - Barge Transport to Port of Houston | 18 | 2025-10-15 | 2025-11-04
TR-1165 | GT #1 Main Unit - Truck from Port of Houston to Amarillo | 6 | 2025-11-05 | 2025-11-11
TR-1020 | GT #2 Main Unit - Barge Transport to Port of Houston | 18 | 2025-10-23 | 2025-11-12
TR-1135 | Steam Turbine - Transport to Refurb location | 18 | 2025-10-25 | 2025-11-14
TR-1160 | GT #2 Main Unit - Truck from Port of Houston to Amarillo | 6 | 2025-11-13 | 2025-11-19
TR-1005 | GT #3 Main Unit - Barge Transport to Port of Houston | 18 | 2025-11-03 | 2025-11-22
TR-1145 | GT #3 Main Unit - Truck from Port of Houston to Amarillo | 6 | 2025-11-24 | 2025-11-29
Refurbishment |  | 111 | 2025-11-12 | 2026-03-20
Turbines |  | 111 | 2025-11-12 | 2026-03-20
GT #3 |  | 58 | 2025-12-01 | 2026-02-05
RF-1000 | GT #3 Main Unit - Receive at Shop and Set in Position | 2 | 2025-12-01 | 2025-12-02
RF-1010 | GT #3 Main Unit - Refurbish (3 weeks) | 18 | 2025-12-26 | 2026-01-15
RF-1020 | GT #3 Main Unit - Transport to Jobsite | 1 | 2026-01-16 | 2026-01-16
RF-1090 | GT #3 Main Unit - Pull & Refurb Parts (4 Weeks) | 24 | 2026-01-09 | 2026-02-05
GT #2 |  | 104 | 2025-11-20 | 2026-03-20
RF-1005 | GT #2 Main Unit - Receive at Shop and Set in Position | 2 | 2025-11-20 | 2025-11-21
RF-1025 | GT #2 Main Unit - Refurbish (3 weeks) | 18 | 2026-02-06 | 2026-02-26
RF-1030 | GT #2 Main Unit - Transport to Jobsite | 1 | 2026-02-27 | 2026-02-27
RF-1095 | GT #2 Main Unit - Pull & Refurb Parts (4 Weeks) | 24 | 2026-02-20 | 2026-03-19
RF-1105 | GT #2 Main Unit - Transport to Jobsite (spare parts inventory) | 1 | 2026-03-20 | 2026-03-20
GT #1 |  | 38 | 2025-11-12 | 2025-12-25
RF-1015 | GT #1 Main Unit - Receive at Shop and Set in Position | 2 | 2025-11-12 | 2025-11-13
RF-1035 | GT #1 Main Unit - Refurbish (3 weeks) | 18 | 2025-11-14 | 2025-12-04
RF-1040 | GT #1 Main Unit - Transport to Jobsite | 1 | 2025-12-05 | 2025-12-05
RF-1100 | GT #1 Main Unit - Pull & Refurb Parts (4 Weeks) | 24 | 2025-11-28 | 2025-12-25
Generators |  | 52 | 2025-11-12 | 2026-01-10
Unit #3 |  | 36 | 2025-12-01 | 2026-01-10
RF-1045 | Unit #3 Generator - Receive and set at Site | 3 | 2025-12-01 | 2025-12-03
RF-1050 | Unit #3 Generator - Test On site (2 weeks) | 12 | 2025-12-04 | 2025-12-17
RF-1110 | Unit #3 Generator - Pull Rotor / Send to Shop for Testing / Refurb (3 weeks) | 18 | 2025-12-18 | 2026-01-07
RF-1055 | Unit #3 Generator - Transport to Foundation | 3 | 2026-01-08 | 2026-01-10
Unit #2 |  | 36 | 2025-11-20 | 2025-12-31
RF-1060 | Unit #2 Generator - Receive and set at Site | 3 | 2025-11-20 | 2025-11-22
RF-1065 | Unit #2 Generator - Test On site (2 weeks) | 12 | 2025-11-24 | 2025-12-06
RF-1115 | Unit #2 Generator - Pull Rotor / Send to Shop for Testing / Refurb (3 weeks) | 18 | 2025-12-08 | 2025-12-27
RF-1070 | Unit #2 Generator - Transport to Foundation | 3 | 2025-12-29 | 2025-12-31
Unit #1 |  | 36 | 2025-11-12 | 2025-12-23
RF-1075 | Unit #1 Generator - Receive and set at Site | 3 | 2025-11-12 | 2025-11-14
RF-1080 | Unit #1 Generator - Test On site (2 weeks) | 12 | 2025-11-15 | 2025-11-28
RF-1120 | Unit #1 Generator - Pull Rotor / Send to Shop for Testing / Refurb (3 weeks) | 18 | 2025-11-29 | 2025-12-19
RF-1085 | Unit #1 Generator - Transport to Foundation | 3 | 2025-12-20 | 2025-12-23
Engineering |  | 95 | 20-Jul-25 A | 2026-02-13
Process |  | 30 | 04-Aug-25 A | 2025-11-14
FIDs (P&IDs) |  | 30 | 04-Aug-25 A | 2025-11-14
EN-PR-100 | Receive and Review Existing FIDs | 0 | 04-Aug-25 A | 07-Aug-25 A
EN-PR-125 | Process Data - Chiller / WSAC Study | 0 | 14-Aug-25 A | 25-Aug-25 A
EN-PR-105 | Draft FIDs - IFR (Existing Equipment) | 0 | 14-Aug-25 A | 29-Aug-25 A
EN-PR-140 | Process Data - Fuel Gas System (LC Filters / FG Cntl Valve) - DS by end of this week | 0 | 25-Aug-25 A | 29-Aug-25 A
EN-PR-110 | FIDs - Review (Existing Equipment) | 0 | 02-Sep-25 A | 03-Sep-25 A
EN-PR-155 | Process Data - Cooling System (Cooling Tower for Generators / Air Cooled Closed System Glycol for Turbine) | 0 | 25-Aug-25 A | 08-Sep-25 A
EN-PR-130 | Draft P&IDs - IFR (Simple Cycle Complete Set) | 0 | 01-Sep-25 A | 26-Sep-25 A
EN-PR-145 | Process Data - Water Systems (Well Water / Demin Water) pending TM 2500 | 0 | 25-Aug-25 A | 2025-10-06
EN-PR-135 | P&IDs - Review (Simple Cycle Complete Set) | 5 | 29-Sep-25 A | 2025-10-10
EN-PR-115 | P&IDs - Pick up Comments and IFD (Simple Cycle Complete Set) | 15 | 2025-10-13 | 2025-10-31
EN-PR-120 | P&IDs - IFC | 10 | 2025-11-03 | 2025-11-14
Civil |  | 25 | 21-Jul-25 A | 2025-11-07
EN-CS-125 | Engineering and Design Steel Supports / Ladders / Handrails / Platforms | 2 | 22-Sep-25 A | 2025-10-07
General |  | 25 | 21-Jul-25 A | 2025-11-07
EN-CV-100 | 3D Modeling - Civil Modeling | 25 | 21-Jul-25 A | 2025-11-07
Piles |  | 13 | 04-Sep-25 A | 2025-10-22
EN-ST-150 | Pile Schedule (Drilled Piers) - IFR | 3 | 04-Sep-25 A | 2025-10-08
EN-ST-485 | Pile Schedule (Drilled Piers) - IFC | 10 | 2025-10-09 | 2025-10-22
CT #1 |  | 0 | 21-Jul-25 A | 19-Sep-25 A
EN-CS-105 | Engineering and Design Foundations for GT #1 & Skids - IFR | 0 | 21-Jul-25 A | 03-Sep-25 A
EN-CS-120 | Engineering and Design Foundations for GT #1 & Skids - IFC | 0 | 04-Sep-25 A | 19-Sep-25 A
CT #2 |  | 0 | 04-Aug-25 A | 19-Sep-25 A
EN-CS-110 | Engineering and Design Foundations for GT #2 & Skids - IFR | 0 | 04-Aug-25 A | 03-Sep-25 A
EN-CS-130 | Engineering and Design Foundations for GT #2 & Skids - IFC | 0 | 04-Sep-25 A | 19-Sep-25 A
CT #3 |  | 0 | 04-Aug-25 A | 19-Sep-25 A
EN-CS-115 | Engineering and Design Foundations for GT #3 & Skids - IFR | 0 | 04-Aug-25 A | 03-Sep-25 A
EN-CS-135 | Engineering and Design Foundations for GT #3 & Skids - IFC | 0 | 04-Sep-25 A | 19-Sep-25 A
SCR #1 |  | 10 | 22-Sep-25 A | 2025-10-17
EN-ST-155 | Engineering and Design Foundations for SCR #1 & Skids - IFR | 3 | 22-Sep-25 A | 2025-10-08
EN-ST-165 | Engineering and Design Foundations for SCR #1 & Skids - Pick up Comments | 5 | 2025-10-09 | 2025-10-15
EN-ST-160 | Engineering and Design Foundations for SCR #1 & Skids - IFC | 2 | 2025-10-16 | 2025-10-17
SCR #2 |  | 10 | 22-Sep-25 A | 2025-10-17
EN-ST-170 | Engineering and Design Foundations for SCR #2 & Skids - IFR | 3 | 22-Sep-25 A | 2025-10-08
EN-ST-175 | Engineering and Design Foundations for SCR #2 & Skids - Pick up Comments | 5 | 2025-10-09 | 2025-10-15
EN-ST-180 | Engineering and Design Foundations for SCR #2 & Skids - IFC | 2 | 2025-10-16 | 2025-10-17
SCR #3 |  | 10 | 22-Sep-25 A | 2025-10-17
EN-ST-185 | Engineering and Design Foundations for SCR #3 & Skids - IFR | 3 | 22-Sep-25 A | 2025-10-08
EN-ST-190 | Engineering and Design Foundations for SCR #3 & Skids - Pick up Comments | 5 | 2025-10-09 | 2025-10-15
EN-ST-195 | Engineering and Design Foundations for SCR #3 & Skids - IFC | 2 | 2025-10-16 | 2025-10-17
GSUs |  | 10 | 22-Sep-25 A | 2025-10-17
EN-ST-200 | Engineering and Design Foundations for GSUs - IFR | 3 | 22-Sep-25 A | 2025-10-08
EN-ST-205 | Engineering and Design Foundations for GSUs - Pick up Comments | 5 | 2025-10-09 | 2025-10-15
EN-ST-210 | Engineering and Design Foundations for GSUs - IFC | 2 | 2025-10-16 | 2025-10-17
Auxillary Transformers |  | 10 | 22-Sep-25 A | 2025-10-17
EN-ST-215 | Engineering and Design Foundations for Auxillary Transformers - IFR | 3 | 22-Sep-25 A | 2025-10-08
EN-ST-220 | Engineering and Design Foundations for Auxillary Transformers - Pick up Comments | 5 | 2025-10-09 | 2025-10-15
EN-ST-225 | Engineering and Design Foundations for Auxillary Transformers - IFC | 2 | 2025-10-16 | 2025-10-17
Tempering Fans (3) |  | 25 | 22-Sep-25 A | 2025-11-07
EN-ST-230 | Engineering and Design Foundations for Tempering Fans (3) - IFR | 15 | 22-Sep-25 A | 2025-10-24
EN-ST-235 | Engineering and Design Foundations for Tempering Fans (3) - Pick up Comments | 4 | 2025-10-27 | 2025-10-30
EN-ST-240 | Engineering and Design Foundations for Tempering Fans (3) - IFC | 6 | 2025-10-31 | 2025-11-07
Dilution Skid for SCR (3) |  | 10 | 22-Sep-25 A | 2025-10-17
EN-ST-245 | Engineering and Design Foundations for Dilution Skid for SCR (3) - IFR | 3 | 22-Sep-25 A | 2025-10-08
EN-ST-250 | Engineering and Design Foundations for Dilution Skid for SCR (3) - Pick up Comments | 4 | 2025-10-09 | 2025-10-14
EN-ST-255 | Engineering and Design Foundations for Dilution Skid for SCR (3) - IFC | 3 | 2025-10-15 | 2025-10-17
Water Injection Skids (3) |  | 25 | 22-Sep-25 A | 2025-11-07
EN-ST-260 | Engineering and Design Foundations for Water Injection Skids (3) - IFR | 15 | 22-Sep-25 A | 2025-10-24
EN-ST-265 | Engineering and Design Foundations for Water Injection Skids (3) - Pick up Comments | 5 | 2025-10-27 | 2025-10-31
EN-ST-270 | Engineering and Design Foundations for Water Injection Skids (3) - IFC | 5 | 2025-11-03 | 2025-11-07
Ring Wall Tanks (Demin Water / Raw Water) |  | 15 | 2025-10-20 | 2025-11-07
EN-ST-275 | Engineering and Design Foundations for Ring Wall Tanks - IFR | 5 | 2025-10-20 | 2025-10-24
EN-ST-280 | Engineering and Design Foundations for Ring Wall Tanks - Pick up Comments | 5 | 2025-10-27 | 2025-10-31
EN-ST-285 | Engineering and Design Foundations for Ring Wall Tanks - IFC | 5 | 2025-11-03 | 2025-11-07
Water Wash Skid |  | 15 | 2025-10-20 | 2025-11-07
EN-ST-335 | Engineering and Design Foundations for Water Wash Skid - IFR | 5 | 2025-10-20 | 2025-10-24
EN-ST-340 | Engineering and Design Foundations for Water Wash Skid - Pick up Comments | 4 | 2025-10-27 | 2025-10-30
EN-ST-345 | Engineering and Design Foundations for Water Wash Skid - IFC | 6 | 2025-10-31 | 2025-11-07
Ammonia Dilution Skid |  | 10 | 29-Sep-25 A | 2025-10-17
EN-ST-425 | Engineering and Design Foundations for Ammonia Dilution Skid - IFR | 3 | 29-Sep-25 A | 2025-10-08
EN-ST-430 | Engineering and Design Foundations for Ammonia Dilution Skid - Pick up Comments | 4 | 2025-10-09 | 2025-10-14
EN-ST-435 | Engineering and Design Foundations for Ammonia Dilution Skid - IFC | 3 | 2025-10-15 | 2025-10-17
CT Control Modules |  | 17 | 2025-10-16 | 2025-11-07
EN-ST-410 | Engineering and Design Foundations for CT Control Modules - IFR | 7 | 2025-10-16 | 2025-10-24
EN-ST-415 | Engineering and Design Foundations for CT Control Modules - Pick up Comments | 4 | 2025-10-27 | 2025-10-30
EN-ST-420 | Engineering and Design Foundations for CT Control Modules - IFC | 6 | 2025-10-31 | 2025-11-07
MCC Building |  | 17 | 2025-10-16 | 2025-11-07
EN-ST-395 | Engineering and Design Foundations for MCC Building - IFR | 7 | 2025-10-16 | 2025-10-24
EN-ST-400 | Engineering and Design Foundations for MCC Building - Pick up Comments | 5 | 2025-10-27 | 2025-10-31
EN-ST-405 | Engineering and Design Foundations for MCC Building - IFC | 5 | 2025-11-03 | 2025-11-07
Air Compressor Package |  | 17 | 2025-10-16 | 2025-11-07
EN-ST-380 | Engineering and Design Foundations for Air Compressor Package - IFR | 7 | 2025-10-16 | 2025-10-24
EN-ST-385 | Engineering and Design Foundations for Air Compressor Package - Pick up Comments | 4 | 2025-10-27 | 2025-10-30
EN-ST-390 | Engineering and Design Foundations for Air Compressor Package - IFC | 6 | 2025-10-31 | 2025-11-07
MEE Fog Skids (3) |  | 10 | 29-Sep-25 A | 2025-10-17
EN-ST-365 | Engineering and Design Foundations for MEE Fog Skids (3) - IFR | 3 | 29-Sep-25 A | 2025-10-08
EN-ST-370 | Engineering and Design Foundations for MEE Fog Skids (3) - Pick up Comments | 4 | 2025-10-09 | 2025-10-14
EN-ST-375 | Engineering and Design Foundations for MEE Fog Skids (3) - IFC | 3 | 2025-10-15 | 2025-10-17
Structrual Steel |  | 48 | 08-Sep-25 A | 2025-12-10
EN-ST-100 | 3D Modeling - Structural Steel (Main Members) | 25 | 08-Sep-25 A | 2025-11-07
EN-ST-125 | 3D Modeling - Structural Steel (Remaining Steel) | 10 | 2025-11-10 | 2025-11-21
Helical Piles |  | 0 | 15-Sep-25 A | 03-Oct-25 A
EN-ST-490 | Helical Piles - Pile Schedule with Reactions IFB (Connection Details included) | 0 | 15-Sep-25 A | 03-Oct-25 A
EN-ST-495 | Helical Piles - SOW and Bid Package | 0 | 02-Oct-25 A | 03-Oct-25 A
Pipe Rack Steel |  | 8 | 15-Sep-25 A | 2025-11-19
EN-ST-105 | Main Steel BOM / Steel Model for Bidders | 0 | 15-Sep-25 A | 22-Sep-25 A
EN-ST-110 | Main Steel Issue Main Steel Dwgs - IFA | 3 | 2025-11-10 | 2025-11-12
EN-ST-115 | Main Steel Issue Main Steel Dwgs - Pick up Comments | 2 | 2025-11-13 | 2025-11-14
EN-ST-120 | Main Steel Issue Main Steel Dwgs - IFC | 3 | 2025-11-17 | 2025-11-19
Misc Supports |  | 18 | 2025-11-17 | 2025-12-10
EN-ST-145 | Remaining Steel BOM | 3 | 2025-11-17 | 2025-11-19
EN-ST-130 | Remaining Steel Issue Main Steel Dwgs - IFA | 3 | 2025-11-24 | 2025-11-26
EN-ST-135 | Remaining Steel Issue Main Steel Dwgs - Pick up Comments | 5 | 2025-11-27 | 2025-12-03
EN-ST-140 | Remaining Steel Issue Main Steel Dwgs - IFC | 5 | 2025-12-04 | 2025-12-10
Mechanical |  | 88 | 20-Jul-25 A | 2026-02-04
Lists |  | 30 | 04-Aug-25 A | 2025-11-14
EN-ME-100 | Generate Equipment List - IFR Rev0 | 0 | 04-Aug-25 A | 13-Aug-25 A
EN-ME-555 | Generate Equipment List - IFR Rev1 | 0 | 14-Aug-25 A | 22-Aug-25 A
EN-ME-635 | Generate Valve List (Control Valves for Simple Cycle) | 0 | 01-Sep-25 A | 05-Sep-25 A
EN-ME-560 | Generate Equipment List - IFR Rev 2 (wCooling System) | 0 | 25-Aug-25 A | 12-Sep-25 A
EN-ME-410 | Generate Pipe Specs - For Record | 0 | 11-Aug-25 A | 2025-10-06
EN-ME-645 | Manual Valve List (Simple Cycle) | 10 | 2025-10-27 | 2025-11-07
EN-ME-105 | Generate Line List | 2 | 2025-11-10 | 2025-11-11
EN-ME-640 | Generate Valve List (Control Valves for Combined Cycle) | 5 | 2025-11-10 | 2025-11-14
Equipment Requisitions |  | 88 | 20-Jul-25 A | 2026-02-04
HRSG |  | 88 | 20-Jul-25 A | 2026-02-04
EN-ME-110 | HRSG - Develop Requisition and Issue for Quote | 0 | 20-Jul-25 A | 24-Jul-25 A
EN-ME-115 | HRSG - Recieve Quote | 0 | 25-Jul-25 A | 26-Aug-25 A
EN-ME-120 | HRSG - Evaluate and Issue Requisition for Purchase | 3 | 04-Aug-25 A | 2025-10-08
EN-ME-125 | HRSG - Issue Purchase Order | 5 | 2025-10-09 | 2025-10-15
EN-ME-130 | HRSG - Receive GAs | 15 | 2025-10-16 | 2025-11-05
EN-ME-135 | HRSG - Receive P&IDs and One Lines | 25 | 2025-11-06 | 2025-12-10
EN-ME-140 | HRSG - Ready To Ship | 60 | 2025-10-16 | 2026-01-07
EN-ME-145 | HRSG - Deliver to Site | 20 | 2026-01-08 | 2026-02-04
SCR (Tempering Fans (3) / Ammonia Inj Pumps (3) / Power for CEMs) |  | 85 | 21-Jul-25 A | 2026-01-30
EN-ME-155 | SCR - Recieve Quote | 0 | 21-Jul-25 A | 24-Jul-25 A
EN-ME-160 | SCR - Evaluate and Issue Requisition for Purchase | 0 | 25-Jul-25 A | 18-Aug-25 A
EN-ME-165 | SCR - Issue Purchase Order | 0 | 18-Aug-25 A | 22-Aug-25 A
EN-ME-170 | SCR - Receive GAs | 0 | 25-Aug-25 A | 12-Sep-25 A
EN-ME-175 | SCR - Receive P&IDs and One Lines | 10 | 15-Sep-25 A | 2025-10-17
EN-ME-180 | SCR - Ready To Ship (All Ducting and stack) | 80 | 22-Sep-25 A | 2026-01-23
EN-ME-185 | SCR - Deliver to Site (All Ducting and stack) | 5 | 2026-01-26 | 2026-01-30
GSU (GTs T1 / T2 / T3) |  | 20 | 28-Jul-25 A | 2025-10-31
EN-ME-220 | GSU GTs - Ready To Ship | 0 | 28-Jul-25 A | 2025-10-06
EN-ME-225 | GSU GTs - Deliver to Site | 20 | 2025-10-06 | 2025-10-31
Transformers - Step Down (2) AT-1 / AT-2 |  | 55 | 04-Aug-25 A | 2025-12-19
EN-ME-265 | Step Down XMR AT-1 / AT-2 - Develop Requisition and Issue for Quote | 0 | 04-Aug-25 A | 06-Aug-25 A
EN-ME-270 | Step Down XMR AT-1 / AT-2 - Recieve Quote | 0 | 07-Aug-25 A | 14-Aug-25 A
EN-ME-275 | Step Down XMR AT-1 / AT-2 - Evaluate and Issue Requisition for Purchase | 0 | 15-Aug-25 A | 21-Aug-25 A
EN-ME-280 | Step Down XMR AT-1 / AT-2 - Issue Purchase Order | 0 | 22-Aug-25 A | 22-Sep-25 A
EN-ME-285 | Step Down XMR AT-1 / AT-2 - Receive GAs | 6 | 23-Sep-25 A | 2025-10-13
EN-ME-290 | Step Down XMR AT-1 / AT-2 - Ready To Ship | 50 | 22-Sep-25 A | 2025-12-12
EN-ME-295 | Step Down XMR AT-1 / AT-2 - Deliver to Site | 5 | 2025-12-15 | 2025-12-19
Transformers - Step Down (2) AT-11 / AT-21 |  | 56 | 04-Aug-25 A | 2025-12-22
EN-ME-315 | Step Down XMR AT-11 / AT-21 - Issue Purchase Order | 0 | 04-Aug-25 A | 15-Sep-25 A
EN-ME-325 | Step Down XMR AT-11 / AT-21 - Ready To Ship | 51 | 16-Sep-25 A | 2025-12-15
EN-ME-330 | Step Down XMR AT-11 / AT-21 - Deliver to Site | 5 | 2025-12-16 | 2025-12-22
Demin Skid Trailers (Rental) |  | 48 | 25-Aug-25 A | 2025-12-10
EN-ME-520 | Demin Skid Trailers (Rental) - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 2025-10-06
EN-ME-525 | Demin Skid Trailers (Rental) - Recieve Quote | 5 | 2025-10-06 | 2025-10-10
EN-ME-530 | Demin Skid Trailers (Rental) - Evaluate and Issue Requisition for Purchase | 5 | 2025-10-13 | 2025-10-17
EN-ME-535 | Demin Skid Trailers (Rental) - Issue Purchase Order | 3 | 2025-10-20 | 2025-10-22
EN-ME-540 | Demin Skid Trailers (Rental) - Receive GAs | 10 | 2025-10-23 | 2025-11-05
EN-ME-545 | Demin Skid Trailers (Rental) - Ready To Ship | 30 | 2025-10-23 | 2025-12-03
EN-ME-550 | Demin Skid Trailers (Rental) - Deliver to Site | 5 | 2025-12-04 | 2025-12-10
Wet Surface Air Cooler (WSAC) |  | 55 | 25-Aug-25 A | 2025-12-19
EN-ME-375 | WSAC Package - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 27-Aug-25 A
EN-ME-380 | WSAC Package - Recieve Quote | 0 | 22-Sep-25 A | 26-Sep-25 A
EN-ME-385 | WSAC Package - Evaluate and Issue Requisition for Purchase | 5 | 2025-10-06 | 2025-10-10
EN-ME-390 | WSAC Package - Issue Purchase Order | 5 | 2025-10-13 | 2025-10-17
EN-ME-395 | WSAC Package - Receive GAs | 15 | 2025-10-20 | 2025-11-07
EN-ME-400 | WSAC Package - Ready To Ship | 40 | 2025-10-20 | 2025-12-12
EN-ME-405 | WSAC Package - Deliver to Site | 5 | 2025-12-15 | 2025-12-19
Drain Transfer Pump - Centrifugal |  | 80 | 2025-10-06 | 2026-01-23
EN-ME-450 | Oily Water Pumps - Develop Requisition and Issue for Quote | 5 | 2025-10-06 | 2025-10-10
EN-ME-455 | Oily Water Pumps - Recieve Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-460 | Oily Water Pumps - Evaluate and Issue Requisition for Purchase | 5 | 2025-10-27 | 2025-10-31
EN-ME-465 | Oily Water Pumps - Issue Purchase Order | 5 | 2025-11-03 | 2025-11-07
EN-ME-470 | Oily Water Pumps - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-475 | Oily Water Pumps - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-480 | Oily Water Pumps - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
MCCs |  | 70 | 2025-10-13 | 2026-01-16
EN-ME-415 | MCCs - Develop Requisition and Issue for Quote | 5 | 2025-10-13 | 2025-10-17
EN-ME-420 | MCCs - Recieve Quote | 5 | 2025-10-20 | 2025-10-24
EN-ME-425 | MCCs - Evaluate and Issue Requisition for Purchase | 5 | 2025-10-27 | 2025-10-31
EN-ME-430 | MCCs - Issue Purchase Order | 5 | 2025-11-03 | 2025-11-07
EN-ME-435 | MCCs - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-440 | MCCs - Ready To Ship | 40 | 2025-11-10 | 2026-01-02
EN-ME-445 | MCCs - Deliver to Site | 10 | 2026-01-05 | 2026-01-16
RO Water Storage Tank |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-650 | RO Water Storage Tank - Develop Requisition and Issue for Quote | 0 | 2025-10-13 | 2025-10-13
EN-ME-655 | RO Water Storage Tank - Recieve Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-660 | RO Water Storage Tank - Evaluate and Issue Requisition for Purchase | 5 | 2025-10-27 | 2025-10-31
EN-ME-665 | RO Water Storage Tank - Issue Purchase Order | 5 | 2025-11-03 | 2025-11-07
EN-ME-670 | RO Water Storage Tank - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-675 | RO Water Storage Tank - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-680 | RO Water Storage Tank - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Instrument Air Package |  | 80 | 2025-10-13 | 2026-01-30
EN-ME-720 | Instrument Air Package - Develop Requisition and Issue for Quote | 5 | 2025-10-13 | 2025-10-17
EN-ME-725 | Instrument Air Package - Recieve Quote | 10 | 2025-10-20 | 2025-10-31
EN-ME-730 | Instrument Air Package - Evaluate and Issue Requisition for Purchase | 5 | 2025-11-03 | 2025-11-07
EN-ME-735 | Instrument Air Package - Issue Purchase Order | 5 | 2025-11-10 | 2025-11-14
EN-ME-740 | Instrument Air Package - Receive GAs | 15 | 2025-11-17 | 2025-12-05
EN-ME-745 | Instrument Air Package - Ready To Ship | 50 | 2025-11-17 | 2026-01-23
EN-ME-750 | Instrument Air Package - Deliver to Site | 5 | 2026-01-26 | 2026-01-30
Last Chance Filters |  | 60 | 25-Aug-25 A | 2025-12-26
EN-ME-600 | Last Chance Filters - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 17-Sep-25 A
EN-ME-605 | Last Chance Filters - Recieve Quote | 0 | 18-Sep-25 A | 2025-10-06
EN-ME-610 | Last Chance Filters - Evaluate and Issue Requisition for Purchase | 2 | 2025-10-06 | 2025-10-07
EN-ME-615 | Last Chance Filters - Issue Purchase Order | 3 | 2025-10-08 | 2025-10-10
EN-ME-620 | Last Chance Filters - Receive GAs | 15 | 2025-10-13 | 2025-10-31
EN-ME-625 | Last Chance Filters - Ready To Ship | 50 | 2025-10-13 | 2025-12-19
EN-ME-630 | Last Chance Filters - Deliver to Site | 5 | 2025-12-22 | 2025-12-26
Fuel Gas Let Down Skid |  | 60 | 25-Aug-25 A | 2025-12-26
EN-ME-565 | Fuel Gas Package (includes Controls) - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 18-Sep-25 A
EN-ME-570 | Fuel Gas Package (includes Controls) - Recieve Quote | 0 | 19-Sep-25 A | 2025-10-06
EN-ME-575 | Fuel Gas Package (includes Controls) - Evaluate and Issue Requisition for Purchase | 2 | 2025-10-06 | 2025-10-07
EN-ME-580 | Fuel Gas Package (includes Controls) - Issue Purchase Order | 3 | 2025-10-08 | 2025-10-10
EN-ME-585 | Fuel Gas Package (includes Controls) - Receive GAs | 15 | 2025-10-13 | 2025-10-31
EN-ME-590 | Fuel Gas Package (includes Controls) - Ready To Ship | 50 | 2025-10-13 | 2025-12-19
EN-ME-595 | Fuel Gas Package (includes Controls) - Deliver to Site | 5 | 2025-12-22 | 2025-12-26
Control Module Skid / Gas Turbines (Refurbish) |  | 65 | 25-Aug-25 A | 2026-01-16
EN-ME-755 | Control Module Skid / Gas Turbines (Refurbish) - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 2025-10-20
EN-ME-760 | Control Module Skid / Gas Turbines (Refurbish) - Recieve Quote | 5 | 2025-10-20 | 2025-10-24
EN-ME-765 | Control Module Skid / Gas Turbines (Refurbish) - Evaluate and Issue Requisition for Purchase | 2 | 2025-10-27 | 2025-10-28
EN-ME-770 | Control Module Skid / Gas Turbines (Refurbish) - Issue Purchase Order | 3 | 2025-10-29 | 2025-10-31
EN-ME-775 | Control Module Skid / Gas Turbines (Refurbish) - Receive GAs | 15 | 2025-11-03 | 2025-11-21
EN-ME-780 | Control Module Skid / Gas Turbines (Refurbish) - Ready To Ship | 50 | 2025-11-03 | 2026-01-09
EN-ME-785 | Control Module Skid / Gas Turbines (Refurbish) - Deliver to Site | 5 | 2026-01-12 | 2026-01-16
Aftercooler |  | 65 | 2025-10-13 | 2026-01-09
EN-ME-790 | Aftercooler - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-795 | Aftercooler - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-800 | Aftercooler - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-805 | Aftercooler - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-810 | Aftercooler - Receive GAs | 10 | 2025-11-10 | 2025-11-21
EN-ME-815 | Aftercooler - Ready To Ship | 40 | 2025-11-10 | 2026-01-02
EN-ME-820 | Aftercooler - Deliver to Site | 5 | 2026-01-05 | 2026-01-09
Raw / Service Water Storage Tank |  | 55 | 2025-10-13 | 2025-12-26
EN-ME-895 | Raw / Service Water Storage Tank - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-900 | Raw / Service Water Storage Tank - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-905 | Raw / Service Water Storage Tank - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-910 | Raw / Service Water Storage Tank - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-915 | Raw / Service Water Storage Tank - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-920 | Raw / Service Water Storage Tank - Ready To Ship | 30 | 2025-11-10 | 2025-12-19
EN-ME-925 | Raw / Service Water Storage Tank - Deliver to Site | 5 | 2025-12-22 | 2025-12-26
Service Water Pumps |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-930 | Service Water Pumps - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-935 | Service Water Pumps - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-940 | Service Water Pumps - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-945 | Service Water Pumps - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-950 | Service Water Pumps - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-955 | Service Water Pumps - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-960 | Service Water Pumps - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Desuperheater Water Injection Skid (Refurbish) |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1070 | Desuperheater Water Injection Skid (Refurb) - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1075 | Desuperheater Water Injection Skid (Refurb) - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1080 | Desuperheater Water Injection Skid (Refurb) - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1085 | Desuperheater Water Injection Skid (Refurb) - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1090 | Desuperheater Water Injection Skid (Refurb) - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1095 | Desuperheater Water Injection Skid (Refurb) - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1100 | Desuperheater Water Injection Skid (Refurb) - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Water Injection Pump (Refurbish) |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1105 | Water Injection Pump (Refurb) - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1110 | Water Injection Pump (Refurb) - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1115 | Water Injection Pump (Refurb) - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1120 | Water Injection Pump (Refurb) - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1125 | Water Injection Pump (Refurb) - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1130 | Water Injection Pump (Refurb) - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1135 | Water Injection Pump (Refurb) - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
IP Steam Silencer (Refurbish) |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1140 | IP Steam Silencer (Refurb) - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1145 | IP Steam Silencer (Refurb) - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1150 | IP Steam Silencer (Refurb) - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1155 | IP Steam Silencer (Refurb) - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1160 | IP Steam Silencer (Refurb) - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1165 | IP Steam Silencer (Refurb) - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1170 | IP Steam Silencer (Refurb) - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
HRSG Dearator (Refurbish) |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1175 | HRSG Dearator (Refurb) - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1180 | HRSG Dearator (Refurb) - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1185 | HRSG Dearator (Refurb) - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1190 | HRSG Dearator (Refurb) - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1195 | HRSG Dearator (Refurb) - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1200 | HRSG Dearator (Refurb) - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1205 | HRSG Dearator (Refurb) - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
CEMS |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1210 | CEMS - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1215 | CEMS - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1220 | CEMS - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1225 | CEMS - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1230 | CEMS - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1235 | CEMS - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1240 | CEMS - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Inlet Air Filter |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1245 | Inlet Air Filter - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1250 | Inlet Air Filter - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1255 | Inlet Air Filter - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1260 | Inlet Air Filter - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1265 | Inlet Air Filter - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1270 | Inlet Air Filter - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1275 | Inlet Air Filter - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Dearator Pump |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1315 | Dearator Pump - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1320 | Dearator Pump - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1325 | Dearator Pump - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1330 | Dearator Pump - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1335 | Dearator Pump - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1340 | Dearator Pump - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1345 | Dearator Pump - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Saturated Boiler |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1350 | Saturated Boiler - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1355 | Saturated Boiler - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1360 | Saturated Boiler - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1365 | Saturated Boiler - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1370 | Saturated Boiler - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1375 | Saturated Boiler - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1380 | Saturated Boiler - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Superheat Boiler |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1385 | Superheat Boiler - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1390 | Superheat Boiler - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1395 | Superheat Boiler - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1400 | Superheat Boiler - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1405 | Superheat Boiler - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1410 | Superheat Boiler - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1415 | Superheat Boiler - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Lube Oil Storage Tanks |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1420 | Lube Oil Storage Tanks - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1425 | Lube Oil Storage Tanks - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1430 | Lube Oil Storage Tanks - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1435 | Lube Oil Storage Tanks - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1440 | Lube Oil Storage Tanks - Receive GAs | 10 | 2025-11-10 | 2025-11-21
EN-ME-1445 | Lube Oil Storage Tanks - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1450 | Lube Oil Storage Tanks - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Lube Oil Transfer Pump |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1455 | Lube Oil Transfer Pump - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1460 | Lube Oil Transfer Pump - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1465 | Lube Oil Transfer Pump - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1470 | Lube Oil Transfer Pump - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1475 | Lube Oil Transfer Pump - Receive GAs | 10 | 2025-11-10 | 2025-11-21
EN-ME-1480 | Lube Oil Transfer Pump - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1485 | Lube Oil Transfer Pump - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Lube Oil Conditioner |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1490 | Lube Oil Conditioner - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1495 | Lube Oil Conditioner - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1500 | Lube Oil Conditioner - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1505 | Lube Oil Conditioner - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1510 | Lube Oil Conditioner - Receive GAs | 10 | 2025-11-10 | 2025-11-21
EN-ME-1515 | Lube Oil Conditioner - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1520 | Lube Oil Conditioner - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Control System |  | 75 | 2025-10-13 | 2026-01-23
EN-ME-1665 | Control System - Develop Requisition and Issue for Quote | 10 | 2025-10-13 | 2025-10-24
EN-ME-1670 | Control System - Recieve Quote | 5 | 2025-10-27 | 2025-10-31
EN-ME-1675 | Control System - Evaluate and Issue Requisition for Purchase | 2 | 2025-11-03 | 2025-11-04
EN-ME-1680 | Control System - Issue Purchase Order | 3 | 2025-11-05 | 2025-11-07
EN-ME-1685 | Control System - Receive GAs | 15 | 2025-11-10 | 2025-11-28
EN-ME-1690 | Control System - Ready To Ship | 50 | 2025-11-10 | 2026-01-16
EN-ME-1695 | Control System - Deliver to Site | 5 | 2026-01-19 | 2026-01-23
Piping |  | 25 | 21-Jul-25 A | 2025-11-07
3D Scanning and Modeling |  | 6 | 29-Jul-25 A | 2025-10-10
EN-PP-120 | 3D Modeling (from scan and new site) | 0 | 29-Jul-25 A | 15-Aug-25 A
EN-PP-145 | Piping BOM - UG Water / Fuel Gas (from TP to West edge of PR) | 0 | 19-Aug-25 A | 2025-10-04
EN-PP-135 | 3D Modeling New SIte | 6 | 19-Aug-25 A | 2025-10-10
Plot Plan |  | 2 | 21-Jul-25 A | 2025-10-07
EN-PP-105 | Plot Plan - Issue for Review | 0 | 11-Aug-25 A | 15-Aug-25 A
EN-PP-110 | Plot Plan Review | 0 | 18-Aug-25 A | 19-Aug-25 A
EN-PP-115 | Plot Plan - Issue for Design | 0 | 20-Aug-25 A | 22-Aug-25 A
EN-PP-140 | Plot Plan - Issue for Design Rev2 | 0 | 25-Aug-25 A | 19-Sep-25 A
EN-CS-100 | UG Pipe Layout | 0 | 21-Jul-25 A | 2025-10-04
EN-PP-125 | Plot Plan - Issue for Construction | 2 | 22-Sep-25 A | 2025-10-07
Lists |  | 10 | 2025-10-27 | 2025-11-07
EN-PP-100 | Generate Line List | 10 | 2025-10-27 | 2025-11-07
ISO Production |  | 20 | 2025-10-06 | 2025-10-31
EN-PP-130 | Drop ISOs for Check / IFC | 20 | 2025-10-06 | 2025-10-31
Electrical |  | 40 | 27-Jul-25 A | 2025-11-28
Load List and One-Lines |  | 15 | 27-Jul-25 A | 2025-11-07
EN-EL-105 | Develop Load List | 0 | 27-Jul-25 A | 06-Aug-25 A
EN-EL-110 | Develop One Lines - Key | 0 | 28-Jul-25 A | 06-Aug-25 A
EN-EL-135 | Develop One Lines - Detail (Preliminary - work in progress) | 0 | 07-Aug-25 A | 01-Sep-25 A
EN-EL-155 | Develop One Lines - Detail IFD | 15 | 02-Sep-25 A | 2025-11-07
Conduit & Cable Schedule |  | 30 | 18-Aug-25 A | 2025-11-14
EN-EL-140 | Main Cable BOM | 15 | 18-Aug-25 A | 2025-10-24
EN-EL-115 | Develop and Issue Cable Schedule | 10 | 18-Aug-25 A | 2025-11-14
Grounding Plans and Details |  | 7 | 25-Aug-25 A | 2025-10-14
EN-EL-100 | Develop and Issue Grounding Plans and Details | 7 | 25-Aug-25 A | 2025-10-14
Area Classification |  | 7 | 25-Aug-25 A | 2025-10-14
EN-EL-160 | Area Classification IFR | 0 | 25-Aug-25 A | 2025-10-06
EN-EL-165 | Area Classification IFC | 5 | 2025-10-08 | 2025-10-14
Cable Tray Plans and Details |  | 15 | 19-Sep-25 A | 2025-11-24
EN-EL-145 | Modeling for Building / Racks / layout from piping | 0 |  | 19-Sep-25 A
EN-EL-150 | Cable Tray BOM (identified Long Leads) | 5 | 2025-11-12 | 2025-11-18
EN-EL-120 | Develop and Issue Cable Tray Plans and Details | 15 | 2025-11-04 | 2025-11-24
Lighting Plans and Details |  | 15 | 2025-10-08 | 2025-10-28
EN-EL-125 | Develop and Issue Lighting Plans and Details | 15 | 2025-10-08 | 2025-10-28
Motor Schematics |  | 10 | 2025-11-17 | 2025-11-28
EN-EL-130 | Develop and Issue Motor Schematics Vendor Docs +2weeks | 10 | 2025-11-17 | 2025-11-28
Instrumentation & Controls |  | 95 | 25-Aug-25 A | 2026-02-13
Instrument Index & IO List |  | 25 | 25-Aug-25 A | 2025-11-14
EN-IT-155 | Instrument Index and IO List - IFR | 0 | 25-Aug-25 A | 05-Sep-25 A
EN-IT-160 | Instrument Index and IO List - IFC | 25 | 25-Aug-25 A | 2025-11-14
Control Wiring Drawings |  | 20 | 25-Aug-25 A | 2025-11-14
EN-IT-170 | Control Drawings - IFR | 15 | 25-Aug-25 A | 2025-11-07
EN-IT-165 | Control Drawings - IFC | 5 | 2025-11-10 | 2025-11-14
Junction Box Drawings |  | 10 | 2025-11-10 | 2025-11-21
EN-IT-175 | Junction Box Drawings - IFR | 0 | 2025-11-10 | 2025-11-10
EN-IT-180 | Junction Box Drawings - IFC | 10 | 2025-11-10 | 2025-11-21
Wiring Drawings |  | 25 | 08-Sep-25 A | 2025-11-21
EN-IT-185 | Control / Wiring Drawings - IFR | 15 | 08-Sep-25 A | 2025-11-07
EN-IT-190 | Control / Wiring Drawings - IFC | 10 | 2025-11-10 | 2025-11-21
Instrument Location Plan |  | 9 | 26-Sep-25 A | 2025-10-16
EN-IT-195 | Instrument Location Plan - IFC | 9 | 26-Sep-25 A | 2025-10-16
FIIS |  | 10 | 2025-10-06 | 2025-10-17
EN-IT-205 | Field Instrument Installation Summary - IFC | 10 | 2025-10-06 | 2025-10-17
Instrument & Controls Requisitions |  | 75 | 2025-11-03 | 2026-02-13
PLC & HMI |  | 70 | 2025-11-10 | 2026-02-13
EN-IT-210 | PLC & HMI - Develop Requisition and Issue for Quote | 5 | 2025-11-10 | 2025-11-14
EN-IT-215 | PLC & HMI - Recieve Quote | 10 | 2025-11-17 | 2025-11-28
EN-IT-220 | PLC & HMI - Evaluate and Issue Requisition for Purchase | 5 | 2025-12-01 | 2025-12-05
EN-IT-225 | PLC & HMI - Issue Purchase Order | 5 | 2025-12-08 | 2025-12-12
EN-IT-235 | PLC & HMI - Ready To Ship | 40 | 2025-12-15 | 2026-02-06
EN-IT-240 | PLC & HMI - Deliver to Site | 5 | 2026-02-09 | 2026-02-13
Misc Instrumentation |  | 70 | 2025-11-03 | 2026-02-06
EN-IT-245 | Misc Instrumentation - Develop Requisition and Issue for Quote | 5 | 2025-11-03 | 2025-11-07
EN-IT-250 | Misc Instrumentation - Recieve Quote | 10 | 2025-11-10 | 2025-11-21
EN-IT-255 | Misc Instrumentation - Evaluate and Issue Requisition for Purchase | 5 | 2025-11-24 | 2025-11-28
EN-IT-260 | Misc Instrumentation - Issue Purchase Order | 5 | 2025-12-01 | 2025-12-05
EN-IT-265 | Misc Instrumentation - Ready To Ship | 40 | 2025-12-08 | 2026-01-30
EN-IT-270 | Misc Instrumentation - Deliver to Site | 5 | 2026-02-02 | 2026-02-06
Procurement |  | 80 | 22-Sep-25 A | 2026-01-23
Bulk Material & Fabrication |  | 80 | 22-Sep-25 A | 2026-01-23
Civil Material |  | 32 | 2025-10-06 | 2025-11-18
PR-1065 | Civil Material - RFQ issued / Bids Received / Evaluated | 12 | 2025-10-06 | 2025-10-21
PR-1075 | Civil Material - Issue PO to Vendor | 2 | 2025-10-22 | 2025-10-23
PR-1085 | Civil Material - Fab and receive Rebar | 12 | 2025-10-24 | 2025-11-10
PR-1095 | Civil Material - Fab and receive Anchor Bolts | 18 | 2025-10-24 | 2025-11-18
Helical Piles |  | 30 | 03-Oct-25 A | 2025-11-14
PR-1260 | Helical Piles - RFQ issued / Bids Received / Evaluated / WPS approved | 7 | 03-Oct-25 A | 2025-10-14
PR-1265 | Helical Piles - Issue PO to Shop for Fabrication | 2 | 2025-10-15 | 2025-10-16
PR-1270 | Helical Piles - Fabricate | 18 | 2025-10-17 | 2025-11-11
PR-1275 | Helical Piles - shipped to Site | 12 | 2025-10-30 | 2025-11-14
Structural Steel |  | 60 | 2025-10-08 | 2025-12-30
PR-1105 | Structural Steel - RFQ issued / Bids Received / Evaluated / WPS approved | 12 | 2025-10-08 | 2025-10-23
PR-1115 | Structural Steel - Issue PO to Shop for Fabrication | 6 | 2025-10-24 | 2025-10-31
PR-1125 | Structural Steel - Fabricate Steel | 30 | 2025-11-03 | 2025-12-12
PR-1135 | Structural Steel shipped to Site | 30 | 2025-11-19 | 2025-12-30
Piping |  | 80 | 22-Sep-25 A | 2026-01-23
Field |  | 38 | 22-Sep-25 A | 2025-11-26
PR-1005 | Approve WPS (Field Welding) | 2 | 22-Sep-25 A | 2025-10-07
PR-1015 | Receive Field ISOs for Field work | 18 | 2025-11-03 | 2025-11-26
Shop |  | 72 | 2025-10-16 | 2026-01-23
PR-1025 | RFQ issued / Bids Received / Evaluated / WPS approved | 12 | 2025-10-16 | 2025-10-31
PR-1035 | Issue PO to Shop for Fabrication | 6 | 2025-11-03 | 2025-11-10
PR-1045 | Spool and Fabricate ISOs | 48 | 2025-11-11 | 2026-01-15
PR-1055 | Spools shipped to Site | 36 | 2025-12-05 | 2026-01-23
E&I |  | 59 | 2025-10-15 | 2026-01-05
Grounding |  | 30 | 2025-10-15 | 2025-11-25
PR-1145 | Grounding - RFQ issued / Bids Received / Evaluated | 12 | 2025-10-15 | 2025-10-30
PR-1155 | Grounding - Issue PO to Vendor | 6 | 2025-10-31 | 2025-11-07
PR-1165 | Grounding - Fab and receive on site | 12 | 2025-11-10 | 2025-11-25
Cable Tray |  | 30 | 2025-11-25 | 2026-01-05
PR-1205 | Cable Tray - RFQ issued / Bids Received / Evaluated | 12 | 2025-11-25 | 2025-12-10
PR-1215 | Cable Tray - Issue PO to Vendor | 6 | 2025-12-11 | 2025-12-18
PR-1225 | Cable Tray - Fab and receive on site | 12 | 2025-12-19 | 2026-01-05
Conduit & Cable |  | 36 | 2025-11-17 | 2026-01-05
PR-1175 | Conduit & Cable Schedule - RFQ issued / Bids Received / Evaluated | 12 | 2025-11-17 | 2025-12-02
PR-1185 | Conduit & Cable Schedule - Issue PO to Vendor | 6 | 2025-12-03 | 2025-12-10
PR-1195 | Conduit & Cable Schedule - Fab and receive on site | 18 | 2025-12-11 | 2026-01-05
Lighting |  | 36 | 2025-10-29 | 2025-12-17
PR-1235 | Lighting and Receptacles - RFQ issued / Bids Received / Evaluated | 12 | 2025-10-29 | 2025-11-13
PR-1245 | Lighting and Receptacles - Issue PO to Vendor | 6 | 2025-11-14 | 2025-11-21
PR-1255 | Lighting and Receptacles - Fab and receive on site | 18 | 2025-11-24 | 2025-12-17
Construction (On-Site) |  | 139 | 17-Sep-25 A | 2026-03-14
General |  | 36 | 17-Sep-25 A | 2025-11-14
CN-1395 | Survey and Benchmarks set (Park Hill) | 0 | 24-Sep-25 A | 26-Sep-25 A
CN-1495 | Construction Mobilization | 12 | 01-Oct-25 A | 2025-10-17
CN-1400 | Site Mobilization | 36 | 17-Sep-25 A | 2025-11-14
Site Work |  | 27 | 2025-10-18 | 2025-11-18
CN-1505 | Receive Equipment - Tie in CP's / Stake out Areas | 3 | 2025-10-18 | 2025-10-21
CN-1000 | Cut and Grub (4ft ) Laydown / Site | 12 | 2025-10-22 | 2025-11-04
CN-1500 | bathtub for foundations | 12 | 2025-11-05 | 2025-11-18
Temporary Facilities |  | 36 | 2025-10-04 | 2025-11-14
CN-1510 | Place Order for Trailers / Generators | 5 | 2025-10-04 | 2025-10-09
CN-1530 | Delivery of Trailers / Generators | 12 | 2025-10-18 | 2025-10-31
CN-1525 | Receive and Install Trailers | 3 | 2025-11-11 | 2025-11-13
CN-1515 | Install Generators | 12 | 2025-11-01 | 2025-11-14
Civil & Structural |  | 43 | 2025-11-12 | 2025-12-31
Drilled Piers |  | 18 | 2025-11-12 | 2025-12-02
CN-1540 | Install Drilled Piers | 18 | 2025-11-12 | 2025-12-02
GT #3 |  | 18 | 2025-11-19 | 2025-12-09
CN-1015 | GT #3 / SCR #3 - Survey / Excavate / Rebar / Formwork / Pour / Cure Time (3d break) | 18 | 2025-11-19 | 2025-12-09
GT #2 |  | 18 | 2025-11-26 | 2025-12-16
CN-1010 | GT #2 / SCR #2 - Survey / Excavate / Rebar / Formwork / Pour / Cure Time (3d break) | 18 | 2025-11-26 | 2025-12-16
GT #1 |  | 18 | 2025-12-03 | 2025-12-23
CN-1005 | GT #1 / SCR #1 - Survey / Excavate / Rebar / Formwork / Pour / Cure Time | 18 | 2025-12-03 | 2025-12-23
Remaining Foundations |  | 24 | 2025-11-19 | 2025-12-16
CN-1685 | Remaining Foundations - Survey / Excavate / Rebar / Formwork / Pour / Cure Time (3d break) | 24 | 2025-11-19 | 2025-12-16
Steel Supports |  | 40 | 2025-11-15 | 2025-12-31
CN-1740 | Helical Pile Installation | 8 | 2025-11-15 | 2025-11-24
CN-1745 | Pipe Rack Erection | 12 | 2025-11-25 | 2025-12-08
CN-1020 | Erect Misc PIpe and Electrical Supports | 18 | 2025-12-11 | 2025-12-31
Equipment |  | 78 | 2025-12-10 | 2026-03-10
GT #3 |  | 52 | 2025-12-10 | 2026-02-07
CN-1200 | Set and Install GT #3 MEE Fog Skid | 4 | 2025-12-17 | 2025-12-20
CN-1210 | Set and Install GT #3 Water Injection Skid | 6 | 2025-12-17 | 2025-12-23
CN-1230 | Set and Install GT #3 MCCs | 18 | 2025-12-17 | 2026-01-06
CN-1180 | Set and Install GT #3 Control Room / Building | 24 | 2025-12-17 | 2026-01-13
GT #3 Main Component Installation |  | 52 | 2025-12-10 | 2026-02-07
CN-1615 | Set and Install GT #3 - Install GAC | 3 | 2025-12-10 | 2025-12-12
CN-1600 | Set and Install GT #3 - Load Gear | 4 | 2025-12-10 | 2025-12-13
CN-1610 | Set and Install GT #3 - Set and Install Accessory skid (oil systems / pumps / atomizing air compressor) | 7 | 2025-12-10 | 2025-12-17
CN-1605 | Set and Install GT #3 - Set and Install Generator | 4 | 2026-01-12 | 2026-01-15
CN-1170 | Set and Install GT #3 - Turbine base Frame with Compressor / turbine / exhaust casings (split for transport) | 7 | 2026-01-17 | 2026-01-24
CN-1190 | Set and Install GT #3 - Inlet Air Filter | 2 | 2026-01-26 | 2026-01-27
CN-1620 | Set and Install GT #3 - Install SCR (exhaust stack sections) | 7 | 2026-01-31 | 2026-02-07
GT #2 |  | 72 | 2025-12-17 | 2026-03-10
CN-1140 | Set and Install GT #2 Water Injection Skid | 6 | 2025-12-17 | 2025-12-23
CN-1130 | Set and Install GT #2 MEE Fog Skid | 4 | 2025-12-24 | 2025-12-27
CN-1160 | Set and Install GT #2 MCCs | 18 | 2025-12-17 | 2026-01-06
CN-1110 | Set and Install GT #2 Control Room / Building | 24 | 2025-12-17 | 2026-01-13
GT #2 Main Component Installation |  | 72 | 2025-12-17 | 2026-03-10
CN-1645 | Set and Install GT #2 - Install GAC | 3 | 2025-12-17 | 2025-12-19
CN-1630 | Set and Install GT #2 - Load Gear | 4 | 2025-12-17 | 2025-12-20
CN-1640 | Set and Install GT #2 - Set and Install Accessory skid (oil systems / pumps / atomizing air compressor) | 7 | 2025-12-17 | 2025-12-24
CN-1635 | Set and Install GT #2 - Set and Install Generator | 4 | 2026-01-01 | 2026-01-05
CN-1650 | Set and Install GT #2 - Install SCR (exhaust stack sections) | 7 | 2026-01-31 | 2026-02-07
CN-1100 | Set and Install GT #2 - Turbine base Frame with Compressor / turbine / exhaust casings (split for transport) | 7 | 2026-02-28 | 2026-03-07
CN-1120 | Set and Install GT #2 - Inlet Air Filter | 2 | 2026-03-09 | 2026-03-10
GT #1 |  | 42 | 2025-12-17 | 2026-02-03
CN-1070 | Set and Install GT #1 Water Injection Skid | 6 | 2025-12-17 | 2025-12-23
CN-1060 | Set and Install GT #1 MEE Fog Skid | 4 | 2025-12-24 | 2025-12-27
CN-1090 | Set and Install GT #1 MCCs | 18 | 2025-12-17 | 2026-01-06
CN-1040 | Set and Install GT #1 Control Room / Building | 24 | 2025-12-17 | 2026-01-13
GT #1 Main Component Installation |  | 36 | 2025-12-24 | 2026-02-03
CN-1660 | Set and Install GT #1 - Load Gear | 4 | 2025-12-24 | 2025-12-27
CN-1665 | Set and Install GT #1 - Set and Install Generator | 4 | 2025-12-29 | 2026-01-01
CN-1675 | Set and Install GT #1 - Install GAC | 3 | 2026-01-02 | 2026-01-05
CN-1670 | Set and Install GT #1 - Set and Install Accessory skid (oil systems / pumps / atomizing air compressor) | 7 | 2026-01-02 | 2026-01-09
CN-1030 | Set and Install GT #1 - Turbine base Frame with Compressor / turbine / exhaust casings (split for transport) | 7 | 2026-01-16 | 2026-01-23
CN-1050 | Set and Install GT #1 - Inlet Air Filter | 7 | 2026-01-24 | 2026-01-31
CN-1680 | Set and Install GT #1 - Install SCR (exhaust stack sections) | 3 | 2026-01-31 | 2026-02-03
Cooling System |  | 36 | 2025-12-20 | 2026-01-30
CN-1240 | Set and Cooling System | 36 | 2025-12-20 | 2026-01-30
Piping |  | 64 | 2025-12-24 | 2026-03-07
Fuel Gas Piping |  | 64 | 2025-12-24 | 2026-03-07
CN-1480 | Make Fuel Gas Piping Tie In to GT #1 | 2 | 2026-01-22 | 2026-01-23
CN-1470 | Make Fuel Gas Piping Tie In to GT #3 | 2 | 2026-01-23 | 2026-01-24
CN-1250 | Fuel Gas Piping - Erect / Connect / Support | 30 | 2025-12-24 | 2026-01-27
CN-1475 | Make Fuel Gas Piping Tie In to GT #2 | 2 | 2026-03-06 | 2026-03-07
Cooling System Piping |  | 30 | 2026-01-03 | 2026-02-06
CN-1270 | Cooling System Piping - Erect / Connect / Support | 30 | 2026-01-03 | 2026-02-06
Interconnect Piping |  | 36 | 2025-12-29 | 2026-02-07
CN-1280 | Interconnect Piping - Erect / Connect / Support GT #1 | 36 | 2025-12-29 | 2026-02-07
CN-1690 | Interconnect Piping - Erect / Connect / Support GT #2 | 36 | 2025-12-29 | 2026-02-07
CN-1695 | Interconnect Piping - Erect / Connect / Support GT #3 | 36 | 2025-12-29 | 2026-02-07
Pipe Testing |  | 30 | 2026-01-30 | 2026-03-05
CN-1360 | Pipe Testing - Pre Test Punch #1 | 12 | 2026-01-30 | 2026-02-12
CN-1370 | Pipe Testing - Test #1 | 6 | 2026-02-13 | 2026-02-19
CN-1380 | Pipe Testing - Restoration #1 | 4 | 2026-02-18 | 2026-02-21
CN-1700 | Pipe Testing - Pre Test Punch #2 | 12 | 2026-02-09 | 2026-02-21
CN-1720 | Pipe Testing - Pre Test Punch #3 | 12 | 2026-02-09 | 2026-02-21
CN-1390 | Pipe Testing - Sell-Off #1 | 2 | 2026-02-23 | 2026-02-24
CN-1705 | Pipe Testing - Test #2 | 6 | 2026-02-23 | 2026-02-28
CN-1725 | Pipe Testing - Test #3 | 6 | 2026-02-23 | 2026-02-28
CN-1710 | Pipe Testing - Restoration #2 | 4 | 2026-02-27 | 2026-03-03
CN-1730 | Pipe Testing - Restoration #3 | 4 | 2026-02-27 | 2026-03-03
CN-1715 | Pipe Testing - Sell-Off #2 | 2 | 2026-03-04 | 2026-03-05
CN-1735 | Pipe Testing - Sell-Off #3 | 2 | 2026-03-04 | 2026-03-05
Electrical & Instrumentation |  | 112 | 2025-11-05 | 2026-03-14
Grounding |  | 47 | 2025-12-10 | 2026-02-02
CN-1290 | Install UG Grounding | 12 | 2025-12-10 | 2025-12-23
CN-1300 | Install Bonding | 18 | 2026-01-13 | 2026-02-02
Cable Tray |  | 12 | 2026-01-06 | 2026-01-19
CN-1310 | Install Cable Tray | 12 | 2026-01-06 | 2026-01-19
Conduit and Cable |  | 23 | 2026-01-20 | 2026-02-14
CN-1330 | Install Bonding | 18 | 2026-01-20 | 2026-02-09
CN-1320 | Pull / Terminate Power and Control Cable | 18 | 2026-01-26 | 2026-02-14
LIghting and Receptacles |  | 12 | 2026-01-20 | 2026-02-02
CN-1340 | Install / Terminate Lighting and Receptacles | 12 | 2026-01-20 | 2026-02-02
Electrical Equipment Installation |  | 112 | 2025-11-05 | 2026-03-14
CN-1435 | Set and Install Step Down Transformer AT-12 (Existing from NJ) | 12 | 2025-11-05 | 2025-11-18
CN-1450 | Set and Install MCCs (from NJ) | 12 | 2025-11-05 | 2025-11-18
CN-1555 | Set and Install Generator #1 | 4 | 2025-12-24 | 2025-12-27
CN-1415 | Set and Install Step Down Transformer AT-1 | 12 | 2025-12-20 | 2026-01-02
CN-1420 | Set and Install Step Down Transformer AT-2 | 12 | 2025-12-20 | 2026-01-02
CN-1425 | Set and Install Step Down Transformer AT-11 | 12 | 2025-12-23 | 2026-01-05
CN-1430 | Set and Install Step Down Transformer AT-21 | 12 | 2025-12-23 | 2026-01-05
CN-1440 | Set and Install Step Down Transformer AT-22 | 12 | 2025-12-23 | 2026-01-05
CN-1445 | Set and Install Step Down Transformer AT-EM | 12 | 2025-12-23 | 2026-01-05
CN-1560 | Set and Install Step Down Transformer AT-11 | 12 | 2025-12-23 | 2026-01-05
CN-1565 | Set and Install Step Down Transformer AT-21 | 12 | 2025-12-23 | 2026-01-05
CN-1570 | Set and Install Generator #2 | 4 | 2026-01-01 | 2026-01-05
CN-1575 | Set and Install Generator #3 | 4 | 2026-01-12 | 2026-01-15
CN-1455 | Set and Install MCCs (New) | 12 | 2026-01-17 | 2026-01-30
CN-1405 | Set and Install Step Up Transformer GTs - T1 / T2 / T3 | 12 | 2026-03-02 | 2026-03-14
Electrical Testing |  | 6 | 2026-02-18 | 2026-02-24
CN-1485 | Motor Run-Ins / Electrical Testing GT #2 | 2 | 2026-02-18 | 2026-02-19
CN-1490 | Motor Run-Ins / Electrical Testing GT #3 | 2 | 2026-02-20 | 2026-02-21
CN-1350 | Motor Run-Ins / Electrical Testing GT #1 | 2 | 2026-02-23 | 2026-02-24
Commissioning |  | 32 | 2026-02-11 | 2026-03-19
CM-1000 | Commissioning GT#1 | 18 | 2026-02-11 | 2026-03-03
CM-1005 | Commissioning GT#2 | 18 | 2026-02-20 | 2026-03-12
CM-1010 | Commissioning GT#3 | 18 | 2026-02-20 | 2026-03-12
CM-1015 | Startup, functional testing and commissioning review of documentation | 20 | 2026-02-25 | 2026-03-19
Start-up (First Fire) |  | 10 | 2026-03-04 | 2026-03-14
SU-1000 | Start-Up (First Fire) GT#1 | 2 | 2026-03-04 | 05-Mar-26*
SU-1005 | Start-Up (First Fire) GT#2 | 2 | 2026-03-13 | 14-Mar-26*
SU-1010 | Start-Up (First Fire) GT#3 | 2 | 2026-03-13 | 14-Mar-26*