## Sheet1
Activity ID | Activity Name | Remaining Duration | Start | Finish
Frame 6B Power Group Project |  | 95 | 21-Jul-25 A | 2026-05-28
General Milestones |  | 65 | 21-Jul-25 A | 2026-05-28
GN-1000 | Project Award | 0 | 21-Jul-25 A
GN-1010 | Disconnect Complete (iMTT) | 0 |  | 25-Jul-25 A
GN-1085 | RIGGS Agreement and Task Order #1 | 0 |  | 27-Aug-25 A
GN-1120 | Mobilize Sitework Contractors and Temp Facillities to Site (Construction Notice to Proceed) | 0 | 01-Oct-25 A
GN-1140 | Disassembly Complete CTs (excludes ST) | 0 |  | 22-Nov-25 A
GN-1095 | HRSG Drums (LP / IP / HP) Disassembly | 0 |  | 01-Dec-25 A
GN-1020 | Disassembly Complete (ST) | 0 |  | 01-Dec-25 A
GN-1030 | Transportation Complete (Road / Barge from IMTT) | 0 |  | 08-Jan-26 A
GN-1040 | Refurbishment Complete (Turbines and Generators) | 0 |  | 2026-02-26
GN-1145 | Steel Fabrication Complete | 0 |  | 2026-02-28
GN-1090 | Permit to Construct | 0 |  | 02-Mar-26*
GN-1060 | Construction Complete | 0 |  | 2026-04-16
GN-1070 | Testing and Commissioning Complete GT #1 | 0 |  | 2026-05-08
GN-1100 | Testing and Commissioning Complete GT #2 | 0 |  | 2026-05-08
GN-1080 | First Fire GT #1 | 0 |  | 2026-05-12
GN-1110 | First Fire GT #2 | 0 |  | 2026-05-12
GN-1135 | On Line Testing and Commercial Operation GT #1 | 0 |  | 2026-05-13
GN-1125 | On Line Testing and Commercial Operation GT #2 | 0 |  | 2026-05-13
GN-1105 | Testing and Commissioning Complete GT #3 | 0 |  | 2026-05-23
GN-1115 | First Fire GT #3 | 0 |  | 2026-05-26
GN-1130 | On Line Testing and Commercial Operation GT #3 | 0 |  | 2026-05-28
Interface Milestones |  | 99 | 01-Oct-25 A | 2026-05-12
IM-1040 | Construction access to 6B Power block available - Security / Fencing / Roads (Parkhill) | 0 |  | 01-Oct-25 A
IM-1060 | Construction water available at Frame 6B power block laydown area (Parkhill) | 0 |  | 01-Oct-25 A
IM-1035 | Stormwater / Erosion / Site Grading Plans (Red Tree IFC) | 0 |  | 03-Oct-25 A
IM-1070 | Spec for Relays / Communications (Dashiell) | 0 |  | 14-Nov-25 A
IM-1080 | Final Completion - Matador Pipeline | 0 |  | 16-Jan-26*
IM-1055 | Water (Potable Process, Firewater) available from SGT-800 power block (Red Tree) TBD | 0 |  | 16-Jan-26*
IM-1020 | High Pressure fuel gas ready for tie in (PERC) | 0 |  | 06-Feb-26*
IM-1025 | 115 kV Dead End Structure in Power Block ready for tie-in (Dashiel) | 0 |  | 06-Feb-26*
IM-1000 | City of Amarillo water (Potable & Process) available at Frame 6B tie-point | 0 |  | 02-Mar-26*
IM-1010 | Pre-Construction grading in power block complete (Red Tree IFC design) | 0 |  | 2026-03-02
IM-1005 | 115 kV System Ready to Deliver and Accept Power | 0 |  | 2026-05-12
IM-1030 | High Pressure fuel gas supply commissioning complete to tie-in point | 0 |  | 2026-05-12
IMTT Faciltiy |  | 0 | 21-Jul-25 A | 09-Jan-26 A
Disconnect |  | 0 | 21-Jul-25 A | 25-Jul-25 A
DC-1000 | Disconnect Components - Make Safe | 0 | 21-Jul-25 A | 25-Jul-25 A
Disassembly |  | 0 | 23-Jul-25 A | 29-Dec-25 A
General |  | 0 | 23-Jul-25 A | 26-Sep-25 A
DA-2025 | General Assessment - 3D Scanning and Equipment Assessment | 0 | 23-Jul-25 A | 16-Aug-25 A
DA-2255 | Riggs Agreement Finalized | 0 | 27-Aug-25 A | 27-Aug-25 A
DA-2260 | Riggs Letter of Credit Accepted | 0 | 27-Aug-25 A | 27-Aug-25 A
DA-2045 | Riggs Mobilize and Begin Disassembly | 0 | 28-Aug-25 A | 02-Sep-25 A
DA-2265 | NAES Copies of all documentation, manuals, drawings, equipment O&M Manuals and distribute | 0 | 28-Aug-25 A | 26-Sep-25 A
Assessments |  | 0 | 06-Sep-25 A | 12-Sep-25 A
GT #3 Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2100 | GT#3 Inspection - Borescope | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2105 | GT#3 Inspection - Bearing Inspection | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #3 Generator Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2110 | GT#3 Generator Inspection - Stator Electrical Testing (megger tests / visual inspections / busings / insulators) | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2115 | GT#3 Generator Inspection - Field Electrical Testing (megger / visual) | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #2 Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2120 | GT#2 Inspection - Borescope | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2125 | GT#2 Inspection - Bearing Inspection | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #2 Generator Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2130 | GT#2 Generator Inspection - Stator Electrical Testing (megger tests / visual inspections / busings / insulators) | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2135 | GT#2 Generator Inspection - Field Electrical Testing (megger / visual) | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #1 Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2140 | GT#1 Inspection - Borescope | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2145 | GT#1 Inspection - Bearing Inspection | 0 | 06-Sep-25 A | 10-Sep-25 A
GT #1 Generator Inspection |  | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2150 | GT#1 Generator Inspection - Stator Electrical Testing (megger tests / visual inspections / busings / insulators) | 0 | 06-Sep-25 A | 10-Sep-25 A
DA-2155 | GT#1 Generator Inspection - Field Electrical Testing (megger / visual) | 0 | 06-Sep-25 A | 10-Sep-25 A
Steam Generator Inspection |  | 0 | 09-Sep-25 A | 12-Sep-25 A
DA-2160 | Steam Turbine Generator Inspection - Continuity / Megger test | 0 | 09-Sep-25 A | 12-Sep-25 A
Site Prep |  | 0 | 06-Sep-25 A | 04-Oct-25 A
DA-2190 | Prep Site Construction Trailers and Temporary Facilities | 0 | 06-Sep-25 A | 25-Sep-25 A
DA-2185 | Prep Site Laydown Areas (Demo / Fence relocation) | 0 | 06-Sep-25 A | 04-Oct-25 A
Dismantle GT-3 |  | 0 | 15-Sep-25 A | 16-Nov-25 A
A2490 | CT #3 - Clean out both GT buildings - remove all debris, 3 center skids, 2 acid tanks, center platform & eyewash station | 0 | 15-Sep-25 A | 20-Sep-25 A
A2540 | CT #3 - Remove inlet duct | 0 | 29-Sep-25 A | 03-Oct-25 A
A2500 | CT #3 - Work ubolting internal piping, bearings, and expansion joints | 0 | 18-Sep-25 A | 04-Oct-25 A
A2510 | CT #3 - Un-bolt and/ or cut inlet duct, heat recovery duct and outlet duct | 0 | 03-Oct-25 A | 04-Oct-25 A
A2530 | CT #3 - Remove Inlet Air Duct Steel | 0 | 03-Oct-25 A | 04-Oct-25 A
A2560 | CT #3 - Remove all floor grating and tanks | 0 | 02-Oct-25 A | 04-Oct-25 A
A2660 | CT #3 - Disconnect all electrical, panel misc. wiring | 0 | 15-Sep-25 A | 11-Oct-25 A
A1790 | CT #3 - Remove Welded On Exhaust Plenum Cover (Gouge) | 0 | 10-Oct-25 A | 13-Oct-25 A
A1780 | CT #3 - Remove Welded On Expansion Joints Hardware(Gouge) | 0 | 14-Oct-25 A | 15-Oct-25 A
A2570 | CT #3 - Demo and clean vault area - Waiting For Fire Station's Notification | 0 | 03-Oct-25 A | 19-Oct-25 A
A2600 | CT #3 - Remove Overhead Roll-Up Door and Make Opening Taller | 0 | 04-Oct-25 A | 19-Oct-25 A
A2580 | CT #3 - Fill pit area with materials (sand or other) in order to support heavy rigging equipment, gantries and tracks | 0 | 19-Oct-25 A | 20-Oct-25 A
A2550 | CT #3 - Remove all Turbine cat walks | 0 | 17-Oct-25 A | 23-Oct-25 A
A2141 | CT #3 - Re-install Turbine Doors | 0 | 27-Sep-25 A | 24-Oct-25 A
A2520 | CT #3 - Remove all wanted piping on both sides | 0 | 25-Sep-25 A | 24-Oct-25 A
A2610 | CT #3 - Remove GAC compartment and strage/load for over the road transport | 0 | 23-Oct-25 A | 25-Oct-25 A
A2441 | CT #3 - Install engineered scaffolding to support housing-NEW | 0 | 24-Oct-25 A | 26-Oct-25 A
A2590 | CT #3 - Move in and set up heavy rigging gantries (Bay Crane mobilization) | 0 | 26-Oct-25 A | 27-Oct-25 A
A2620 | CT #3 - Remove Generator compartment and stage on SPMT for barge transport | 0 | 27-Oct-25 A | 27-Oct-25 A
A2451 | CT #3 - Dismantle piping/valves from Gas Scrubbers-NEW | 0 | 25-Oct-25 A | 28-Oct-25 A
A2461 | CT #3 - Dismantle piping/valves from Coalescer tank-NEW | 0 | 28-Oct-25 A | 29-Oct-25 A
A2471 | CT #3 - Remove anchor bolts from Gas Scrubber grout-NEW | 0 | 28-Oct-25 A | 29-Oct-25 A
A2630 | CT #3 - Remove Philadelphia gearbox compartment and stage/load for over the road transport | 0 | 27-Oct-25 A | 29-Oct-25 A
A2640 | CT #3 - Remove Turbine Auxillary compartment and stage on SPMT for barge transport | 0 | 28-Oct-25 A | 29-Oct-25 A
A2650 | CT #3 - Split Inlet Air Filter Compartment-NEW | 0 | 28-Oct-25 A | 29-Oct-25 A
A2561 | CT #3 - Transport to Barge (UTC Scope) duration TBD | 0 | 29-Oct-25 A | 30-Oct-25 A
A2472 | CT #3 - Cut embedded anchor bolts on Water Injection Unit-NEW | 0 | 07-Nov-25 A | 07-Nov-25 A
A2670 | CT #3 - Remove "Puffer" System from Inlet Air filter compartment-NEW | 0 | 06-Nov-25 A | 07-Nov-25 A
A2680 | CT #3 - Remove Catwalks & Platforms from Air filter compartment-NEW | 0 | 06-Nov-25 A | 07-Nov-25 A
A2501 | CT #3 - Disconnect subterranean cables from Mark IV Cabinets (Confined Space)-NEW | 0 | 30-Oct-25 A | 08-Nov-25 A
A2551 | CT #3 - Breakdown 350t AT Crane and move to Unit 3 (Maxim) - Unit 3 ONLY-NEW | 0 | 10-Nov-25 A | 10-Nov-25 A
A2521 | CT #3 - Remove and Stage Mark IV Cabs-NEW | 0 | 12-Nov-25 A | 12-Nov-25 A
A2511 | CT #3 - Remove and Stage Inlet Air Filter Compartments-NEW | 0 | 09-Nov-25 A | 12-Nov-25 A
A2531 | CT #3 - Remove and Stage Water Injection Cabs-NEW | 0 | 11-Nov-25 A | 12-Nov-25 A
A2700 | CT #3 - Remove Batteries from Mark IV Cabs-NEW | 0 | 12-Nov-25 A | 14-Nov-25 A
A2481 | CT #3 - Stage Gas Scrubber for transport-NEW | 0 | 07-Nov-25 A | 15-Nov-25 A
A2491 | CT #3 - Stage Coalescer for transport-NEW | 0 | 07-Nov-25 A | 16-Nov-25 A
Dismantle GT-1 |  | 0 | 02-Sep-25 A | 14-Nov-25 A
A2110 | CT #1 - Work ubolting internal piping, bearings, and expansion joints | 0 | 02-Sep-25 A | 06-Sep-25 A
A2160 | CT #1 - Remove inlet duct | 0 | 05-Sep-25 A | 06-Sep-25 A
A2140 | CT #1 - Remove all wanted piping on both sides | 0 | 03-Sep-25 A | 20-Sep-25 A
A2150 | CT #1 - Remove Inlet Air Duct Steel | 0 | 02-Sep-25 A | 20-Sep-25 A
A2100 | CT #1 - Clean out both GT buildings - remove all debris, 3 center skids, 2 acid tanks, center platform & eyewash station | 0 | 03-Sep-25 A | 20-Sep-25 A
A2130 | CT #1 - Remove Lage outlet ducts @ HRSG | 0 | 15-Sep-25 A | 20-Sep-25 A
A2280 | CT #1 - Disconnect all electrical, panel misc. wiring | 0 | 02-Sep-25 A | 20-Sep-25 A
A1750 | CT #1 - Remove Cover on Gear Box/Excitor Cover | 0 | 19-Sep-25 A | 20-Sep-25 A
A2231 | CT #1 - Cut embedded anchor bolts on Water Injection Unit-NEW | 0 | 28-Sep-25 A | 29-Sep-25 A
A1740 | CT #1 - Re-install Turbine Doors | 0 | 22-Sep-25 A | 30-Sep-25 A
A2170 | CT #1 - Remove all Turbine cat walks | 0 | 20-Sep-25 A | 04-Oct-25 A
A2180 | CT #1 - Remove all floor grating and tanks | 0 | 03-Oct-25 A | 06-Oct-25 A
A2190 | CT #1 - Demo and clean vault area | 0 | 03-Oct-25 A | 06-Oct-25 A
A2220 | CT #1 - Remove overhead roll-up door and make opening taller | 0 | 01-Oct-25 A | 06-Oct-25 A
A2120 | CT #1 - Remove Welded on Expansion Joints Hardware (Gouge) | 0 | 08-Oct-25 A | 10-Oct-25 A
A1770 | CT #1 - Remove Welded on Exhaust Plenum Cover (Gouge) | 0 | 10-Oct-25 A | 11-Oct-25 A
A2200 | CT #1 - Fill pit area with materials (sand or other) in order to support heavy rigging equipment, gantries and tracks | 0 | 07-Oct-25 A | 11-Oct-25 A
A2210 | CT #1 - Move in and set up heavy rigging gantries (Bay Crane mobilization)-Pending Transport Plng. | 0 | 15-Oct-25 A | 17-Oct-25 A
A2240 | CT #1 - Remove Generator compartment and stage on SPMT for barge transport | 0 | 18-Oct-25 A | 19-Oct-25 A
A2260 | CT #1 - Remove Turbine Auxillary compartment and stage on SPMT for barge transport | 0 | 18-Oct-25 A | 19-Oct-25 A
A2171 | CT #1 - Overhead Crane Delay in Unit 1 | 0 | 21-Oct-25 A | 21-Oct-25 A
A2181 | CT #1 - Split Inlet Air Filter Compartment-NEW | 0 | 20-Oct-25 A | 21-Oct-25 A
A2191 | CT #1 - Install engineered scaffolding to support housing-NEW | 0 | 24-Oct-25 A | 26-Oct-25 A
A2230 | CT #1 - Remove GAC compartment and strage/load for over the road transport | 0 | 17-Oct-25 A | 30-Oct-25 A
A2250 | CT #1 - Remove Philadelphia gearbox compartment and stage/load for over the road transport to Panhandle | 0 | 19-Oct-25 A | 30-Oct-25 A
A2270 | CT #1 - Transport to Barge (UTC Scope) duration TBD-Pending UTC Plan Confirmation | 0 | 30-Oct-25 A | 30-Oct-25 A
A2201 | CT #1 - Dismantle piping/valves from Gas Scrubbers-NEW | 0 | 28-Oct-25 A | 01-Nov-25 A
A2211 | CT #1 - Dismantle piping/valves from Coalescer tank-NEW | 0 | 28-Oct-25 A | 01-Nov-25 A
A2221 | CT #1 - Remove anchor bolts from Gas Scrubber grout-NEW | 0 | 28-Oct-25 A | 01-Nov-25 A
A2261 | CT #1 - Disconnect subterranean cables from Mark IV Cabinets (Confined Space)-NEW | 0 | 30-Oct-25 A | 01-Nov-25 A
A2271 | CT #1 - Mobilize and set up 350t AT Crane (Maxim) - Units 1&2 ONLY-NEW | 0 | 03-Nov-25 A | 04-Nov-25 A
A2301 | CT #1 - Remove and Stage Water Injection Cabs-NEW | 0 | 03-Nov-25 A | 04-Nov-25 A
A2281 | CT #1 - Remove and Stage Inlet Air Filter Compartments-NEW | 0 | 05-Nov-25 A | 06-Nov-25 A
A2291 | CT #1 - Remove and Stage Mark IV Cabs-NEW | 0 | 05-Nov-25 A | 06-Nov-25 A
A2690 | CT #1 - Remove Batteries from Mark IV Cabs-NEW | 0 | 11-Nov-25 A | 12-Nov-25 A
A2241 | CT #1 - Stage Gas Scrubber for transport-NEW | 0 | 07-Nov-25 A | 14-Nov-25 A
A2251 | CT #1 - Stage Coalescer for transport-NEW | 0 | 07-Nov-25 A | 14-Nov-25 A
Dismantle GT-2 |  | 0 | 04-Sep-25 A | 12-Nov-25 A
A2310 | CT #2 - Clean out both GT buildings - remove all debris, 3 center skids, 2 acid tanks, center platform & eyewash station | 0 | 04-Sep-25 A | 20-Sep-25 A
A2320 | CT #2 - Work ubolting internal piping, bearings, and expansion joints | 0 | 04-Sep-25 A | 20-Sep-25 A
A2360 | CT #2 - Remove inlet duct | 0 | 16-Sep-25 A | 20-Sep-25 A
A2480 | CT #2 - Disconnect all electrical, panel misc. wiring | 0 | 04-Sep-25 A | 20-Sep-25 A
A2340 | CT #2 - Remove all wanted piping on both sides | 0 | 16-Sep-25 A | 04-Oct-25 A
A2380 | CT #2 - Remove all floor grating and tanks | 0 | 29-Sep-25 A | 04-Oct-25 A
A2330 | CT #2 - Un-bolt and/ or cut inlet duct, heat recovery duct and outlet duct | 0 | 17-Sep-25 A | 04-Oct-25 A
A2350 | CT #2 - Remove Inlet Air Duct Steel | 0 | 02-Oct-25 A | 04-Oct-25 A
A1810 | CT #2 - Remove Welded On Exhaust Plenum Cover (Gouge) | 0 | 07-Oct-25 A | 09-Oct-25 A
A1800 | CT #2 - Remove Welded On Expansion Joint Hardware (Gouge) | 0 | 07-Oct-25 A | 10-Oct-25 A
A2390 | CT #2 - Demo and clean vault area-Waiting For Fire Station's Notification | 0 | 02-Oct-25 A | 10-Oct-25 A
A2420 | CT #2 - Remove overhead roll-up door and make opening taller | 0 | 03-Oct-25 A | 11-Oct-25 A
A2370 | CT #2 - Remove all Turbine cat walks | 0 | 07-Oct-25 A | 11-Oct-25 A
A2400 | CT #2 - Fill pit area with materials (sand or other) in order to support heavy rigging equipment, gantries and tracks | 0 | 07-Oct-25 A | 11-Oct-25 A
A1760 | CT #2 - Re-install Turbine Doors | 0 | 27-Sep-25 A | 17-Oct-25 A
A2410 | CT #2 - Move in and set up heavy rigging gantries (Bay Crane mobilization) | 0 | 15-Oct-25 A | 19-Oct-25 A
A2151 | CT #2 - Re-position Gantries for GT-2 activities | 0 | 19-Oct-25 A | 21-Oct-25 A
A2311 | CT #2 - Split Inlet Air Filter Compartment-NEW | 0 | 20-Oct-25 A | 21-Oct-25 A
A2440 | CT #2 - Remove Generator compartment and stage on SPMT for barge transport | 0 | 21-Oct-25 A | 23-Oct-25 A
A2460 | CT #2 - Remove Turbine Auxillary compartment and stage on SPMT for barge transport | 0 | 24-Oct-25 A | 24-Oct-25 A
A2161 | CT #2 - Breakdown Gantry and move to Unit 3 | 0 | 25-Oct-25 A | 26-Oct-25 A
A2321 | CT #2 - nstall engineered scaffolding to support housing-NEW | 0 | 24-Oct-25 A | 26-Oct-25 A
A2331 | CT #2 - Dismantle piping/valves from Gas Scrubbers-NEW | 0 | 25-Oct-25 A | 26-Oct-25 A
A2361 | CT #2 - Cut embedded anchor bolts on Water Injection Unit-NEW | 0 | 29-Oct-25 A | 29-Oct-25 A
A2450 | CT #2 - Remove Philadelphia gearbox compartment and stage/load for over the road transport | 0 | 23-Oct-25 A | 29-Oct-25 A
A2341 | CT #2 - Dismantle piping/valves from Coalescer tank-NEW | 0 | 28-Oct-25 A | 29-Oct-25 A
A2351 | CT #2 - Remove anchor bolts from Gas Scrubber grout-NEW | 0 | 28-Oct-25 A | 29-Oct-25 A
A2470 | CT #2 - Transport to Barge (UTC Scope) duration TBD | 0 | 29-Oct-25 A | 30-Oct-25 A
A2371 | CT #2 - Stage Gas Scrubber for transport-NEW | 0 | 30-Oct-25 A | 31-Oct-25 A
A2391 | CT #2 - Disconnect subterranean cables from Mark IV Cabinets (Confined Space)-NEW | 0 | 30-Oct-25 A | 31-Oct-25 A
A2430 | CT #2 - Remove GAC compartment and strage/load for over the road transport | 0 | 18-Oct-25 A | 01-Nov-25 A
A2401 | CT #2 - Mobilise and set up 350t AT Crane (Maxim) - Units 1&2 ONLY-NEW | 0 | 04-Nov-25 A | 04-Nov-25 A
A2381 | CT #2 - Stage Coalescer for transport-NEW | 0 | 07-Nov-25 A | 07-Nov-25 A
A2411 | CT #2 - Remove and Stage Inlet Air Filter Compartments-NEW | 0 | 08-Nov-25 A | 08-Nov-25 A
A2421 | CT #2 - Remove and Stage Mark IV Cabs-NEW | 0 | 09-Nov-25 A | 09-Nov-25 A
A2431 | CT #2 - Remove and Stage Water Injection Cabs-NEW | 0 | 09-Nov-25 A | 09-Nov-25 A
A2710 | CT #2 - Remove Batteries from Mark IV Cabs-NEW | 0 | 11-Nov-25 A | 12-Nov-25 A
Dismantle Steam Generator |  | 0 | 15-Sep-25 A | 01-Dec-25 A
Steam Turbine Building |  | 0 | 01-Oct-25 A | 30-Nov-25 A
DSG1020 | Tear down pipe bridge (rack) | 0 | 01-Nov-25 A | 02-Nov-25 A
DSG1030 | Modifiy Southern entry point | 0 | 10-Nov-25 A | 11-Nov-25 A
DSG1340 | Reroute Exxon Remediation Control Conduit: Start-Finish TBD-NEW | 0 | 13-Nov-25 A | 15-Nov-25 A
DSG1010 | Demo all piping on steam turbine compartments and skids | 0 | 01-Oct-25 A | 17-Nov-25 A
DSG1040 | Remove Catwalks, Handrails, & Structural Steel | 0 | 07-Nov-25 A | 24-Nov-25 A
DSG1050 | Mobilize Bay Crane 900 ton Gantry | 0 | 26-Nov-25 A | 29-Nov-25 A
DSG1000 | Remove Wanted Valves | 0 | 01-Oct-25 A | 30-Nov-25 A
Steam Turbine GAC Compartment |  | 0 | 15-Oct-25 A | 14-Nov-25 A
DSG1060 | Remove bus ducts from GAC to Generator | 0 | 15-Oct-25 A | 21-Oct-25 A
DSG1070 | Remove bus duct from GAC to TSFMR | 0 | 07-Nov-25 A | 10-Nov-25 A
DSG1080 | Remove anchor bolts from GAC base | 0 | 11-Nov-25 A | 11-Nov-25 A
DSG1090 | Remove GAC and stage w/Kranco Crane | 0 | 12-Nov-25 A | 14-Nov-25 A
Clean/Dirty Oil Tank |  | 0 | 15-Sep-25 A | 06-Nov-25 A
DSG1100 | Remove piping connections from nozzles | 0 | 15-Sep-25 A | 18-Sep-25 A
DSG1110 | Remove anchor bolts | 0 | 01-Nov-25 A | 02-Nov-25 A
DSG1120 | Remove lube oil skid and stage | 0 | 06-Nov-25 A | 06-Nov-25 A
Lube Oil Skid |  | 0 | 18-Sep-25 A | 04-Nov-25 A
DSG1130 | Remove piping connections from nozzles | 0 | 18-Sep-25 A | 21-Sep-25 A
DSG1140 | Remove anchor bolts | 0 | 01-Nov-25 A | 01-Nov-25 A
DSG1150 | Remove lube oil skid and stage | 0 | 04-Nov-25 A | 04-Nov-25 A
Lube Oil Coinditioner Skid |  | 0 | 18-Sep-25 A | 08-Nov-25 A
DSG1160 | Remove piping connections from nozzles | 0 | 18-Sep-25 A | 21-Sep-25 A
DSG1170 | Remove anchor bolts | 0 | 01-Nov-25 A | 01-Nov-25 A
DSG1180 | Remove lube oil skid and stage | 0 | 08-Nov-25 A | 08-Nov-25 A
Turbine Shell/Rotor |  | 0 | 10-Nov-25 A | 24-Nov-25 A
DSG1190 | Subcontract for Analytic Stress to utilize conduction heating on turbine shell bolts | 0 | 10-Nov-25 A | 12-Nov-25 A
DSG1200 | Remove Top Turbine Shell | 0 | 14-Nov-25 A | 14-Nov-25 A
DSG1360 | Mobilize KSI subcontractor to facilitate removing of rotor | 0 | 18-Nov-25 A | 19-Nov-25 A
DSG1350 | Turbine Clearance Check | 0 | 18-Nov-25 A | 20-Nov-25 A
DSG1220 | Wrap Rotor on stands and stage for transit (Over the road) via KSI | 0 | 20-Nov-25 A | 21-Nov-25 A
DSG1210 | Remove Rotor from Turbine Shell and set in stands | 0 | 20-Nov-25 A | 21-Nov-25 A
DSG1230 | Remove bottom turbine shell for over the road transport via KSI | 0 | 21-Nov-25 A | 24-Nov-25 A
Steam Condenser |  | 0 | 15-Oct-25 A | 01-Dec-25 A
DSG1240 | Remove pumps from top of condenser | 0 | 15-Oct-25 A | 17-Oct-25 A
DSG1250 | Remove pumps circ pumps | 0 | 15-Oct-25 A | 22-Oct-25 A
DSG1260 | Remove Water Box Doors | 0 | 20-Oct-25 A | 01-Nov-25 A
DSG1270 | Remove Guillotine from Condenser (torch cut) | 0 | 01-Nov-25 A | 07-Nov-25 A
DSG1280 | Stage Guillotine for transport | 0 | 08-Nov-25 A | 08-Nov-25 A
DSG1370 | Weld lifting eyes on each section of condensor | 0 | 20-Nov-25 A | 24-Nov-25 A
DSG1290 | Remove condenser and stage for transit. | 0 | 29-Nov-25 A | 01-Dec-25 A
Steam Turbine Generator Compartment |  | 0 | 28-Sep-25 A | 30-Nov-25 A
DSG1300 | Remove Aux Cooling water piping | 0 | 28-Sep-25 A | 05-Oct-25 A
DSG1310 | Cut pipe supports from Generator | 0 | 15-Oct-25 A | 15-Oct-25 A
DSG1320 | Remove Generator Cooler Compartment | 0 | 07-Nov-25 A | 13-Nov-25 A
DSG1330 | Remove Generator Compartment and stage in transit yard | 0 | 29-Nov-25 A | 30-Nov-25 A
Dismantle Cooling Tower |  | 0 | 03-Nov-25 A | 03-Dec-25 A
DCT1000 | Build scaffolding, add new flooring and make safety tie-off points on all 5 Towers | 0 | 03-Nov-25 A | 10-Nov-25 A
DCT1030 | Disconnect feed water pumps | 0 | 11-Nov-25 A | 12-Nov-25 A
DCT101 | Install scaffolding and new plywood | 0 | 10-Nov-25 A | 12-Nov-25 A
DCT1080 | Disconnect all 5 motors | 0 | 14-Nov-25 A | 17-Nov-25 A
DCT1050 | Move crane to middle of Tower 4 and lift out assembies 3, 4, and 5. | 0 | 19-Nov-25 A | 20-Nov-25 A
DCT1060 | Remove feed water pumps from pump station cooling tower | 0 | 17-Nov-25 A | 24-Nov-25 A
DCT1070 | Remove fan rotors and gearboxes | 0 | 26-Nov-25 A | 03-Dec-25 A
DCT1040 | Disassemble fan rotors and gearboxes from cooling tower assembly (Confined Space) | 0 | 18-Nov-25 A | 03-Dec-25 A
HRSG #3 |  | 0 | 20-Sep-25 A | 01-Dec-25 A
DA-2030 | HRSG #3 - Inspection / Testing | 0 | 20-Sep-25 A | 25-Sep-25 A
DA-2090 | HRSG #3 - Analyze Reports | 0 | 26-Sep-25 A | 14-Oct-25 A
DA-1815 | HRSG #3 - Disassemble Drums | 0 | 20-Oct-25 A | 22-Oct-25 A
DA-2355 | HRSG #3 - Removal of the IP Drum | 0 | 14-Nov-25 A | 21-Nov-25 A
DA-2375 | HRSG #3 - Removal of the HP Drum | 0 | 15-Nov-25 A | 21-Nov-25 A
DA-2315 | HRSG #3 - Removal of the DA Drum | 0 | 17-Nov-25 A | 22-Nov-25 A
DA-2335 | HRSG #3 - Removal of the LP Drum | 0 | 17-Nov-25 A | 22-Nov-25 A
DA-1825 | HRSG #3 - Pack & Load Drums | 0 | 28-Nov-25 A | 01-Dec-25 A
HRSG #2 |  | 0 | 20-Sep-25 A | 01-Dec-25 A
DA-2035 | HRSG #2 - Inspection / Testing | 0 | 20-Sep-25 A | 25-Sep-25 A
DA-2075 | HRSG #2 - Analyze Reports | 0 | 26-Sep-25 A | 14-Oct-25 A
DA-2345 | HRSG #2 - Removal of the LP Drum | 0 | 17-Nov-25 A | 18-Nov-25 A
DA-2365 | HRSG #2 - Removal of the IP Drum | 0 | 17-Nov-25 A | 18-Nov-25 A
DA-2325 | HRSG #2 - Removal of the DA Drum | 0 | 19-Nov-25 A | 20-Nov-25 A
DA-1855 | HRSG #2 - Disassemble Drums | 0 | 21-Oct-25 A | 20-Nov-25 A
DA-2385 | HRSG #2 - Removal of the HP Drum | 0 | 20-Nov-25 A | 22-Nov-25 A
DA-1865 | HRSG #2 - Pack & Load Drums | 0 | 28-Nov-25 A | 01-Dec-25 A
HRSG #1 |  | 0 | 20-Sep-25 A | 01-Dec-25 A
DA-2040 | HRSG #1 - Inspection / Testing | 0 | 20-Sep-25 A | 25-Sep-25 A
DA-2060 | HRSG #1 - Analyze Reports | 0 | 26-Sep-25 A | 14-Oct-25 A
DA-2275 | HRSG #1 - Removal of the DA Drum | 0 | 17-Nov-25 A | 18-Nov-25 A
DA-2285 | HRSG #1 - Removal of the LP Drum | 0 | 17-Nov-25 A | 18-Nov-25 A
DA-2295 | HRSG #1 - Removal of the IP Drum | 0 | 18-Nov-25 A | 19-Nov-25 A
DA-1895 | HRSG #1 - Disassemble Drums | 0 | 22-Oct-25 A | 22-Nov-25 A
DA-2305 | HRSG #1 - Removal of the HP Drum | 0 | 20-Nov-25 A | 22-Nov-25 A
DA-1905 | HRSG #1 - Pack & Load Drums | 0 | 28-Nov-25 A | 01-Dec-25 A
Water Wash Skid |  | 0 | 19-Nov-25 A | 24-Nov-25 A
DA-1975 | Water Wash Skid - De-Term and Unbolt | 0 | 19-Nov-25 A | 22-Nov-25 A
DA-1985 | Water Wash Skid - Transport to 440 Yard | 0 | 21-Nov-25 A | 24-Nov-25 A
Final Transport Schedule |  | 0 | 28-Nov-25 A | 10-Dec-25 A
DA-2445 | HRSG Drum 1 | 0 | 01-Dec-25 A | 01-Dec-25 A
DA-2535 | Condenser Transition - Barge Transport | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2555 | HRSG Drum 2 | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2565 | WWS - Barge Transport | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2575 | GCX - Barge Transport | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2585 | ECH - Barge Transport | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2665 | HRSG Drum 3 | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2745 | VALVES 4 (Dooling) | 0 | 28-Nov-25 A | 01-Dec-25 A
DA-2695 | COND Top - Barge Transport | 0 | 28-Nov-25 A | 02-Dec-25 A
DA-2705 | COND Bottom - Barge Transport | 0 | 28-Nov-25 A | 02-Dec-25 A
DA-2735 | HRSG Drum 4 | 0 | 28-Nov-25 A | 02-Dec-25 A
DA-2545 | Condenser Guillotine - Barge Transport | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2605 | Water Box Door 1 - Barge Transport | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2615 | Water Box Door 2 - Barge Transport | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2675 | HP Drum 3 - Barge Transport | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2465 | CONEX #9 - GT#1 | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2475 | CONEX #10 - GT#2 | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2485 | CONEX #11 - GT#3 | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2715 | ST TUR 1 - Barge Transport | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2725 | ST TUR 2 - Barge Transport | 0 | 28-Nov-25 A | 03-Dec-25 A
DA-2435 | Conex 8 - ST#1 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2455 | CT#5 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2515 | MISC OL #4 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2525 | MISC OL #5 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2595 | GAC - Barge Transport | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2625 | Clean/Dirty Oil Tank - Barge Transport | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2635 | Condensate Tank - Barge Transport | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2645 | HP Drum 1 - Barge Transport | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2655 | HP Drum 2 - Barge Transport | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2685 | ST GEN - Barge Transport | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2755 | STG Steel 1 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2765 | STG Steel 2 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2775 | OPEN LOAD#3 | 0 | 28-Nov-25 A | 06-Dec-25 A
DA-2425 | IMT Conex 7 | 0 | 28-Nov-25 A | 08-Dec-25 A
DA-2495 | CONEX 12 | 0 | 28-Nov-25 A | 08-Dec-25 A
DA-2785 | CT#4 | 0 | 28-Nov-25 A | 09-Dec-25 A
DA-2505 | CONEX 13 - (MISC) | 0 | 28-Nov-25 A | 10-Dec-25 A
Restoration Schedule |  | 0 | 01-Dec-25 A | 29-Dec-25 A
DA-2935 | Disposal of Mark IV batteries | 0 | 04-Dec-25 A | 04-Dec-25 A
DA-2795 | Building 1 Garage Door (Reinstallation)-Insulation Del.:12/3 | 0 | 02-Dec-25 A | 08-Dec-25 A
DA-2805 | Building 2 Garage Door (Reinstallation)-Insulation Del.:12/3 | 0 | 03-Dec-25 A | 08-Dec-25 A
DA-2815 | Building 3 Garage Door (Reinstallation)-Insulation Del.:12/3 | 0 | 05-Dec-25 A | 08-Dec-25 A
DA-2945 | Inlet duct. Install Framing and Panels | 0 | 04-Dec-25 A | 08-Dec-25 A
DA-2895 | Staging IMTT Equipment in Building 3 | 0 | 09-Dec-25 A | 10-Dec-25 A
DA-2915 | Access Harness Required Gate for bottom of HRSG Stairs | 0 | 10-Dec-25 A | 10-Dec-25 A
DA-2825 | 711 Feed (Reroute) | 0 | 02-Dec-25 A | 15-Dec-25 A
DA-2835 | Acid Caustic Panel (Reroute) | 0 | 02-Dec-25 A | 15-Dec-25 A
DA-2845 | Laboratory (Reroute) | 0 | 02-Dec-25 A | 15-Dec-25 A
DA-2855 | Compressor #2 (Reroute) | 0 | 02-Dec-25 A | 15-Dec-25 A
DA-2865 | Demin Monitor Panel (Reroute) | 0 | 02-Dec-25 A | 16-Dec-25 A
DA-2875 | Site Pick Ups | 0 | 02-Dec-25 A | 18-Dec-25 A
DA-2905 | Removal of 360 Cam-(Pending Eli Approval) | 0 | 19-Dec-25 A | 19-Dec-25 A
DA-2415 | GIS Demo | 0 | 01-Dec-25 A | 22-Dec-25 A
DA-2925 | Remaining Cables cut 6" above ground level | 0 | 02-Dec-25 A | 23-Dec-25 A
DA-2885 | Demob Tools /Trailer | 0 | 02-Dec-25 A | 29-Dec-25 A
Transportation |  | 0 | 04-Nov-25 A | 09-Jan-26 A
Permitted Loads |  | 0 | 04-Nov-25 A | 09-Jan-26 A
TR-1005 | GT #3 Main Unit - Barge Transport to Port of Houston | 0 | 04-Nov-25 A | 18-Nov-25 A
TR-1020 | GT #2 Main Unit - Barge Transport to Port of Houston | 0 | 04-Nov-25 A | 18-Nov-25 A
TR-1030 | GT #1 Main Unit - Barge Transport to Port of Houston | 0 | 04-Nov-25 A | 18-Nov-25 A
TR-1145 | GT #3 Main Unit - Truck from Port of Houston to Shop | 0 | 19-Nov-25 A | 19-Nov-25 A
TR-1160 | GT #2 Main Unit - Truck from Port of Houston to Shop | 0 | 19-Nov-25 A | 21-Nov-25 A
TR-1165 | GT #1 Main Unit - Truck from Port of Houston to Shop | 0 | 19-Nov-25 A | 21-Nov-25 A
TR-1135 | Steam Turbine - Barge Transport to Port of Houston | 0 | 08-Dec-25 A | 08-Jan-26 A
TR-1175 | Steam Turbine - Truck from Port of Houston to Refurb shop | 0 | 09-Jan-26 A | 09-Jan-26 A
Refurbishment |  | 37 | 20-Nov-25 A | 2026-03-09
Turbines |  | 36 | 20-Nov-25 A | 2026-02-26
GT #3 |  | 7 | 21-Nov-25 A | 2026-01-23
RF-1000 | GT #3 - Receive and Begin Disassembly | 0 | 21-Nov-25 A | 27-Nov-25 A
RF-1010 | GT #3 - Clean and Inspect | 0 | 25-Nov-25 A | 2026-01-16
RF-1020 | GT #3 - Shop Scope | 0 | 25-Nov-25 A | 2026-01-16
RF-1090 | GT #3 - Assembly | 7 | 2026-01-16 | 2026-01-23
GT #1 |  | 12 | 20-Nov-25 A | 2026-01-29
RF-1035 | GT #1 - Clean and Inspect | 0 | 26-Nov-25 A | 2026-01-16
RF-1040 | GT #1 - Shop Scope | 1 | 26-Nov-25 A | 2026-01-16
RF-1015 | GT #1 - Receive and Begin Disassembly | 10 | 20-Nov-25 A | 2026-01-27
RF-1100 | GT #1 - Assembly | 12 | 09-Dec-25 A | 2026-01-29
GT #2 |  | 36 | 21-Nov-25 A | 2026-02-26
RF-1005 | GT #2 - Receive and Begin Disassembly | 0 | 21-Nov-25 A | 2026-01-16
RF-1025 | GT #2 - Clean and Inspect | 8 | 08-Dec-25 A | 2026-01-24
RF-1030 | GT #2 - Shop Scope | 27 | 07-Dec-25 A | 2026-02-16
RF-1095 | GT #2 - Assembly | 36 | 08-Dec-25 A | 2026-02-26
Generators |  | 37 | 20-Nov-25 A | 2026-03-09
Unit #3 |  | 22 | 21-Nov-25 A | 2026-02-16
RF-1045 | Unit #3 Generator - Receive at Shop and Set in Position | 0 | 21-Nov-25 A | 04-Dec-25 A
RF-1110 | Unit #3 Generator - Heat Exchanger Inspection | 0 | 05-Dec-25 A | 11-Dec-25 A
RF-1125 | Unit #3 Generator - Rotor Inspection and Testing | 0 | 21-Nov-25 A | 15-Dec-25 A
RF-1050 | Unit #3 Generator - Stator Inspection and Testing | 0 | 05-Dec-25 A | 15-Dec-25 A
RF-1135 | Unit #3 Generator - Reassemble Generator | 28 | 2026-01-16 | 2026-02-12
RF-1055 | Unit #3 Generator - Transport to Foundation | 3 | 2026-02-13 | 2026-02-16
Unit #2 |  | 22 | 20-Nov-25 A | 2026-02-23
RF-1140 | Unit #2 Generator - Receive at Shop and Set in Position | 0 | 20-Nov-25 A | 02-Dec-25 A
RF-1145 | Unit #2 Generator - Heat Exchanger Inspection | 0 | 01-Dec-25 A | 11-Dec-25 A
RF-1150 | Unit #2 Generator - Stator Inspection and Testing | 0 | 03-Dec-25 A | 12-Dec-25 A
RF-1165 | Unit #2 Generator - Rotor Inspection and Testing | 0 | 03-Dec-25 A | 14-Dec-25 A
RF-1170 | Unit #2 Generator - Reassemble Generator | 28 | 2026-01-23 | 2026-02-19
RF-1160 | Unit #2 Generator - Transport to Foundation | 3 | 2026-02-20 | 2026-02-23
Unit #1 |  | 22 | 20-Nov-25 A | 2026-03-09
RF-1175 | Unit #1 Generator - Receive at Shop and Set in Position | 0 | 20-Nov-25 A | 29-Nov-25 A
RF-1185 | Unit #1 Generator - Stator Inspection and Testing | 0 | 30-Nov-25 A | 06-Dec-25 A
RF-1200 | Unit #1 Generator - Rotor Inspection and Testing | 0 | 26-Nov-25 A | 07-Dec-25 A
RF-1180 | Unit #1 Generator - Heat Exchanger Inspection | 0 | 01-Dec-25 A | 11-Dec-25 A
RF-1205 | Unit #1 Generator - Reassemble Generator | 28 | 2026-02-06 | 2026-03-05
RF-1195 | Unit #1 Generator - Transport to Foundation | 3 | 2026-03-06 | 2026-03-09
Engineering |  | 65 | 21-Jul-25 A | 2026-04-16
Process |  | 0 | 04-Aug-25 A | 16-Jan-26 A
FIDs (P&IDs) |  | 0 | 04-Aug-25 A | 16-Jan-26 A
EN-PR-100 | Receive and Review Existing FIDs | 0 | 04-Aug-25 A | 07-Aug-25 A
EN-PR-125 | Process Data - Chiller / WSAC Study | 0 | 14-Aug-25 A | 25-Aug-25 A
EN-PR-140 | Process Data - Fuel Gas System (LC Filters / FG Cntl Valve) - DS by end of this week | 0 | 25-Aug-25 A | 29-Aug-25 A
EN-PR-105 | Draft FIDs - IFR (Existing Equipment) | 0 | 14-Aug-25 A | 29-Aug-25 A
EN-PR-110 | FIDs - Review (Existing Equipment) | 0 | 02-Sep-25 A | 03-Sep-25 A
EN-PR-155 | Process Data - Cooling System (Cooling Tower for Generators / Air Cooled Closed System Glycol for Turbine) | 0 | 25-Aug-25 A | 08-Sep-25 A
EN-PR-130 | Draft P&IDs - IFR (Simple Cycle Complete Set) | 0 | 01-Sep-25 A | 26-Sep-25 A
EN-PR-145 | Process Data - Water Systems (Well Water / Demin Water) pending TM 2500 | 0 | 25-Aug-25 A | 03-Oct-25 A
EN-PR-135 | P&IDs - Review (Simple Cycle Complete Set) | 0 | 29-Sep-25 A | 03-Oct-25 A
EN-PR-160 | Determination of Ammonia Line size and associated connections | 0 | 06-Oct-25 A | 20-Oct-25 A
EN-PR-115 | P&IDs - Pick up Comments and IFD (Simple Cycle Complete Set) | 0 | 06-Oct-25 A | 31-Oct-25 A
EN-PR-120 | P&IDs - IFC | 0 | 10-Nov-25 A | 16-Jan-26 A
Civil |  | 10 | 21-Jul-25 A | 2026-01-29
General |  | 0 | 21-Jul-25 A | 19-Dec-25 A
EN-CV-100 | 3D Modeling - Civil Modeling | 0 | 21-Jul-25 A | 19-Dec-25 A
Piles |  | 0 | 04-Sep-25 A | 24-Oct-25 A
EN-ST-150 | Pile Schedule (Drilled Piers) - IFR | 0 | 04-Sep-25 A | 08-Oct-25 A
EN-ST-485 | Pile Schedule (Drilled Piers) - IFC | 0 | 09-Oct-25 A | 24-Oct-25 A
CT #1 |  | 0 | 21-Jul-25 A | 19-Sep-25 A
EN-CS-105 | Engineering and Design Foundations for GT #1 & Skids - IFR | 0 | 21-Jul-25 A | 03-Sep-25 A
EN-CS-120 | Engineering and Design Foundations for GT #1 & Skids - IFC | 0 | 04-Sep-25 A | 19-Sep-25 A
CT #2 |  | 0 | 04-Aug-25 A | 19-Sep-25 A
EN-CS-110 | Engineering and Design Foundations for GT #2 & Skids - IFR | 0 | 04-Aug-25 A | 03-Sep-25 A
EN-CS-130 | Engineering and Design Foundations for GT #2 & Skids - IFC | 0 | 04-Sep-25 A | 19-Sep-25 A
CT #3 |  | 0 | 04-Aug-25 A | 19-Sep-25 A
EN-CS-115 | Engineering and Design Foundations for GT #3 & Skids - IFR | 0 | 04-Aug-25 A | 03-Sep-25 A
EN-CS-135 | Engineering and Design Foundations for GT #3 & Skids - IFC | 0 | 04-Sep-25 A | 19-Sep-25 A
SCR #1 |  | 0 | 22-Sep-25 A | 24-Oct-25 A
EN-ST-155 | Engineering and Design Foundations for SCR #1 & Skids - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-165 | Engineering and Design Foundations for SCR #1 & Skids - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-160 | Engineering and Design Foundations for SCR #1 & Skids - IFC | 0 | 16-Oct-25 A | 24-Oct-25 A
SCR #2 |  | 0 | 22-Sep-25 A | 24-Oct-25 A
EN-ST-170 | Engineering and Design Foundations for SCR #2 & Skids - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-175 | Engineering and Design Foundations for SCR #2 & Skids - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-180 | Engineering and Design Foundations for SCR #2 & Skids - IFC | 0 | 16-Oct-25 A | 24-Oct-25 A
SCR #3 |  | 0 | 22-Sep-25 A | 24-Oct-25 A
EN-ST-185 | Engineering and Design Foundations for SCR #3 & Skids - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-190 | Engineering and Design Foundations for SCR #3 & Skids - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-195 | Engineering and Design Foundations for SCR #3 & Skids - IFC | 0 | 16-Oct-25 A | 24-Oct-25 A
GSUs |  | 0 | 22-Sep-25 A | 19-Dec-25 A
EN-ST-200 | Engineering and Design Foundations for GSUs - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-205 | Engineering and Design Foundations for GSUs - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-210 | Engineering and Design Foundations for GSUs - IFC | 0 | 16-Oct-25 A | 19-Dec-25 A
Auxillary Transformers |  | 0 | 22-Sep-25 A | 07-Nov-25 A
EN-ST-215 | Engineering and Design Foundations for Auxillary Transformers - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-220 | Engineering and Design Foundations for Auxillary Transformers - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-225 | Engineering and Design Foundations for Auxillary Transformers - IFC | 0 | 16-Oct-25 A | 07-Nov-25 A
Tempering Fans (3) |  | 0 | 22-Sep-25 A | 07-Nov-25 A
EN-ST-230 | Engineering and Design Foundations for Tempering Fans (3) - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-235 | Engineering and Design Foundations for Tempering Fans (3) - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-240 | Engineering and Design Foundations for Tempering Fans (3) - IFC | 0 | 16-Oct-25 A | 07-Nov-25 A
Dilution Skid for SCR (3) |  | 0 | 22-Sep-25 A | 07-Nov-25 A
EN-ST-245 | Engineering and Design Foundations for Dilution Skid for SCR (3) - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-255 | Engineering and Design Foundations for Dilution Skid for SCR (3) - IFC | 0 | 07-Nov-25 A | 07-Nov-25 A
Water Injection Skids (3) |  | 0 | 22-Sep-25 A | 24-Oct-25 A
EN-ST-260 | Engineering and Design Foundations for Water Injection Skids (3) - IFR | 0 | 22-Sep-25 A | 08-Oct-25 A
EN-ST-265 | Engineering and Design Foundations for Water Injection Skids (3) - Pick up Comments | 0 | 09-Oct-25 A | 15-Oct-25 A
EN-ST-270 | Engineering and Design Foundations for Water Injection Skids (3) - IFC | 0 | 16-Oct-25 A | 24-Oct-25 A
Slop Tank Containment |  | 0 | 09-Jan-26 A | 16-Jan-26 A
EN-ST-275 | Engineering and Design Slop Tank Containment - Scope of Work | 0 | 09-Jan-26 A | 16-Jan-26 A
Glycol Cooling water pumps |  | 10 | 09-Jan-26 A | 2026-01-29
EN-ST-560 | Engineering and Design Foundations for Glycol Pump - IFR | 0 | 09-Jan-26 A | 15-Jan-26 A
EN-ST-570 | Engineering and Design Foundations for Glycol Pump - Pick up Comments | 4 | 2026-01-16 | 2026-01-21
EN-ST-580 | Engineering and Design Foundations for Glycol Pump - IFC | 6 | 2026-01-22 | 2026-01-29
Water Wash Skid |  | 0 | 20-Oct-25 A | 14-Nov-25 A
EN-ST-335 | Engineering and Design Foundations for Water Wash Skid - IFR | 0 | 20-Oct-25 A | 25-Oct-25 A
EN-ST-340 | Engineering and Design Foundations for Water Wash Skid - Pick up Comments | 0 | 27-Oct-25 A | 11-Nov-25 A
EN-ST-345 | Engineering and Design Foundations for Water Wash Skid - IFC | 0 | 12-Nov-25 A | 14-Nov-25 A
SCR Ammonia Injection Skid Foundation |  | 7 | 09-Jan-26 A | 2026-01-26
EN-ST-590 | Engineering and Design Foundations for SCR Ammonia Injection Skid - IFR | 0 | 09-Jan-26 A | 15-Jan-26 A
EN-ST-600 | Engineering and Design Foundations for SCR Ammonia Injection Skid - Pick up Comments | 4 | 2026-01-16 | 2026-01-21
EN-ST-610 | Engineering and Design Foundations for SCR Ammonia Injection Skid - IFC | 3 | 2026-01-22 | 2026-01-26
Ammonia Dilution Skid |  | 0 | 29-Sep-25 A | 24-Oct-25 A
EN-ST-425 | Engineering and Design Foundations for Ammonia Injection Skid - IFR | 0 | 29-Sep-25 A | 08-Oct-25 A
EN-ST-430 | Engineering and Design Foundations for Ammonia Injection Skid - Pick up Comments | 0 | 09-Oct-25 A | 14-Oct-25 A
EN-ST-435 | Engineering and Design Foundations for Ammonia Injection Skid - IFC | 0 | 15-Oct-25 A | 24-Oct-25 A
CT Control Modules |  | 0 | 13-Oct-25 A | 24-Oct-25 A
EN-ST-410 | Engineering and Design Foundations for CT Control Modules - IFC | 0 | 13-Oct-25 A | 24-Oct-25 A
MCC Building |  | 0 | 13-Oct-25 A | 02-Jan-26 A
EN-ST-395 | Engineering and Design Foundations for MCC Building - IFR (Lynn E-Bulding Dwg IFA 11/21/25) | 0 | 13-Oct-25 A | 05-Dec-25 A
EN-ST-400 | Engineering and Design Foundations for MCC Building - Pick up Comments | 0 | 19-Dec-25 A | 19-Dec-25 A
EN-ST-405 | Engineering and Design Foundations for MCC Building - IFC | 0 | 22-Dec-25 A | 02-Jan-26 A
Air Compressor Package |  | 9 | 09-Jan-26 A | 2026-01-28
EN-ST-380 | Engineering and Design Foundations for Air Compressor Package - IFR | 4 | 09-Jan-26 A | 2026-01-21
EN-ST-385 | Engineering and Design Foundations for Air Compressor Package - Pick up Comments | 2 | 2026-01-22 | 2026-01-23
EN-ST-390 | Engineering and Design Foundations for Air Compressor Package - IFC | 3 | 2026-01-26 | 2026-01-28
MEE Fog Skids (3) |  | 0 | 29-Sep-25 A | 24-Oct-25 A
EN-ST-365 | Engineering and Design Foundations for MEE Fog Skids (3) - IFR | 0 | 29-Sep-25 A | 08-Oct-25 A
EN-ST-370 | Engineering and Design Foundations for MEE Fog Skids (3) - Pick up Comments | 0 | 09-Oct-25 A | 14-Oct-25 A
EN-ST-375 | Engineering and Design Foundations for MEE Fog Skids (3) - IFC | 0 | 15-Oct-25 A | 24-Oct-25 A
Fencing |  | 0 | 08-Dec-25 A | 08-Jan-26 A
EN-ST-500 | Fencing Drawing - IFR | 0 | 08-Dec-25 A | 19-Dec-25 A
EN-ST-510 | Fencing Drawing - Review | 0 | 02-Jan-26 A | 07-Jan-26 A
EN-ST-520 | Fencing Drawing - IFC | 0 | 08-Jan-26 A | 08-Jan-26 A
Structrual Steel |  | 19 | 08-Sep-25 A | 2026-02-11
EN-ST-100 | 3D Modeling - Structural Steel (Main Members) | 0 | 08-Sep-25 A | 24-Oct-25 A
EN-ST-125 | 3D Modeling - Structural Steel (Remaining Steel) | 0 | 06-Oct-25 A | 12-Jan-26 A
Helical Piles |  | 0 | 15-Sep-25 A | 03-Oct-25 A
EN-ST-490 | Helical Piles - Pile Schedule with Reactions IFB (Connection Details included) | 0 | 15-Sep-25 A | 03-Oct-25 A
EN-ST-495 | Helical Piles - SOW and Bid Package | 0 | 02-Oct-25 A | 03-Oct-25 A
Pipe Rack Steel |  | 0 | 15-Sep-25 A | 14-Nov-25 A
EN-ST-105 | Main Steel BOM / Steel Model for Bidders | 0 | 15-Sep-25 A | 22-Sep-25 A
EN-ST-550 | Main Steel Issue PR Bridge Dwgs - IFF | 0 | 20-Oct-25 A | 04-Nov-25 A
EN-ST-120 | Main Steel Issue Main Steel Dwgs - IFF | 0 | 20-Oct-25 A | 14-Nov-25 A
Misc Supports |  | 19 | 02-Jan-26 A | 2026-02-11
EN-ST-145 | Remaining Steel BOM | 3 | 2026-01-16 | 2026-01-20
EN-ST-130 | Remaining Steel Issue Main Steel Dwgs - IFR | 9 | 02-Jan-26 A | 2026-01-28
EN-ST-135 | Remaining Steel Issue Main Steel Dwgs - Pick up Comments | 5 | 2026-01-29 | 2026-02-04
EN-ST-140 | Remaining Steel Issue Main Steel Dwgs - IFC | 5 | 2026-02-05 | 2026-02-11
Mechanical |  | 0 | 21-Jul-25 A | 08-Jan-26 A
Lists |  | 0 | 04-Aug-25 A | 07-Nov-25 A
EN-ME-100 | Generate Equipment List - IFR Rev0 | 0 | 04-Aug-25 A | 13-Aug-25 A
EN-ME-555 | Generate Equipment List - IFR Rev1 | 0 | 14-Aug-25 A | 22-Aug-25 A
EN-ME-635 | Generate Valve List (Control Valves for Simple Cycle) | 0 | 01-Sep-25 A | 05-Sep-25 A
EN-ME-560 | Generate Equipment List - IFR Rev 2 (wCooling System) | 0 | 25-Aug-25 A | 12-Sep-25 A
EN-ME-1700 | Generate Equipment List - IFD | 0 | 15-Sep-25 A | 10-Oct-25 A
EN-ME-410 | Generate Pipe Specs - For Record | 0 | 11-Aug-25 A | 20-Oct-25 A
EN-ME-105 | Generate Line List | 0 | 27-Oct-25 A | 07-Nov-25 A
EN-ME-1850 | SP Item List | 0 | 03-Nov-25 A | 07-Nov-25 A
EN-ME-645 | Manual Valve List (Simple Cycle) | 0 | 03-Nov-25 A | 07-Nov-25 A
Equipment Requisitions |  | 0 | 21-Jul-25 A | 08-Jan-26 A
HRSG |  | 0 | 21-Jul-25 A | 24-Jul-25 A
EN-ME-110 | HRSG - Develop Requisition and Issue for Quote | 0 | 21-Jul-25 A | 24-Jul-25 A
SCR (Tempering Fans (3) / Ammonia Inj Pumps (3) / Power for CEMs) |  | 0 | 25-Aug-25 A | 24-Oct-25 A
EN-ME-170 | SCR - Receive GAs | 0 | 25-Aug-25 A | 12-Sep-25 A
EN-ME-175 | SCR - Receive P&IDs and One Lines | 0 | 15-Sep-25 A | 24-Oct-25 A
Transformers - Step Down (2) AT-1 / AT-2 |  | 0 | 04-Aug-25 A | 20-Oct-25 A
EN-ME-265 | Step Down XMR AT-1 / AT-2 - Develop Requisition and Issue for Quote | 0 | 04-Aug-25 A | 06-Aug-25 A
EN-ME-285 | Step Down XMR AT-1 / AT-2 - Receive GAs | 0 | 23-Sep-25 A | 20-Oct-25 A
Switchboard & Transfer Switches |  | 0 | 22-Jul-25 A | 14-Aug-25 A
EN-ME-1785 | Switchboard & Transfer Switches - Develop Requisition and Issue for Quote | 0 | 22-Jul-25 A | 14-Aug-25 A
Wet Surface Air Cooler (WSAC) |  | 0 | 22-Sep-25 A | 14-Nov-25 A
EN-ME-380 | WSAC Package - Recieve Quote | 0 | 22-Sep-25 A | 26-Sep-25 A
EN-ME-395 | WSAC Package - Receive GAs | 0 | 15-Oct-25 A | 14-Nov-25 A
Drain Transfer Pump - Centrifugal |  | 0 | 06-Oct-25 A | 08-Oct-25 A
EN-ME-450 | Oily Water Pumps - Develop Requisition and Issue for Quote | 0 | 06-Oct-25 A | 08-Oct-25 A
MCCs |  | 0 | 06-Oct-25 A | 24-Oct-25 A
EN-ME-415 | MCCs - Develop Requisition and Issue for Quote | 0 | 06-Oct-25 A | 09-Oct-25 A
EN-ME-435 | MCCs - Receive GAs | 0 | 17-Oct-25 A | 24-Oct-25 A
Instrument Air Package |  | 0 | 15-Sep-25 A | 08-Jan-26 A
EN-ME-720 | Instrument Air Package - Develop Requisition and Issue for Quote | 0 | 15-Sep-25 A | 18-Sep-25 A
EN-ME-740 | Instrument Air Package - Receive GAs | 0 | 26-Dec-25 A | 08-Jan-26 A
Last Chance Filters |  | 0 | 25-Aug-25 A | 08-Jan-26 A
EN-ME-600 | Last Chance Filters - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 17-Sep-25 A
EN-ME-620 | Last Chance Filters - Receive GAs | 0 | 18-Nov-25 A | 08-Jan-26 A
Fuel Gas Let Down Skid |  | 0 | 25-Aug-25 A | 18-Sep-25 A
EN-ME-565 | Fuel Gas Package (includes Controls) - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 18-Sep-25 A
Control Module Skid / Gas Turbines (Refurbish) |  | 0 | 25-Aug-25 A | 13-Oct-25 A
EN-ME-755 | Control Module Skid / Gas Turbines (Refurbish) - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 13-Oct-25 A
Raw / Service Water Storage Tank |  | 0 | 13-Oct-25 A | 08-Jan-26 A
EN-ME-895 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Develop Requisition and Issue for Quote | 0 | 13-Oct-25 A | 20-Oct-25 A
EN-ME-915 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Receive GAs | 0 | 20-Nov-25 A | 08-Jan-26 A
Service Water Pumps |  | 0 | 06-Oct-25 A | 08-Jan-26 A
EN-ME-930 | Service Water Pumps - Develop Requisition and Issue for Quote | 0 | 06-Oct-25 A | 08-Oct-25 A
EN-ME-950 | Service Water Pumps - Receive GAs | 0 | 12-Dec-25 A | 08-Jan-26 A
Inlet Air Filter |  | 0 | 06-Oct-25 A | 05-Dec-25 A
EN-ME-1245 | Inlet Air Filter - Develop Requisition and Issue for Quote | 0 | 06-Oct-25 A | 09-Oct-25 A
EN-ME-1265 | Inlet Air Filter - Receive GAs | 0 | 04-Dec-25 A | 05-Dec-25 A
MCC Building |  | 0 | 13-Oct-25 A | 04-Dec-25 A
EN-ME-1740 | MCC Building - Develop Requisition and Issue for Quote | 0 | 13-Oct-25 A | 20-Oct-25 A
EN-ME-1760 | MCC Building - Receive GAs | 0 | 30-Oct-25 A | 04-Dec-25 A
Piping |  | 0 | 21-Jul-25 A | 31-Dec-25 A
3D Scanning and Modeling |  | 0 | 29-Jul-25 A | 13-Dec-25 A
EN-PP-120 | 3D Modeling (from scan and new site) | 0 | 29-Jul-25 A | 15-Aug-25 A
EN-PP-145 | Piping BOM - UG (All except Firewater and fnal FG Tie-In) | 0 | 19-Aug-25 A | 16-Oct-25 A
EN-PP-135 | 3D Modeling New SIte | 0 | 19-Aug-25 A | 13-Dec-25 A
Plot Plan |  | 0 | 21-Jul-25 A | 14-Nov-25 A
EN-PP-105 | Plot Plan - Issue for Review | 0 | 11-Aug-25 A | 15-Aug-25 A
EN-PP-110 | Plot Plan Review | 0 | 18-Aug-25 A | 19-Aug-25 A
EN-PP-115 | Plot Plan - Issue for Design | 0 | 20-Aug-25 A | 22-Aug-25 A
EN-PP-140 | Plot Plan - Issue for Design Rev2 | 0 | 25-Aug-25 A | 19-Sep-25 A
EN-PP-150 | Plot Plan - Issue for Design | 0 | 22-Sep-25 A | 10-Oct-25 A
EN-CS-100 | UG Pipe Layout - IFR | 0 | 21-Jul-25 A | 13-Oct-25 A
EN-CS-140 | UG Pipe Layout - IFD | 0 | 14-Nov-25 A | 14-Nov-25 A
EN-PP-125 | Plot Plan - Issue for Construction | 0 | 14-Nov-25 A | 14-Nov-25 A
Lists |  | 0 | 20-Oct-25 A | 11-Nov-25 A
EN-PP-100 | Generate Line List | 0 | 20-Oct-25 A | 11-Nov-25 A
ISO Production |  | 0 | 20-Oct-25 A | 31-Dec-25 A
EN-PP-160 | AG - Drop 80% BOM for Purchase | 0 | 10-Nov-25 A | 21-Nov-25 A
EN-PP-130 | UG - Drop ISOs for Check / IFC | 0 | 20-Oct-25 A | 09-Dec-25 A
EN-PP-155 | AG - Drop ISOs for Check / IFC- Final BOM | 0 | 26-Dec-25 A | 31-Dec-25 A
Electrical |  | 16 | 27-Jul-25 A | 2026-02-06
Load List and One-Lines |  | 0 | 27-Jul-25 A | 10-Oct-25 A
EN-EL-105 | Develop Load List | 0 | 27-Jul-25 A | 06-Aug-25 A
EN-EL-110 | Develop One Lines - Key | 0 | 28-Jul-25 A | 06-Aug-25 A
EN-EL-135 | Develop One Lines - Detail (Preliminary - work in progress) | 0 | 07-Aug-25 A | 01-Sep-25 A
EN-EL-155 | Develop One Lines - IFD | 0 | 02-Sep-25 A | 10-Oct-25 A
Conduit & Cable Schedule |  | 0 | 18-Aug-25 A | 23-Dec-25 A
EN-EL-115 | Develop and Issue Conduit & Cable Schedule | 0 | 18-Aug-25 A | 09-Dec-25 A
EN-EL-170 | Develop and Issue UG I&E Duct Bank Plans - IFC | 0 | 27-Oct-25 A | 23-Dec-25 A
Grounding Plans and Details |  | 0 | 25-Aug-25 A | 12-Nov-25 A
EN-EL-100 | Develop and Issue Grounding Plans and Details | 0 | 25-Aug-25 A | 12-Nov-25 A
Area Classification |  | 0 | 25-Aug-25 A | 15-Dec-25 A
EN-EL-160 | Area Classification IFR | 0 | 25-Aug-25 A | 14-Nov-25 A
EN-EL-165 | Area Classification IFC | 0 | 04-Dec-25 A | 15-Dec-25 A
Cable Tray Plans and Details |  | 0 | 19-Sep-25 A | 09-Jan-26 A
EN-EL-145 | Modeling for Building / Racks / layout from piping | 0 |  | 19-Sep-25 A
EN-EL-150 | Cable Tray BOM (identified Long Leads) | 0 | 14-Nov-25 A | 14-Nov-25 A
EN-EL-120 | Develop and Issue Cable Tray Plans and Details | 0 | 07-Oct-25 A | 09-Jan-26 A
Lighting Plans and Details |  | 0 | 27-Oct-25 A | 09-Jan-26 A
EN-EL-175 | Develop and Issue Lighting Plans and Details - IFR | 0 | 19-Dec-25 A | 23-Dec-25 A
EN-EL-185 | Develop and Issue Lighting Plans and Details - Review | 0 | 26-Dec-25 A | 05-Jan-26 A
EN-EL-125 | Develop and Issue Lighting Plans and Details - IFC | 0 | 27-Oct-25 A | 09-Jan-26 A
Motor Schematics |  | 0 | 01-Jan-26 A | 2026-01-22
EN-EL-130 | Develop and Issue Motor Schematics | 0 | 01-Jan-26 A | 2026-01-22
Electrical Requisitions |  | 16 | 01-Oct-25 A | 2026-02-06
GSU Relays |  | 16 | 01-Oct-25 A | 2026-02-06
EN-EL-190 | GSU Relays - Issue Purchase Order | 0 | 01-Oct-25 A | 02-Oct-25 A
EN-EL-200 | GSU Relays - Ready To Ship | 11 | 03-Oct-25 A | 2026-01-30
EN-EL-205 | GSU Relays - Deliver to Site | 5 | 2026-02-02 | 2026-02-06
E004 - BOP PLC Panel |  | 15 | 13-Oct-25 A | 2026-02-05
EN-ME-650 | BOP PLC Panel - Develop Requisition and Issue for Quote | 0 | 13-Oct-25 A | 10-Nov-25 A
EN-ME-670 | BOP PLC Panel - Receive GAs | 15 | 2026-01-16 | 2026-02-05
Instrumentation & Controls |  | 65 | 25-Aug-25 A | 2026-04-16
Instrument Index & IO List |  | 2 | 25-Aug-25 A | 2026-01-19
EN-IT-155 | Instrument Index and IO List - IFR | 0 | 25-Aug-25 A | 05-Sep-25 A
EN-IT-160 | Instrument Index and IO List - IFC | 2 | 25-Aug-25 A | 2026-01-19
Control Wiring Drawings |  | 0 | 25-Aug-25 A | 09-Jan-26 A
EN-IT-170 | Control Drawings - IFR | 0 | 25-Aug-25 A | 19-Dec-25 A
EN-IT-165 | Control Drawings - IFC | 0 | 22-Dec-25 A | 09-Jan-26 A
Junction Box Drawings |  | 11 | 20-Oct-25 A | 2026-01-30
EN-IT-175 | Junction Box / Instrument Drawings - IFR | 0 | 20-Oct-25 A | 12-Jan-26 A
EN-IT-180 | Junction Box Drawings - IFC | 11 | 13-Jan-26 A | 2026-01-30
Wiring Drawings |  | 6 | 08-Sep-25 A | 2026-01-23
EN-IT-185 | Control / Wiring Drawings - IFR | 0 | 08-Sep-25 A | 19-Dec-25 A
EN-IT-190 | Control / Wiring Drawings - IFC | 6 | 22-Dec-25 A | 2026-01-23
Instrument Location Plan |  | 0 | 26-Sep-25 A | 06-Nov-25 A
EN-IT-195 | Instrument Location Plan - IFC | 0 | 26-Sep-25 A | 06-Nov-25 A
Controls |  | 62 | 01-Dec-25 A | 2026-04-13
PLC Layout Drawings |  | 0 | 26-Dec-25 A | 29-Dec-25 A
EN-IC-1050 | PLC Layout Drawings | 0 | 26-Dec-25 A | 29-Dec-25 A
Wiring Drawings |  | 8 | 08-Dec-25 A | 2026-01-27
EN-IC-1000 | Wiring Drawings IFR | 0 | 08-Dec-25 A | 16-Jan-26 A
EN-IC-1060 | Wiring Drawings IFC | 8 | 2026-01-16 | 2026-01-27
PLC Programming |  | 22 | 08-Dec-25 A | 2026-02-16
EN-IC-1100 | BOP_PLC | 22 | 08-Dec-25 A | 2026-02-16
3rd Party Testing |  | 36 | 2026-01-27 | 2026-03-17
EN-IC-1010 | Air Compressor Package | 2 | 2026-01-27 | 2026-01-28
EN-IC-1030 | Black Start Generator | 2 | 2026-02-18 | 2026-02-19
EN-IC-1040 | Protect & Relay Interface | 2 | 2026-02-18 | 2026-02-19
EN-IC-1020 | SCR Package | 2 | 2026-03-16 | 2026-03-17
HMI Programming |  | 22 | 01-Dec-25 A | 2026-02-16
EN-IC-1110 | HMI Programming | 22 | 01-Dec-25 A | 2026-02-16
EN-IC-1120 | FAT | 0 | 2026-02-16 | 2026-02-16
Network Setup and Configuration |  | 62 | 06-Jan-26 A | 2026-04-13
EN-IC-1070 | HMI Server | 6 | 06-Jan-26 A | 2026-01-23
EN-IC-1080 | Thin Client | 4 | 2026-01-23 | 2026-01-29
EN-IC-1090 | Network Swtiches | 4 | 2026-01-29 | 2026-02-04
EN-IC-1130 | On_Site Set-up | 8 | 2026-04-02 | 2026-04-13
Instrument & Controls Requisitions |  | 65 | 02-Jan-26 A | 2026-04-16
Control System |  | 65 | 02-Jan-26 A | 2026-04-16
EN-ME-1665 | Control System - Develop Requisition and Issue for Quote | 0 | 02-Jan-26 A | 2026-01-16
EN-ME-1670 | Control System - Recieve Quote | 5 | 2026-01-16 | 2026-01-22
EN-ME-1675 | Control System - Evaluate and Issue Requisition for Purchase | 2 | 2026-01-23 | 2026-01-26
EN-ME-1680 | Control System - Issue Purchase Order | 3 | 2026-01-27 | 2026-01-29
EN-ME-1685 | Control System - Receive GAs | 15 | 2026-01-30 | 2026-02-19
EN-ME-1690 | Control System - Ready To Ship | 50 | 2026-01-30 | 2026-04-09
EN-ME-1695 | Control System - Deliver to Site | 5 | 2026-04-10 | 2026-04-16
PLC & HMI |  | 60 | 02-Jan-26 A | 2026-04-09
EN-IT-210 | PLC & HMI - Develop Requisition and Issue for Quote | 0 | 02-Jan-26 A | 08-Jan-26 A
EN-IT-215 | PLC & HMI - Recieve Quote | 5 | 09-Jan-26 A | 2026-01-22
EN-IT-220 | PLC & HMI - Evaluate and Issue Requisition for Purchase | 5 | 2026-01-23 | 2026-01-29
EN-IT-225 | PLC & HMI - Issue Purchase Order | 5 | 2026-01-30 | 2026-02-05
EN-IT-235 | PLC & HMI - Ready To Ship | 40 | 2026-02-06 | 2026-04-02
EN-IT-240 | PLC & HMI - Deliver to Site | 5 | 2026-04-03 | 2026-04-09
Misc Instrumentation |  | 60 | 02-Jan-26 A | 2026-04-09
EN-IT-245 | Misc Instrumentation - Develop Requisition and Issue for Quote | 0 | 02-Jan-26 A | 08-Jan-26 A
EN-IT-250 | Misc Instrumentation - Recieve Quote | 5 | 09-Jan-26 A | 2026-01-22
EN-IT-255 | Misc Instrumentation - Evaluate and Issue Requisition for Purchase | 5 | 2026-01-23 | 2026-01-29
EN-IT-260 | Misc Instrumentation - Issue Purchase Order | 5 | 2026-01-30 | 2026-02-05
EN-IT-265 | Misc Instrumentation - Ready To Ship | 40 | 2026-02-06 | 2026-04-02
EN-IT-270 | Misc Instrumentation - Deliver to Site | 5 | 2026-04-03 | 2026-04-09
Procurement |  | 93 | 21-Jul-25 A | 2026-05-26
Mechanical Equipment |  | 93 | 21-Jul-25 A | 2026-05-26
G001 - HRSG |  | 0 | 25-Jul-25 A | 26-Aug-25 A
EN-ME-115 | HRSG - Recieve Quote | 0 | 25-Jul-25 A | 26-Aug-25 A
G002 - SCR (Tempering Fans (3) / Ammonia Inj Pumps (3) / Power for CEMs) |  | 51 | 21-Jul-25 A | 2026-03-27
EN-ME-155 | SCR - Recieve Quote | 0 | 21-Jul-25 A | 24-Jul-25 A
EN-ME-160 | SCR - Evaluate and Issue Requisition for Purchase | 0 | 25-Jul-25 A | 18-Aug-25 A
EN-ME-165 | SCR - Issue Purchase Order | 0 | 18-Aug-25 A | 22-Aug-25 A
EN-ME-180 | SCR - Ready To Ship (stack) | 28 | 22-Sep-25 A | 2026-02-17
EN-ME-185 | SCR - Ready to Ship (TA and Ducting) | 52 | 22-Sep-25 A | 2026-03-17
EN-ME-195 | SCR - Ready To Ship (Cataysts) | 61 | 22-Sep-25 A | 2026-03-27
G003A - GSU (GTs T1 / T2 / T3) |  | 0 | 28-Jul-25 A | 02-Jan-26 A
EN-ME-220 | GSU GTs - Ready To Ship | 0 | 28-Jul-25 A | 16-Oct-25 A
EN-ME-225 | GSU GTs - Deliver to Site | 0 | 17-Oct-25 A | 02-Jan-26 A
G003B - GSU Relay Protection Panel |  | 23 | 28-Jul-25 A | 2026-02-17
EN-ME-1775 | GSU Relay Protection Panel - Issue Purchase Order | 0 | 28-Jul-25 A | 16-Oct-25 A
EN-ME-1780 | GSU Relay Protection Panel - Deliver to Site | 28 | 17-Oct-25 A | 2026-02-17
G005 - Transformers - Step Down AT-1, AT-2, AT-11, AT-21, AT-22 |  | 5 | 04-Aug-25 A | 2026-01-22
EN-ME-315 | Step Down XMR AT-11 / AT-21 - Issue Purchase Order | 0 | 04-Aug-25 A | 15-Sep-25 A
EN-ME-325 | Step Down XMR AT-11 / AT-21 - Ready To Ship | 0 | 16-Sep-25 A | 2026-01-16
EN-ME-1955 | Step Down XMR AT-11 / AT-11 - Ready To Ship | 0 | 16-Sep-25 A | 2026-01-16
EN-ME-1965 | Step Down XMR AT-11 / AT-22 - Ready To Ship | 0 | 16-Sep-25 A | 2026-01-16
EN-ME-1975 | Step Down XMR AT-11 / AT-3 - Ready To Ship | 0 | 16-Sep-25 A | 2026-01-16
EN-ME-1985 | Step Down XMR AT-11 / AT-2 - Ready To Ship | 0 | 16-Sep-25 A | 2026-01-16
EN-ME-1995 | Step Down XMR AT-11 / AT-1 - Ready To Ship | 0 | 16-Sep-25 A | 2026-01-16
EN-ME-330 | Step Down XMR AT-11 / AT-21 - Deliver to Site | 5 | 2026-01-16 | 2026-01-21
EN-ME-2005 | Step Down XMR AT-11 / AT-11 - Deliver to Site | 5 | 2026-01-16 | 2026-01-22
EN-ME-2015 | Step Down XMR AT-11 / AT-22 - Deliver to Site | 5 | 2026-01-16 | 2026-01-22
EN-ME-2025 | Step Down XMR AT-11 / AT-3 - Deliver to Site | 5 | 2026-01-16 | 2026-01-22
EN-ME-2035 | Step Down XMR AT-11 / AT-2 - Deliver to Site | 5 | 2026-01-16 | 2026-01-22
EN-ME-2045 | Step Down XMR AT-11 / AT-1 - Deliver to Site | 5 | 2026-01-16 | 2026-01-22
G005A - Switchboard & Transfer Switches |  | 4 | 11-Aug-25 A | 2026-01-21
EN-ME-1790 | Switchboard & Transfer Switches - Recieve Quote | 0 | 11-Aug-25 A | 14-Aug-25 A
EN-ME-1800 | Switchboard & Transfer Switches - Issue Purchase Order | 0 | 15-Aug-25 A | 05-Sep-25 A
EN-ME-1810 | Switchboard & Transfer Switches - Ready To Ship (Held at Supplier) | 0 | 08-Sep-25 A | 2026-01-16
EN-ME-1815 | Switchboard & Transfer Switches - Deliver to Site | 5 | 2026-01-16 | 2026-01-21
G007A - Wet Surface Air Cooler (WSAC) |  | 31 | 25-Aug-25 A | 2026-02-28
EN-ME-375 | WSAC Package - Develop Requisition and Issue for Quote | 0 | 25-Aug-25 A | 27-Aug-25 A
EN-ME-390 | WSAC Package - Issue Purchase Order | 0 | 29-Sep-25 A | 14-Oct-25 A
EN-ME-400 | WSAC Package - Ready To Ship (Units 1& 2) | 27 | 15-Oct-25 A | 2026-02-16
EN-ME-405 | WSAC Package - Deliver to Site (Units 1 & 2) | 5 | 2026-02-17 | 2026-02-21
EN-ME-1940 | WSAC Package - Ready To Ship (Unit 3) | 33 | 15-Oct-25 A | 2026-02-23
EN-ME-1945 | WSAC Package - Deliver to Site (Unit 3) | 5 | 2026-02-24 | 2026-02-28
G008 - G012 - Pumps (Demin / WSAC / Glycol / WW / SW) |  | 10 | 09-Oct-25 A | 2026-01-29
EN-ME-455 | Pumps (Demin / WSAC / Glycol / WW / SW) - Recieve Quote | 0 | 09-Oct-25 A | 28-Oct-25 A
EN-ME-460 | Pumps (Demin / WSAC / Glycol / WW / SW) - Evaluate and Issue Requisition for Purchase | 0 | 29-Oct-25 A | 18-Nov-25 A
EN-ME-465 | Pumps (Demin / WSAC / Glycol / WW / SW) - Issue Purchase Order | 0 | 20-Nov-25 A | 21-Nov-25 A
EN-ME-475 | Pumps Demineralized Water Pumps - Ready To Ship | 0 | 24-Nov-25 A | 05-Jan-26 A
EN-ME-490 | Pumps Waste Water Pumps (WSAC) - Ready To Ship | 0 | 24-Nov-25 A | 05-Jan-26 A
EN-ME-510 | Pumps Glycol Cooling Water Pumps - Ready To Ship | 0 | 24-Nov-25 A | 05-Jan-26 A
EN-ME-530 | Pumps Ammonia Injection Pumps - Ready To Ship | 0 | 24-Nov-25 A | 05-Jan-26 A
EN-ME-480 | Pumps Demineralized Water Pumps - Ready To Ship | 0 | 05-Jan-26 A | 06-Jan-26 A
EN-ME-500 | Pumps Waste Water Pumps (WSAC) - Deliver to Site | 0 | 05-Jan-26 A | 06-Jan-26 A
EN-ME-520 | Pumps Glycol Cooling Water Pumps - Deliver to Site | 0 | 05-Jan-26 A | 06-Jan-26 A
EN-ME-640 | Pumps Service Water Pumps - Deliver to Site | 0 | 05-Jan-26 A | 06-Jan-26 A
EN-ME-540 | Pumps Ammonia Injection Pumps - Deliver to Site | 4 | 2026-01-16 | 2026-01-20
EN-ME-550 | Pumps Service Water Pumps - Ready To Ship | 12 | 24-Nov-25 A | 2026-01-29
G013 - Sump Pumps |  | 15 | 09-Oct-25 A | 2026-02-05
EN-ME-1855 | Sump Pump - Recieve Quote | 0 | 09-Oct-25 A | 28-Oct-25 A
EN-ME-1860 | Sump Pump - Evaluate and Issue Requisition for Purchase | 0 | 29-Oct-25 A | 19-Nov-25 A
EN-ME-1865 | Sump Pump - Issue Purchase Order | 0 | 20-Nov-25 A | 21-Nov-25 A
EN-ME-1870 | Sump Pump - Ready To Ship | 13 | 24-Nov-25 A | 2026-01-30
EN-ME-1875 | Sump Pump - Deliver to Site | 5 | 2026-01-31 | 2026-02-05
G014 - Instrument Air Package |  | 13 | 19-Sep-25 A | 2026-02-03
EN-ME-725 | G014 - Instrument Air Package - Recieve Quote | 0 | 19-Sep-25 A | 07-Oct-25 A
EN-ME-730 | G014 - Instrument Air Package - Evaluate and Issue Requisition for Purchase | 0 | 08-Oct-25 A | 19-Nov-25 A
EN-ME-735 | G014 - Instrument Air Package - Issue Purchase Order | 0 | 20-Nov-25 A | 21-Nov-25 A
EN-ME-745 | G014 - Instrument Air Package - Ready To Ship | 11 | 22-Nov-25 A | 2026-01-28
EN-ME-750 | G014 - Instrument Air Package - Deliver to Site | 5 | 2026-01-29 | 2026-02-03
G015 - Inlet Air Filter |  | 14 | 10-Oct-25 A | 2026-02-04
EN-ME-1250 | Inlet Air Filter - Recieve Quote | 0 | 10-Oct-25 A | 17-Oct-25 A
EN-ME-1255 | Inlet Air Filter - Evaluate and Issue Requisition for Purchase | 0 | 20-Oct-25 A | 14-Nov-25 A
EN-ME-1260 | Inlet Air Filter - Issue Purchase Order | 0 | 17-Nov-25 A | 21-Nov-25 A
EN-ME-1270 | Inlet Air Filter - Ready To Ship | 12 | 24-Nov-25 A | 2026-01-29
EN-ME-1275 | Inlet Air Filter - Deliver to Site | 5 | 2026-01-30 | 2026-02-04
G017 - Last Chance Filters |  | 35 | 14-Oct-25 A | 2026-03-05
EN-ME-605 | Last Chance Filters - Recieve Quote | 0 | 14-Oct-25 A | 28-Oct-25 A
EN-ME-610 | Last Chance Filters - Evaluate and Issue Requisition for Purchase | 0 | 29-Oct-25 A | 06-Nov-25 A
EN-ME-615 | Last Chance Filters - Issue Purchase Order | 0 | 07-Nov-25 A | 17-Nov-25 A
EN-ME-625 | Last Chance Filters - Ready To Ship (2 of 6) | 27 | 18-Nov-25 A | 2026-02-16
EN-ME-630 | Last Chance Filters - Deliver to Site (2 of 6) | 5 | 2026-02-17 | 2026-02-21
EN-ME-1935 | Last Chance Filters - Ready To Ship (4 of 6) | 37 | 18-Nov-25 A | 2026-02-27
EN-ME-1930 | Last Chance Filters - Deliver to Site (4 of 6) | 5 | 2026-02-28 | 2026-03-05
G018 - Fuel Gas PCV's (Regulators) |  | 60 | 19-Sep-25 A | 2026-03-26
EN-ME-570 | Fuel Gas Package (includes Controls) - Recieve Quote | 0 | 19-Sep-25 A | 2026-01-16
EN-ME-575 | Fuel Gas Package (includes Controls) - Evaluate and Issue Requisition for Purchase | 2 | 2026-01-16 | 2026-01-17
EN-ME-580 | Fuel Gas Package (includes Controls) - Issue Purchase Order | 3 | 2026-01-19 | 2026-01-21
EN-ME-590 | Fuel Gas Package (includes Controls) - Ready To Ship | 50 | 2026-01-22 | 2026-03-20
EN-ME-595 | Fuel Gas Package (includes Controls) - Deliver to Site | 5 | 2026-03-21 | 2026-03-26
G021 / G030 - Control Module (Refurb) |  | 0 | 03-Nov-25 A | 20-Nov-25 A
EN-ME-1880 | Control Module Refurb - Issue PO for Controls refurb | 0 | 03-Nov-25 A | 12-Nov-25 A
EN-ME-1885 | Control Module Refurb - Refurb Control Modules KO Mtg | 0 | 20-Nov-25 A | 20-Nov-25 A
G022 /G033 / G034 / G039 - SW Tank/ Demin Tank / Slop Tank |  | 23 | 21-Oct-25 A | 2026-02-17
EN-ME-900 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Recieve Quote | 0 | 21-Oct-25 A | 29-Oct-25 A
EN-ME-905 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Evaluate and Issue Requisition for Purchase | 0 | 30-Oct-25 A | 06-Nov-25 A
EN-ME-910 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Issue Purchase Order | 0 | 07-Nov-25 A | 19-Nov-25 A
EN-ME-920 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Ready To Ship | 26 | 21-Nov-25 A | 2026-02-14
EN-ME-925 | SW Tank/ Demin Tank / Slop Tank / Waste Water Tank - Deliver to Site | 2 | 2026-02-16 | 2026-02-17
G032 - Electrical Building |  | 36 | 20-Oct-25 A | 2026-03-07
EN-ME-1905 | Electrical Building - Recieve Quote | 0 | 20-Oct-25 A | 23-Oct-25 A
EN-ME-1910 | Electrical Building - Evaluate and Issue Requisition for Purchase | 0 | 24-Oct-25 A | 27-Oct-25 A
EN-ME-1915 | Electrical Building - Issue Purchase Order | 0 | 28-Oct-25 A | 28-Oct-25 A
EN-ME-1920 | Electrical Building - Ready To Ship | 39 | 29-Oct-25 A | 2026-03-02
EN-ME-1925 | Electrical Building - Deliver to Site | 5 | 2026-03-03 | 2026-03-07
E003 - LV MCCs |  | 0 | 13-Oct-25 A | 08-Jan-26 A
EN-ME-420 | MCCs - Recieve Quote | 0 | 13-Oct-25 A | 15-Oct-25 A
EN-ME-425 | MCCs - Evaluate and Issue Requisition for Purchase | 0 | 16-Oct-25 A | 16-Oct-25 A
EN-ME-430 | MCCs - Issue Purchase Order | 0 | 16-Oct-25 A | 16-Oct-25 A
EN-ME-440 | MCCs - Ready To Ship (holding at Supplier) | 0 | 17-Oct-25 A | 05-Dec-25 A
EN-ME-445 | MCCs - Deliver to E-Building Vendor | 0 | 05-Jan-26 A | 08-Jan-26 A
E004 - BOP PLC Panel |  | 29 | 11-Nov-25 A | 2026-02-25
EN-ME-655 | BOP PLC Panel - Recieve Quote | 0 | 11-Nov-25 A | 17-Nov-25 A
EN-ME-660 | BOP PLC Panel - Evaluate and Issue Requisition for Purchase | 0 | 18-Nov-25 A | 25-Nov-25 A
EN-ME-665 | BOP PLC Panel - Issue Purchase Order | 0 | 26-Nov-25 A | 2026-01-16
EN-ME-675 | BOP PLC Panel - Ready To Ship | 30 | 2026-01-16 | 2026-02-19
EN-ME-680 | BOP PLC Panel - Deliver to Site | 5 | 2026-02-20 | 2026-02-25
O&M Contractor |  | 93 | 22-Sep-25 A | 2026-05-26
EN-ME-1820 | O&M - RFQ To bidders | 0 | 22-Sep-25 A | 20-Oct-25 A
EN-ME-1825 | O&M - Receive Bids | 0 | 21-Oct-25 A | 31-Oct-25 A
EN-ME-1830 | O&M - Contract Award | 0 | 03-Nov-25 A | 12-Dec-25 A
EN-ME-1835 | O&M - Mobilize to Site | 0 | 12-Dec-25 A | 2026-01-16
EN-ME-1840 | O&M - Start O&M Personnel Training by EPC Contractor | 0 | 2026-01-16 | 2026-01-16
EN-ME-1845 | O&M - Three GT Plant IN-Service (Simple Cycle) | 53 | 2026-03-26 | 2026-05-26
Bulk Material & Fabrication |  | 34 | 22-Sep-25 A | 2026-03-04
Civil Material |  | 18 | 24-Sep-25 A | 2026-02-10
PR-1065 | Civil Material - RFQ issued / Bids Received / Evaluated | 0 | 24-Sep-25 A | 16-Oct-25 A
PR-1075 | Civil Material - Issue PO to Vendor | 0 | 17-Oct-25 A | 21-Oct-25 A
PR-1085 | Civil Material - Fab and receive Rebar | 0 | 22-Oct-25 A | 2026-01-16
PR-1345 | Fab & Recieve Embeds | 7 | 09-Jan-26 A | 2026-01-26
PR-1095 | Civil Material - Fab and receive Anchor Bolts | 22 | 22-Oct-25 A | 2026-02-10
Helical Piles |  | 0 | 03-Oct-25 A | 14-Nov-25 A
PR-1260 | Helical Piles - RFQ issued / Bids Received / Evaluated / WPS approved | 0 | 03-Oct-25 A | 14-Oct-25 A
PR-1265 | Helical Piles - Issue PO to Shop for Fabrication | 0 | 15-Oct-25 A | 16-Oct-25 A
PR-1270 | Helical Piles - Fabricate | 0 | 20-Oct-25 A | 05-Nov-25 A
PR-1275 | Helical Piles - shipped to Site | 0 | 06-Nov-25 A | 14-Nov-25 A
Structural Steel |  | 12 | 02-Oct-25 A | 2026-02-28
PR-1105 | Structural Steel - RFQ issued / Bids Received / Evaluated / WPS approved | 0 | 02-Oct-25 A | 15-Oct-25 A
PR-1115 | Structural Steel - Issue PO to Shop for Fabrication | 0 | 16-Oct-25 A | 25-Oct-25 A
PR-1125 | Structural Steel - Fabricate and Deliver Steel Bridges | 0 | 27-Oct-25 A | 15-Dec-25 A
PR-1280 | Structural Steel - Fabricate Main Pipe Racks | 0 | 27-Oct-25 A | 12-Jan-26 A
PR-1135 | Structural Steel - Fabricate and Ship Misc Supports | 15 | 2026-02-12 | 2026-02-28
Piping |  | 26 | 22-Sep-25 A | 2026-02-14
Field |  | 26 | 22-Sep-25 A | 2026-02-14
PR-1005 | Approve WPS (Field Welding) | 0 | 22-Sep-25 A | 17-Dec-25 A
A2840 | Field Fabricate Above Ground Piping | 26 | 2026-01-16 | 2026-02-14
E&I |  | 34 | 12-Nov-25 A | 2026-03-04
Grounding |  | 0 | 12-Nov-25 A | 2026-01-16
PR-1145 | Grounding - RFQ issued / Bids Received / Evaluated | 0 | 12-Nov-25 A | 13-Nov-25 A
PR-1155 | Grounding - Issue PO to Vendor | 0 | 14-Nov-25 A | 02-Dec-25 A
PR-1165 | Grounding - Fab and receive on site | 0 | 03-Dec-25 A | 2026-01-16
Cable Tray |  | 22 | 09-Jan-26 A | 2026-02-10
PR-1205 | Cable Tray - RFQ issued / Bids Received / Evaluated | 0 | 09-Jan-26 A | 15-Jan-26 A
PR-1215 | Cable Tray - Issue PO to Vendor | 0 | 15-Jan-26 A | 15-Jan-26 A
PR-1225 | Cable Tray - Fab and receive on site | 22 | 16-Jan-26 A | 2026-02-10
Conduit & Cable |  | 16 | 13-Nov-25 A | 2026-02-07
PR-1175 | Conduit & Cable Schedule - RFQ issued / Bids Received / Evaluated | 0 | 13-Nov-25 A | 01-Dec-25 A
PR-1185 | Conduit & Cable Schedule - Issue PO to Vendor | 2 | 02-Dec-25 A | 2026-01-17
PR-1195 | Conduit & Cable Schedule - Fab and receive on site | 18 | 2026-01-19 | 2026-02-07
Lighting |  | 36 | 2026-01-16 | 2026-02-26
PR-1235 | Lighting and Receptacles - RFQ issued / Bids Received / Evaluated | 12 | 2026-01-16 | 2026-01-29
PR-1245 | Lighting and Receptacles - Issue PO to Vendor | 6 | 2026-01-30 | 2026-02-05
PR-1255 | Lighting and Receptacles - Fab and receive on site | 18 | 2026-02-06 | 2026-02-26
Junction Boxes |  | 28 | 2026-01-31 | 2026-03-04
PR-1285 | Junction Boxes - RFQ issued / Bids Received / Evaluated | 8 | 2026-01-31 | 2026-02-09
PR-1305 | Junction Boxes - Issue PO to Vendor | 4 | 2026-02-10 | 2026-02-13
PR-1315 | Junction Boxes - Fab and receive on site | 16 | 2026-02-14 | 2026-03-04
Wiring |  | 24 | 2026-01-24 | 2026-02-20
PR-1295 | Wiring - RFQ issued / Bids Received / Evaluated | 8 | 2026-01-24 | 2026-02-02
PR-1325 | Wiring - Issue PO to Vendor | 4 | 2026-02-03 | 2026-02-06
PR-1335 | Wiring - Fab and receive on site | 12 | 2026-02-07 | 2026-02-20
Construction (On-Site) |  | 73 | 24-Sep-25 A | 2026-04-28
General |  | 0 | 24-Sep-25 A | 03-Nov-25 A
CN-1395 | Survey and Benchmarks set (Park Hill) | 0 | 24-Sep-25 A | 26-Sep-25 A
CN-1495 | Construction Mobilization | 0 | 01-Oct-25 A | 03-Nov-25 A
Site Work |  | 15 | 06-Oct-25 A | 2026-01-30
CN-1790 | Trailer Area | 0 | 13-Oct-25 A | 17-Oct-25 A
CN-1535 | Haul and Stockpile | 0 | 06-Oct-25 A | 30-Oct-25 A
CN-1810 | Momentum Laydown | 0 | 13-Oct-25 A | 31-Oct-25 A
CN-1000 | Clearing and Grubbing - 1' depth | 0 | 20-Oct-25 A | 01-Nov-25 A
CN-1760 | Scarifing Site - 6" | 0 | 22-Oct-25 A | 12-Nov-25 A
CN-1800 | RPS Laydown | 0 | 20-Oct-25 A | 24-Nov-25 A
CN-1820 | Parking | 0 | 27-Oct-25 A | 25-Nov-25 A
CN-1505 | Cut for Detention Pond | 0 | 18-Nov-25 A | 09-Dec-25 A
CN-ST-1000 | Site Cut for bathtub | 0 | 20-Nov-25 A | 02-Jan-26 A
CN-ST-1010 | Site Fill and Compact | 15 | 17-Nov-25 A | 2026-01-30
Temporary Facilities |  | 0 | 02-Oct-25 A | 05-Nov-25 A
CN-1510 | Place Order for Trailers / Generators | 0 | 02-Oct-25 A | 15-Oct-25 A
CN-1530 | Delivery of Trailers / Generators | 0 | 20-Oct-25 A | 31-Oct-25 A
CN-1515 | Install Generators | 0 | 27-Oct-25 A | 05-Nov-25 A
CN-1525 | Receive and Install Trailers | 0 | 27-Oct-25 A | 05-Nov-25 A
Civil & Structural |  | 65 | 07-Nov-25 A | 2026-03-21
Drilled Piers |  | 0 | 07-Nov-25 A | 04-Dec-25 A
CN-1860 | SCR 2 Drill Piers | 0 | 17-Nov-25 A | 19-Nov-25 A
CN-1960 | SCR 2 Seal Slab | 0 | 18-Nov-25 A | 20-Nov-25 A
CN-1840 | Turbine 3 Drill Piers | 0 | 11-Nov-25 A | 21-Nov-25 A
CN-1930 | Turbine 3 Seal Slab | 0 | 12-Nov-25 A | 21-Nov-25 A
CN-1540 | Turbine 1 Drill Piers | 0 | 13-Nov-25 A | 22-Nov-25 A
CN-1870 | SCR 3 Drill Piers | 0 | 19-Nov-25 A | 22-Nov-25 A
CN-1880 | Turbine 2 Drill Piers | 0 | 07-Nov-25 A | 24-Nov-25 A
CN-1920 | Turbine 2 Seal Slab | 0 | 10-Nov-25 A | 24-Nov-25 A
CN-1940 | Turbine 1 Seal Slab | 0 | 13-Nov-25 A | 24-Nov-25 A
CN-1970 | SCR 3 Seal Slab | 0 | 21-Nov-25 A | 24-Nov-25 A
CN-1850 | SCR 1 Drill Piers - 7th Drill Pier Waiting on Rebar Delivery | 0 | 17-Nov-25 A | 03-Dec-25 A
CN-1950 | SCR 1 Seal Slab - Waiting on 7th Drill Pier Completion | 0 | 03-Dec-25 A | 04-Dec-25 A
GT #1 & Generator |  | 46 | 24-Nov-25 A | 2026-03-14
CN-3090 | GT #1 - Install Rebar | 0 | 24-Nov-25 A | 10-Dec-25 A
CN-CV-1130 | GT #1 - Install Forms | 0 | 24-Nov-25 A | 09-Jan-26 A
CN-CV-1090 | GT #1 - Install Anchor Bolts and Imbeds | 7 | 09-Jan-26 A | 2026-02-03
CN-CV-1110 | GT #1 - Pour Concrete | 2 | 2026-03-02 | 2026-03-03
CN-CV-1300 | GT #1 - Finish Concrete + 10d Cure | 11 | 2026-03-04 | 2026-03-14
GT #2 & Generator |  | 40 | 01-Dec-25 A | 2026-03-14
CN-3130 | GT #2 - Install Rebar | 0 | 01-Dec-25 A | 10-Dec-25 A
CN-CV-1140 | GT #2 - Install Forms | 0 | 04-Dec-25 A | 09-Jan-26 A
CN-CV-1240 | GT #2 - Install Anchor Bolts and Imbeds | 7 | 12-Jan-26 A | 2026-02-09
CN-CV-1280 | GT #2 - Pour Concrete | 2 | 2026-03-02 | 2026-03-03
CN-CV-1500 | GT #2 - Finish Concrete + 10d Cure | 11 | 2026-03-04 | 2026-03-14
GT #3 & Generator |  | 58 | 08-Dec-25 A | 2026-03-14
CN-3050 | GT #3 - Install Rebar | 0 | 08-Dec-25 A | 11-Dec-25 A
CN-CV-1150 | GT #3 - Install Forms | 1 | 18-Dec-25 A | 2026-01-16
CN-CV-1230 | GT #3 - Install Anchor Bolts and Imbeds | 7 | 2026-02-09 | 2026-02-16
CN-CV-1270 | GT #3 - Pour Concrete | 2 | 2026-03-02 | 2026-03-03
CN-CV-1490 | GT #3 - Finish Concrete + 10d Cure | 11 | 2026-03-04 | 2026-03-14
SCR #1 Foundation |  | 32 | 08-Dec-25 A | 2026-03-14
CN-2050 | SCR #1-Install Forms | 0 | 08-Dec-25 A | 11-Dec-25 A
CN-CV-1200 | SCR #1 Install Rebar | 0 | 15-Dec-25 A | 18-Dec-25 A
CN-CV-1720 | SCR #1 Install Anchor Bolts and Anchor Bolts (STACK) | 4 | 2026-02-10 | 2026-02-14
CN-CV-1850 | SCR #1 Pour Concrete | 2 | 2026-03-02 | 2026-03-03
CN-CV-3070 | SCR #1 Finish Concrete + 10d Cure | 11 | 2026-03-04 | 2026-03-14
SCR #2 Foundation |  | 27 | 09-Dec-25 A | 2026-03-14
CN-CV-1210 | SCR #2 Install Rebar | 0 | 15-Dec-25 A | 18-Dec-25 A
CN-CV-1250 | SCR #2-Install Forms | 0 | 09-Dec-25 A | 18-Dec-25 A
CN-CV-1320 | SCR #2 Install Anchor Bolts and Anchor Bolts (STACK) | 4 | 2026-02-16 | 2026-02-19
CN-CV-1380 | SCR #2 Pour Concrete | 2 | 2026-03-02 | 2026-03-03
CN-CV-1730 | SCR #2 Finish Concrete + 10d Cure | 11 | 2026-03-04 | 2026-03-14
SCR #3 Foundation |  | 58 | 15-Dec-25 A | 2026-03-14
CN-CV-1260 | SCR #3-Install Forms | 0 | 15-Dec-25 A | 18-Dec-25 A
CN-CV-1220 | SCR #3 Install Rebar | 0 | 15-Dec-25 A | 08-Jan-26 A
CN-CV-1330 | SCR #3 Install Anchor Bolts and Anchor Bolts (STACK) | 4 | 2026-01-16 | 2026-01-19
CN-CV-1390 | SCR #3 Pour Concrete | 2 | 2026-03-02 | 2026-03-03
CN-CV-1740 | SCR #3 Finish Concrete + 10d Cure | 11 | 2026-03-04 | 2026-03-14
Water Injection Skid Foundation - #1 |  | 27 | 2026-01-20 | 2026-02-15
CN-CV-1960 | Water Injection Skid Foundation Unit #1 - Install Forms | 5 | 2026-01-20 | 2026-01-24
CN-CV-2070 | Water Injection Skid Foundation Unit #1 - Install Rebar | 1 | 2026-01-25 | 2026-01-25
CN-CV-2220 | Water Injection Skid Foundation Unit #1 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2340 | Water Injection Skid Foundation Unit #1 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-2790 | Water Injection Skid Foundation Unit #1 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
Water Injection Skid Foundation - #2 |  | 26 | 2026-01-21 | 2026-02-15
CN-CV-2150 | Water Injection Skid Foundation Unit #2 - Install Forms | 5 | 2026-01-21 | 2026-01-25
CN-CV-2290 | Water Injection Skid Foundation Unit #2 - Install Rebar | 1 | 2026-01-26 | 2026-01-26
CN-CV-2410 | Water Injection Skid Foundation Unit #2 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2520 | Water Injection Skid Foundation Unit #2 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-2950 | Water Injection Skid Foundation Unit #2 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
Water Injection Skid Foundation - #3 |  | 25 | 2026-01-22 | 2026-02-15
CN-CV-2300 | Water Injection Skid Foundation Unit #3 - Install Forms | 5 | 2026-01-22 | 2026-01-26
CN-CV-2420 | Water Injection Skid Foundation Unit #3 - Install Rebar | 1 | 2026-01-27 | 2026-01-27
CN-CV-2530 | Water Injection Skid Foundation Unit #3 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2620 | Water Injection Skid Foundation Unit #3 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-3030 | Water Injection Skid Foundation Unit #3 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
MEE Fog Pump Skid Foundation - #1 |  | 25 | 2026-01-22 | 2026-02-15
CN-CV-2580 | MEE Fog Pump Skid Foundation #1 - Install Forms | 4 | 2026-01-22 | 2026-01-25
CN-CV-2810 | MEE Fog Pump Skid Foundation #1 - Install Rebar | 2 | 2026-01-26 | 2026-01-27
CN-CV-2910 | MEE Fog Pump Skid Foundation #1 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-3010 | MEE Fog Pump Skid Foundation #1 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-3260 | MEE Fog Pump Skid Foundation #1 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
MEE Fog Pump Skid Foundation - #2 |  | 24 | 2026-01-23 | 2026-02-15
CN-CV-2740 | MEE Fog Pump Skid Foundation #2 - Install Forms | 4 | 2026-01-23 | 2026-01-26
CN-CV-2970 | MEE Fog Pump Skid Foundation #2 - Install Rebar | 2 | 2026-01-27 | 2026-01-28
CN-CV-3050 | MEE Fog Pump Skid Foundation #2 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-3130 | MEE Fog Pump Skid Foundation #2 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-3330 | MEE Fog Pump Skid Foundation #2 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
MEE Fog Pump Skid Foundation - #3 |  | 23 | 2026-01-24 | 2026-02-15
CN-CV-2870 | MEE Fog Pump Skid Foundation #3 - Install Forms | 4 | 2026-01-24 | 2026-01-27
CN-CV-3060 | MEE Fog Pump Skid Foundation #3 - Install Rebar | 2 | 2026-01-28 | 2026-01-29
CN-CV-3140 | MEE Fog Pump Skid Foundation #3 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-3190 | MEE Fog Pump Skid Foundation #3 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-3370 | MEE Fog Pump Skid Foundation #3 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
Tempering Fan Foundation - #1 |  | 26 | 2026-01-22 | 2026-02-16
CN-CV-1880 | Tempering Fan Foundation #1 - Install Forms | 4 | 2026-01-22 | 2026-01-25
CN-CV-1970 | Tempering Fan Foundation #1 - Install Rebar | 1 | 2026-01-26 | 2026-01-26
CN-CV-2080 | Tempering Fan Foundation #1 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2350 | Tempering Fan Foundation #1 - Pour Concrete | 2 | 2026-02-11 | 2026-02-13
CN-CV-2820 | Tempering Fan Foundation #1 - Finish Concrete + 3d Cure | 3 | 2026-02-13 | 2026-02-16
GSU Protection Relay Building Foundation |  | 24 | 2026-01-23 | 2026-02-15
CN-CV-1080 | GSU Protection Relay Building Foundation - Install Forms | 4 | 2026-01-23 | 2026-01-26
CN-CV-1190 | GSU Protection Relay Building Foundation - Install Rebar | 4 | 2026-01-27 | 2026-01-30
CN-CV-1560 | GSU Protection Relay Building Foundation - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-1660 | GSU Protection Relay Building Foundation - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-1790 | GSU Protection Relay Building Foundation - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
Tempering Fan Foundation - #2 |  | 24 | 2026-01-24 | 2026-02-16
CN-CV-1980 | Tempering Fan Foundation #2 - Install Forms | 4 | 2026-01-24 | 2026-01-27
CN-CV-2090 | Tempering Fan Foundation #2 - Install Rebar | 1 | 2026-01-28 | 2026-01-28
CN-CV-2230 | Tempering Fan Foundation #2 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2470 | Tempering Fan Foundation #2 - Pour Concrete | 2 | 2026-02-11 | 2026-02-13
CN-CV-2920 | Tempering Fan Foundation #2 - Finish Concrete + 3d Cure | 3 | 2026-02-13 | 2026-02-16
Tempering Fan Foundation - #3 |  | 22 | 2026-01-26 | 2026-02-16
CN-CV-2100 | Tempering Fan Foundation #3 - Install Forms | 3 | 2026-01-26 | 2026-01-28
CN-CV-2240 | Tempering Fan Foundation #3 - Install Rebar | 1 | 2026-01-29 | 2026-01-29
CN-CV-2360 | Tempering Fan Foundation #3 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2590 | Tempering Fan Foundation #3 - Pour Concrete | 2 | 2026-02-11 | 2026-02-13
CN-CV-3020 | Tempering Fan Foundation #3 - Finish Concrete + 3d Cure | 3 | 2026-02-13 | 2026-02-16
Tempering Fan Foundation - #4 |  | 21 | 2026-01-27 | 2026-02-16
CN-CV-2250 | Tempering Fan Foundation #4 - Install Forms | 4 | 2026-01-27 | 2026-01-30
CN-CV-2370 | Tempering Fan Foundation #4 - Install Rebar | 1 | 2026-01-31 | 2026-01-31
CN-CV-2480 | Tempering Fan Foundation #4 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2670 | Tempering Fan Foundation #4 - Pour Concrete | 2 | 2026-02-11 | 2026-02-13
CN-CV-3090 | Tempering Fan Foundation #4 - Finish Concrete + 3d Cure | 3 | 2026-02-13 | 2026-02-16
Tempering Fan Foundation - #5 |  | 20 | 2026-01-28 | 2026-02-16
CN-CV-2380 | Tempering Fan Foundation #5 - Install Forms | 4 | 2026-01-28 | 2026-01-31
CN-CV-2490 | Tempering Fan Foundation #5 - Install Rebar | 1 | 2026-02-01 | 2026-02-01
CN-CV-2600 | Tempering Fan Foundation #5 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2830 | Tempering Fan Foundation #5 - Pour Concrete | 2 | 2026-02-11 | 2026-02-13
CN-CV-3160 | Tempering Fan Foundation #5 - Finish Concrete + 3d Cure | 3 | 2026-02-13 | 2026-02-16
Tempering Fan Foundation - #6 |  | 19 | 2026-01-29 | 2026-02-16
CN-CV-2390 | Tempering Fan Foundation #6 - Install Forms | 4 | 2026-01-29 | 2026-02-01
CN-CV-2500 | Tempering Fan Foundation #6 - Install Rebar | 1 | 2026-02-02 | 2026-02-02
CN-CV-2610 | Tempering Fan Foundation #6 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2840 | Tempering Fan Foundation #6 - Pour Concrete | 2 | 2026-02-11 | 2026-02-13
CN-CV-3170 | Tempering Fan Foundation #6 - Finish Concrete + 3d Cure | 3 | 2026-02-13 | 2026-02-16
SCR Ammonia Injection Skid Unit #1 Foundation |  | 20 | 2026-01-26 | 2026-02-15
CN-CV-1920 | SCR Ammonia Injection Skid #1 - Install Forms | 4 | 2026-01-26 | 2026-01-30
CN-CV-2040 | SCR Ammonia Injection Skid #1 - Install Rebar | 1 | 2026-01-30 | 2026-01-31
CN-CV-2180 | SCR Ammonia Injection Skid #1 - Install Anchor Bolts | 1 | 2026-02-10 | 2026-02-11
CN-CV-2310 | SCR Ammonia Injection Skid #1 - Pour Concrete | 1 | 2026-02-11 | 2026-02-12
CN-CV-2660 | SCR Ammonia Injection Skid #1 - Finish Concrete + 3d Cure | 3 | 2026-02-12 | 2026-02-15
SCR Ammonia Injection Skid Unit #2 Foundation |  | 10 | 2026-01-29 | 2026-02-08
CN-CV-1930 | SCR Ammonia Injection Skid #2 - Install Forms | 4 | 2026-01-29 | 2026-02-02
CN-CV-2050 | SCR Ammonia Injection Skid #2 - Install Rebar | 1 | 2026-02-02 | 2026-02-03
CN-CV-2190 | SCR Ammonia Injection Skid #2 - Install Anchor Bolts | 1 | 2026-02-03 | 2026-02-04
CN-CV-2320 | SCR Ammonia Injection Skid #2 - Pour Concrete | 1 | 2026-02-04 | 2026-02-05
CN-CV-2760 | SCR Ammonia Injection Skid #2 - Finish Concrete + 3d Cure | 3 | 2026-02-05 | 2026-02-08
SCR Ammonia Injection Skid Unit #3 Foundation |  | 10 | 2026-01-31 | 2026-02-10
CN-CV-1940 | SCR Ammonia Injection Skid #3 - Install Forms | 4 | 2026-01-31 | 2026-02-04
CN-CV-2060 | SCR Ammonia Injection Skid #3 - Install Rebar | 1 | 2026-02-04 | 2026-02-05
CN-CV-2200 | SCR Ammonia Injection Skid #3 - Install Anchor Bolts | 1 | 2026-02-05 | 2026-02-06
CN-CV-2330 | SCR Ammonia Injection Skid #3 - Pour Concrete | 1 | 2026-02-06 | 2026-02-07
CN-CV-2770 | SCR Ammonia Injection Skid #3 - Finish Concrete + 3d Cure | 3 | 2026-02-07 | 2026-02-10
Step Down Transformer Foundation-#1-(West) |  | 15 | 2026-02-02 | 2026-02-17
CN-CV-1840 | Step Down Transformer Foundation and Containment #1 (West) - Install Forms | 7 | 2026-02-02 | 2026-02-09
CN-CV-2030 | Step Down Transformer Foundation and Containment #1 (West) - Install Rebar | 2 | 2026-02-09 | 2026-02-11
CN-CV-2170 | Step Down Transformer Foundation and Containment #1 (West) - Install Anchor Bolts | 1 | 2026-02-11 | 2026-02-12
CN-CV-2440 | Step Down Transformer Foundation and Containment #1 (West) - Pour Concrete | 2 | 2026-02-12 | 2026-02-14
CN-CV-2880 | Step Down Transformer Foundation and Containment #1 (West) - Finish Concrete + 3d Cure | 3 | 2026-02-14 | 2026-02-17
Step Down Transformer Foundation-#2-(West) |  | 15 | 2026-02-02 | 2026-02-17
CN-CV-3510 | Step Down Transformer Foundation and Containment #2 (West) - Install Forms | 7 | 2026-02-02 | 2026-02-09
CN-CV-3520 | Step Down Transformer Foundation and Containment #2 (West) - Install Rebar | 2 | 2026-02-09 | 2026-02-11
CN-CV-3530 | Step Down Transformer Foundation and Containment #2 (West) - Install Anchor Bolts | 1 | 2026-02-11 | 2026-02-12
CN-CV-3540 | Step Down Transformer Foundation and Containment #2 (West) - Pour Concrete | 2 | 2026-02-12 | 2026-02-14
CN-CV-3550 | Step Down Transformer Foundation and Containment #2 (West) - Finish Concrete + 3d Cure | 3 | 2026-02-14 | 2026-02-17
Step Down Transformer Foundation-#3-(West) |  | 15 | 2026-02-02 | 2026-02-17
CN-CV-3560 | Step Down Transformer Foundation and Containment #3 (West) - Install Forms | 7 | 2026-02-02 | 2026-02-09
CN-CV-3570 | Step Down Transformer Foundation and Containment #3 (West) - Install Rebar | 2 | 2026-02-09 | 2026-02-11
CN-CV-3580 | Step Down Transformer Foundation and Containment #3 (West) - Install Anchor Bolts | 1 | 2026-02-11 | 2026-02-12
CN-CV-3590 | Step Down Transformer Foundation and Containment #3 (West) - Pour Concrete | 2 | 2026-02-12 | 2026-02-14
CN-CV-3600 | Step Down Transformer Foundation and Containment #3 (West) - Finish Concrete + 3d Cure | 3 | 2026-02-14 | 2026-02-17
Step Down Transformer Foundation-#21-(East) |  | 15 | 2026-02-05 | 2026-02-20
CN-CV-2160 | Step Down Transformer Foundation and Containment #21 (East) - Install Forms | 7 | 2026-02-05 | 2026-02-12
CN-CV-2430 | Step Down Transformer Foundation and Containment #21 (East) - Install Rebar | 2 | 2026-02-12 | 2026-02-14
CN-CV-2550 | Step Down Transformer Foundation and Containment #21 (East) - Install Anchor Bolts | 1 | 2026-02-14 | 2026-02-15
CN-CV-2750 | Step Down Transformer Foundation and Containment #21 (East) - Pour Concrete | 2 | 2026-02-15 | 2026-02-17
CN-CV-3150 | Step Down Transformer Foundation and Containment #21 (East) - Finish Concrete + 3d Cure | 3 | 2026-02-17 | 2026-02-20
Step Down Transformer Foundation-#22-(East) |  | 15 | 2026-02-05 | 2026-02-20
CN-CV-3610 | Step Down Transformer Foundation and Containment #22 (East) - Install Forms | 7 | 2026-02-05 | 2026-02-12
CN-CV-3620 | Step Down Transformer Foundation and Containment #22 (East) - Install Rebar | 2 | 2026-02-12 | 2026-02-14
CN-CV-3630 | Step Down Transformer Foundation and Containment #22 (East) - Install Anchor Bolts | 1 | 2026-02-14 | 2026-02-15
CN-CV-3640 | Step Down Transformer Foundation and Containment #22 (East) - Pour Concrete | 2 | 2026-02-15 | 2026-02-17
CN-CV-3650 | Step Down Transformer Foundation and Containment #22 (East) - Finish Concrete + 3d Cure | 3 | 2026-02-17 | 2026-02-20
Step Down Transformer Foundation-#11-(East) |  | 15 | 2026-02-05 | 2026-02-20
CN-CV-3660 | Step Down Transformer Foundation and Containment #11 (East) - Install Forms | 7 | 2026-02-05 | 2026-02-12
CN-CV-3670 | Step Down Transformer Foundation and Containment #11 (East) - Install Rebar | 2 | 2026-02-12 | 2026-02-14
CN-CV-3680 | Step Down Transformer Foundation and Containment #11 (East) - Install Anchor Bolts | 1 | 2026-02-14 | 2026-02-15
CN-CV-3690 | Step Down Transformer Foundation and Containment #11 (East) - Pour Concrete | 2 | 2026-02-15 | 2026-02-17
CN-CV-3700 | Step Down Transformer Foundation and Containment #11 (East) - Finish Concrete + 3d Cure | 3 | 2026-02-17 | 2026-02-20
Load Break Switch Foundations 1,2,3 |  | 15 | 2026-01-30 | 2026-02-13
CN-CV-3810 | Load BReak Switch Foundation - Install Forms | 6 | 2026-01-30 | 2026-02-04
CN-CV-3820 | Load BReak Switch Foundation - Install Rebar | 2 | 2026-02-05 | 2026-02-06
CN-CV-3830 | Load BReak Switch Foundation - Install Anchor Bolts | 1 | 2026-02-07 | 2026-02-07
CN-CV-3840 | Load BReak Switch Foundation - Pour Concrete | 2 | 2026-02-08 | 2026-02-09
CN-CV-3850 | Load BReak Switch Foundation - Finish Concrete + 4d Cure | 4 | 2026-02-10 | 2026-02-13
Generator Step Up Transformer Foundation - #1 |  | 26 | 2026-01-26 | 2026-02-20
CN-CV-1050 | GSU T1 Foundation - Install Forms | 14 | 2026-01-26 | 2026-02-08
CN-CV-1160 | GSU T1 Foundation - Install Rebar | 7 | 2026-02-09 | 2026-02-15
CN-CV-1530 | GSU T1 Foundation - Install Anchor Bolts | 1 | 2026-02-16 | 2026-02-16
CN-CV-1630 | GSU T1 Foundation - Pour Concrete | 1 | 2026-02-17 | 2026-02-17
CN-CV-1760 | GSU T1 Foundation - Finish Concrete + 3d Cure | 3 | 2026-02-18 | 2026-02-20
Generator Step Up Transformer Foundation - #2 |  | 26 | 2026-01-30 | 2026-02-24
CN-CV-1060 | GSU T2 Foundation - Install Forms | 14 | 2026-01-30 | 2026-02-12
CN-CV-1170 | GSU T2 Foundation - Install Rebar | 7 | 2026-02-13 | 2026-02-19
CN-CV-1540 | GSU T2 Foundation - Install Anchor Bolts | 1 | 2026-02-20 | 2026-02-20
CN-CV-1640 | GSU T2 Foundation - Pour Concrete | 1 | 2026-02-21 | 2026-02-21
CN-CV-1770 | GSU T2 Foundation - Finish Concrete + 3d Cure | 3 | 2026-02-22 | 2026-02-24
Generator Step Up Transformer Foundation - #3 |  | 26 | 2026-02-03 | 2026-02-28
CN-CV-1070 | GSU T3 Foundation - Install Forms | 14 | 2026-02-03 | 2026-02-16
CN-CV-1180 | GSU T3 Foundation - Install Rebar | 7 | 2026-02-17 | 2026-02-23
CN-CV-1550 | GSU T3 Foundation - Install Anchor Bolts | 1 | 2026-02-24 | 2026-02-24
CN-CV-1650 | GSU T3 Foundation - Pour Concrete | 1 | 2026-02-25 | 2026-02-25
CN-CV-1780 | GSU T3 Foundation - Finish Concrete + 3d Cure | 3 | 2026-02-26 | 2026-02-28
SCR Ammonia Storage Tank |  | 17 | 2026-02-09 | 2026-02-25
CN-CV-3860 | SCR Ammonia Storage Tank - Install Forms | 7 | 2026-02-09 | 2026-02-15
CN-CV-3870 | SCR Ammonia Storage Tank - Install Rebar | 5 | 2026-02-16 | 2026-02-20
CN-CV-3880 | SCR Ammonia Storage Tank - Install Anchor Bolts | 1 | 2026-02-21 | 2026-02-21
CN-CV-3890 | SCR Ammonia Storage Tank - Pour Concrete | 1 | 2026-02-22 | 2026-02-22
CN-CV-3900 | SCR Ammonia Storage Tank - Finish Concrete + 3d Cure | 3 | 2026-02-23 | 2026-02-25
SCR Ammonia Truck Unloading |  | 17 | 2026-02-16 | 2026-03-04
CN-CV-3910 | SCR Ammonia Truck Unloading - Install Forms | 7 | 2026-02-16 | 2026-02-22
CN-CV-3920 | SCR Ammonia Truck Unloading - Install Rebar | 5 | 2026-02-23 | 2026-02-27
CN-CV-3930 | SCR Ammonia Truck Unloading - Install Anchor Bolts | 1 | 2026-02-28 | 2026-02-28
CN-CV-3940 | SCR Ammonia Truck Unloading - Pour Concrete | 1 | 2026-03-01 | 2026-03-01
CN-CV-3950 | SCR Ammonia Truck Unloading - Finish Concrete + 3d Cure | 3 | 2026-03-02 | 2026-03-04
SCR Ammonia Forwarding Skid Foundation |  | 17 | 2026-02-16 | 2026-03-04
CN-CV-2540 | SCR Ammonia Forwarding Skid - Install Forms | 7 | 2026-02-16 | 2026-02-22
CN-CV-2630 | SCR Ammonia Forwarding Skid - Install Rebar | 5 | 2026-02-23 | 2026-02-27
CN-CV-2730 | SCR Ammonia Forwarding Skid - Install Anchor Bolts | 1 | 2026-02-28 | 2026-02-28
CN-CV-2850 | SCR Ammonia Forwarding Skid - Pour Concrete | 1 | 2026-03-01 | 2026-03-01
CN-CV-3180 | SCR Ammonia Forwarding Skid - Finish Concrete + 3d Cure | 3 | 2026-03-02 | 2026-03-04
Wet Surface Air Cooler Foundation (Units 1&2) |  | 18 | 2026-02-16 | 2026-03-05
CN-CV-1310 | WSAC Units 1&2 - Install Forms | 7 | 2026-02-16 | 2026-02-22
CN-CV-1370 | WSAC Units 1&2 - Install Rebar | 5 | 2026-02-23 | 2026-02-27
CN-CV-1510 | WSAC Units 1&2 - Install Anchor Bolts | 1 | 2026-02-28 | 2026-02-28
CN-CV-1710 | WSAC Units 1&2 - Pour Concrete | 2 | 2026-03-01 | 2026-03-02
CN-CV-1870 | WSAC Units 1&2 - Finish Concrete + 3d Cure | 3 | 2026-03-03 | 2026-03-05
Wet Surface Air Cooler Foundation (Unit 3) |  | 18 | 2026-02-16 | 2026-03-05
CN-CV-1340 | WSAC Unit 3 - Install Forms | 7 | 2026-02-16 | 2026-02-22
CN-CV-1400 | WSAC Unit 3 - Install Rebar | 5 | 2026-02-23 | 2026-02-27
CN-CV-1410 | WSAC Unit 3 - Install Anchor Bolts | 1 | 2026-02-28 | 2026-02-28
CN-CV-1440 | WSAC Unit 3 - Pour Concrete | 2 | 2026-03-01 | 2026-03-02
CN-CV-1480 | WSAC Unit 3 - Finish Concrete + 3d Cure | 3 | 2026-03-03 | 2026-03-05
Glycol Cooling water pumps P-200 A/B |  | 14 | 2026-02-18 | 2026-03-03
CN-CV-3760 | Glycol Cooling Water Pumps - Install Forms | 5 | 2026-02-18 | 2026-02-22
CN-CV-3770 | Glycol Cooling Water Pumps - Install Rebar | 3 | 2026-02-23 | 2026-02-25
CN-CV-3780 | Glycol Cooling Water Pumps - Install Anchor Bolts | 1 | 2026-02-26 | 2026-02-26
CN-CV-3790 | Glycol Cooling Water Pumps - Pour Concrete | 2 | 2026-02-27 | 2026-02-28
CN-CV-3800 | Glycol Cooling Water Pumps - Finish Concrete + 3d Cure | 3 | 2026-03-01 | 2026-03-03
Service Water Pumps P-600 A/B |  | 13 | 2026-02-18 | 2026-03-02
CN-CV-3960 | Service Water Pumps P-600 A/B - Install Forms | 5 | 2026-02-18 | 2026-02-22
CN-CV-3970 | Service Water Pumps P-600 A/B - Install Rebar | 3 | 2026-02-23 | 2026-02-25
CN-CV-3980 | Service Water Pumps P-600 A/B - Install Anchor Bolts | 1 | 2026-02-26 | 2026-02-26
CN-CV-3990 | Service Water Pumps P-600 A/B - Pour Concrete | 1 | 2026-02-27 | 2026-02-27
CN-CV-4000 | Service Water Pumps P-600 A/B - Finish Concrete + 3d Cure | 3 | 2026-02-28 | 2026-03-02
Waste Water Loading Pumps P-300 A/B |  | 13 | 2026-02-19 | 2026-03-03
CN-CV-3710 | Waste Water Tank Foundation - Install Forms | 5 | 2026-02-19 | 2026-02-23
CN-CV-3720 | Waste Water Tank Foundation - Install Rebar | 3 | 2026-02-24 | 2026-02-26
CN-CV-3730 | Waste Water Tank Foundation - Install Anchor Bolts | 1 | 2026-02-27 | 2026-02-27
CN-CV-3740 | Waste Water Tank Foundation - Pour Concrete | 1 | 2026-02-28 | 2026-02-28
CN-CV-3750 | Waste Water Tank Foundation - Finish Concrete + 3d Cure | 3 | 2026-03-01 | 2026-03-03
Demin Water Pumps P-400 A/B |  | 13 | 2026-02-19 | 2026-03-03
CN-CV-4010 | Demin Water Pumps P-400 A/B - Install Forms | 5 | 2026-02-19 | 2026-02-23
CN-CV-4020 | Demin Water Pumps P-400 A/B - Install Rebar | 3 | 2026-02-24 | 2026-02-26
CN-CV-4030 | Demin Water Pumps P-400 A/B - Install Anchor Bolts | 1 | 2026-02-27 | 2026-02-27
CN-CV-4040 | Demin Water Pumps P-400 A/B - Pour Concrete | 1 | 2026-02-28 | 2026-02-28
CN-CV-4050 | Demin Water Pumps P-400 A/B - Finish Concrete + 3d Cure | 3 | 2026-03-01 | 2026-03-03
WSAC Waste Water Pumps P-201 A/B |  | 13 | 2026-02-19 | 2026-03-03
CN-CV-4060 | WSAC Waste Water Pumps P-201 A/B - Install Forms | 5 | 2026-02-19 | 2026-02-23
CN-CV-4070 | WSAC Waste Water Pumps P-201 A/B - Install Rebar | 3 | 2026-02-24 | 2026-02-26
CN-CV-4080 | WSAC Waste Water Pumps P-201 A/B - Install Anchor Bolts | 1 | 2026-02-27 | 2026-02-27
CN-CV-4090 | WSAC Waste Water Pumps P-201 A/B - Pour Concrete | 1 | 2026-02-28 | 2026-02-28
CN-CV-4100 | WSAC Waste Water Pumps P-201 A/B - Finish Concrete + 3d Cure | 3 | 2026-03-01 | 2026-03-03
Water Wash Skid Foundation |  | 17 | 2026-02-24 | 2026-03-12
CN-CV-2570 | Water Wash Skid - Install Forms | 7 | 2026-02-24 | 2026-03-02
CN-CV-2800 | Water Wash Skid - Install Rebar | 5 | 2026-03-03 | 2026-03-07
CN-CV-2900 | Water Wash Skid - Install Anchor Bolts | 1 | 2026-03-08 | 2026-03-08
CN-CV-3000 | Water Wash Skid - Pour Concrete | 1 | 2026-03-09 | 2026-03-09
CN-CV-3250 | Water Wash Skid - Finish Concrete + 3d Cure | 3 | 2026-03-10 | 2026-03-12
Slop Tank Foundation |  | 17 | 2026-02-24 | 2026-03-12
CN-CV-2960 | Slop Tank Foundation - Install Forms | 7 | 2026-02-24 | 2026-03-02
CN-CV-3230 | Slop Tank Foundation - Install Rebar | 5 | 2026-03-03 | 2026-03-07
CN-CV-3280 | Slop Tank Foundation - Install Anchor Bolts | 1 | 2026-03-08 | 2026-03-08
CN-CV-3320 | Slop Tank Foundation - Pour Concrete | 1 | 2026-03-09 | 2026-03-09
CN-CV-3420 | Slop Tank Foundation - Finish Concrete + 3d Cure | 3 | 2026-03-10 | 2026-03-12
Air Compressor Package Foundation |  | 13 | 2026-02-24 | 2026-03-08
CN-CV-1290 | Air Compressor Package Foundation - Install Forms | 5 | 2026-02-24 | 2026-02-28
CN-CV-1350 | Air Compressor Package Foundation - Install Rebar | 3 | 2026-03-01 | 2026-03-03
CN-CV-1570 | Air Compressor Package Foundation - Install Anchor Bolts | 1 | 2026-03-04 | 2026-03-04
CN-CV-1670 | Air Compressor Package Foundation - Pour Concrete | 1 | 2026-03-05 | 2026-03-05
CN-CV-1800 | Air Compressor Package Foundation - Finish Concrete + 3d Cure | 3 | 2026-03-06 | 2026-03-08
CT Control Modules Foundation - #1 |  | 17 | 2026-03-01 | 2026-03-17
CN-CV-1360 | CT Control Modules Unit #1 - Install Forms | 7 | 2026-03-01 | 2026-03-07
CN-CV-1420 | CT Control Modules Unit #1 - Install Rebar | 5 | 2026-03-08 | 2026-03-12
CN-CV-1580 | CT Control Modules Unit #1 - Install Anchor Bolts | 1 | 2026-03-13 | 2026-03-13
CN-CV-1680 | CT Control Modules Unit #1 - Pour Concrete | 1 | 2026-03-14 | 2026-03-14
CN-CV-1810 | CT Control Modules Unit #1 - Finish Concrete + 3d Cure | 3 | 2026-03-15 | 2026-03-17
CT Control Modules Foundation - #2 |  | 17 | 2026-03-03 | 2026-03-19
CN-CV-1430 | CT Control Modules Unit #2 - Install Forms | 7 | 2026-03-03 | 2026-03-09
CN-CV-1450 | CT Control Modules Unit #2 - Install Rebar | 5 | 2026-03-10 | 2026-03-14
CN-CV-1590 | CT Control Modules Unit #2 - Install Anchor Bolts | 1 | 2026-03-15 | 2026-03-15
CN-CV-1690 | CT Control Modules Unit #2 - Pour Concrete | 1 | 2026-03-16 | 2026-03-16
CN-CV-1820 | CT Control Modules Unit #2 - Finish Concrete + 3d Cure | 3 | 2026-03-17 | 2026-03-19
CT Control Modules Foundation - #3 |  | 17 | 2026-03-05 | 2026-03-21
CN-CV-1460 | CT Control Modules Unit #3 - Install Forms | 7 | 2026-03-05 | 2026-03-11
CN-CV-1470 | CT Control Modules Unit #3 - Install Rebar | 5 | 2026-03-12 | 2026-03-16
CN-CV-1600 | CT Control Modules Unit #3 - Install Anchor Bolts | 1 | 2026-03-17 | 2026-03-17
CN-CV-1700 | CT Control Modules Unit #3 - Pour Concrete | 1 | 2026-03-18 | 2026-03-18
CN-CV-1830 | CT Control Modules Unit #3 - Finish Concrete + 3d Cure | 3 | 2026-03-19 | 2026-03-21
Area Sump and Sump Pump Foundation - #1 |  | 19 | 2026-02-02 | 2026-02-20
CN-CV-1610 | Area Sump and Sump Pump Foundation #1 - Install Forms | 5 | 2026-02-02 | 2026-02-06
CN-CV-1950 | Area Sump and Sump Pump Foundation #1 - Install Rebar | 6 | 2026-02-07 | 2026-02-12
CN-CV-2210 | Area Sump and Sump Pump Foundation #1 - Install Anchor Bolts | 2 | 2026-02-13 | 2026-02-14
CN-CV-2450 | Area Sump and Sump Pump Foundation #1 - Pour Concrete | 2 | 2026-02-15 | 2026-02-16
CN-CV-2890 | Area Sump and Sump Pump Foundation #1 - Finish Concrete + 3d Cure | 4 | 2026-02-17 | 2026-02-20
Area Sump and Sump Pump Foundation - #2 |  | 19 | 2026-02-02 | 2026-02-20
CN-CV-1860 | Area Sump and Sump Pump Foundation #2 - Install Forms | 5 | 2026-02-02 | 2026-02-06
CN-CV-2560 | Area Sump and Sump Pump Foundation #2 - Install Rebar | 6 | 2026-02-07 | 2026-02-12
CN-CV-2780 | Area Sump and Sump Pump Foundation #2 - Install Anchor Bolts | 2 | 2026-02-13 | 2026-02-14
CN-CV-2980 | Area Sump and Sump Pump Foundation #2 - Pour Concrete | 2 | 2026-02-15 | 2026-02-16
CN-CV-3240 | Area Sump and Sump Pump Foundation #2 - Finish Concrete + 3d Cure | 4 | 2026-02-17 | 2026-02-20
Area Sump and Sump Pump Foundation - #3 |  | 19 | 2026-02-02 | 2026-02-20
CN-CV-2460 | Area Sump and Sump Pump Foundation #3 - Install Forms | 5 | 2026-02-02 | 2026-02-06
CN-CV-3080 | Area Sump and Sump Pump Foundation #3 - Install Rebar | 6 | 2026-02-07 | 2026-02-12
CN-CV-3200 | Area Sump and Sump Pump Foundation #3 - Install Anchor Bolts | 2 | 2026-02-13 | 2026-02-14
CN-CV-3290 | Area Sump and Sump Pump Foundation #3 - Pour Concrete | 2 | 2026-02-15 | 2026-02-16
CN-CV-3400 | Area Sump and Sump Pump Foundation #3 - Finish Concrete + 3d Cure | 4 | 2026-02-17 | 2026-02-20
Area Sump and Sump Pump Foundation - #4 |  | 19 | 2026-02-02 | 2026-02-20
CN-CV-2990 | Area Sump and Sump Pump Foundation #4 - Install Forms | 5 | 2026-02-02 | 2026-02-06
CN-CV-3340 | Area Sump and Sump Pump Foundation #4 - Install Rebar | 6 | 2026-02-07 | 2026-02-12
CN-CV-3380 | Area Sump and Sump Pump Foundation #4 - Install Anchor Bolts | 2 | 2026-02-13 | 2026-02-14
CN-CV-3430 | Area Sump and Sump Pump Foundation #4 - Pour Concrete | 2 | 2026-02-15 | 2026-02-16
CN-CV-3470 | Area Sump and Sump Pump Foundation #4 - Finish Concrete + 3d Cure | 4 | 2026-02-17 | 2026-02-20
Demin Water Mobile Trailer System Foundation - #1 |  | 18 | 2026-02-07 | 2026-02-24
CN-CV-2020 | Demin Water Mobile Trailer System #1 - Install Forms | 5 | 2026-02-07 | 2026-02-11
CN-CV-2640 | Demin Water Mobile Trailer System #1 - Install Rebar | 5 | 2026-02-12 | 2026-02-16
CN-CV-2860 | Demin Water Mobile Trailer System #1 - Install Anchor Bolts | 2 | 2026-02-17 | 2026-02-18
CN-CV-3040 | Demin Water Mobile Trailer System #1 - Pour Concrete | 2 | 2026-02-19 | 2026-02-20
CN-CV-3270 | Demin Water Mobile Trailer System #1 - Finish Concrete + 3d Cure | 4 | 2026-02-21 | 2026-02-24
Demin Water Mobile Trailer System Foundation - #2 |  | 18 | 2026-02-07 | 2026-02-24
CN-CV-2650 | Demin Water Mobile Trailer System #2 - Install Forms | 5 | 2026-02-07 | 2026-02-11
CN-CV-3110 | Demin Water Mobile Trailer System #2 - Install Rebar | 5 | 2026-02-12 | 2026-02-16
CN-CV-3220 | Demin Water Mobile Trailer System #2 - Install Anchor Bolts | 2 | 2026-02-17 | 2026-02-18
CN-CV-3310 | Demin Water Mobile Trailer System #2 - Pour Concrete | 2 | 2026-02-19 | 2026-02-20
CN-CV-3410 | Demin Water Mobile Trailer System #2 - Finish Concrete + 3d Cure | 4 | 2026-02-21 | 2026-02-24
Demin Water Mobile Trailer System Foundation - #3 |  | 18 | 2026-02-07 | 2026-02-24
CN-CV-3120 | Demin Water Mobile Trailer System #3 - Install Forms | 5 | 2026-02-07 | 2026-02-11
CN-CV-3350 | Demin Water Mobile Trailer System #3 - Install Rebar | 5 | 2026-02-12 | 2026-02-16
CN-CV-3390 | Demin Water Mobile Trailer System #3 - Install Anchor Bolts | 2 | 2026-02-17 | 2026-02-18
CN-CV-3440 | Demin Water Mobile Trailer System #3 - Pour Concrete | 2 | 2026-02-19 | 2026-02-20
CN-CV-3480 | Demin Water Mobile Trailer System #3 - Finish Concrete + 3d Cure | 4 | 2026-02-21 | 2026-02-24
Demin Water Mobile Trailer System Foundation - #4 |  | 18 | 2026-02-07 | 2026-02-24
CN-CV-3360 | Demin Water Mobile Trailer System #4 - Install Forms | 5 | 2026-02-07 | 2026-02-11
CN-CV-3450 | Demin Water Mobile Trailer System #4 - Install Rebar | 5 | 2026-02-12 | 2026-02-16
CN-CV-3460 | Demin Water Mobile Trailer System #4 - Install Anchor Bolts | 2 | 2026-02-17 | 2026-02-18
CN-CV-3490 | Demin Water Mobile Trailer System #4 - Pour Concrete | 2 | 2026-02-19 | 2026-02-20
CN-CV-3500 | Demin Water Mobile Trailer System #4 - Finish Concrete + 3d Cure | 4 | 2026-02-21 | 2026-02-24
SCR CEMS Foundation - #1 |  | 8 | 2026-02-12 | 2026-02-19
CN-CV-1890 | SCR CEMS Foundation Unit #1 - Install Forms | 1 | 2026-02-12 | 2026-02-12
CN-CV-1990 | SCR CEMS Foundation Unit #1 - Install Rebar | 1 | 2026-02-13 | 2026-02-13
CN-CV-2110 | SCR CEMS Foundation Unit #1 - Install Anchor Bolts | 1 | 2026-02-14 | 2026-02-14
CN-CV-2260 | SCR CEMS Foundation Unit #1 - Pour Concrete | 1 | 2026-02-15 | 2026-02-15
CN-CV-2680 | SCR CEMS Foundation Unit #1 - Finish Concrete + 3d Cure | 4 | 2026-02-16 | 2026-02-19
SCR CEMS Foundation - #2 |  | 8 | 2026-02-12 | 2026-02-19
CN-CV-1900 | SCR CEMS Foundation Unit #2 - Install Forms | 1 | 2026-02-12 | 2026-02-12
CN-CV-2000 | SCR CEMS Foundation Unit #2 - Install Rebar | 1 | 2026-02-13 | 2026-02-13
CN-CV-2120 | SCR CEMS Foundation Unit #2 - Install Anchor Bolts | 1 | 2026-02-14 | 2026-02-14
CN-CV-2270 | SCR CEMS Foundation Unit #2 - Pour Concrete | 1 | 2026-02-15 | 2026-02-15
CN-CV-2690 | SCR CEMS Foundation Unit #2 - Finish Concrete + 3d Cure | 4 | 2026-02-16 | 2026-02-19
SCR CEMS Foundation - #3 |  | 8 | 2026-02-12 | 2026-02-19
CN-CV-1910 | SCR CEMS Foundation Unit #3 - Install Forms | 1 | 2026-02-12 | 2026-02-12
CN-CV-2010 | SCR CEMS Foundation Unit #3 - Install Rebar | 1 | 2026-02-13 | 2026-02-13
CN-CV-2130 | SCR CEMS Foundation Unit #3 - Install Anchor Bolts | 1 | 2026-02-14 | 2026-02-14
CN-CV-2280 | SCR CEMS Foundation Unit #3 - Pour Concrete | 1 | 2026-02-15 | 2026-02-15
CN-CV-2700 | SCR CEMS Foundation Unit #3 - Finish Concrete + 3d Cure | 4 | 2026-02-16 | 2026-02-19
Demin Water Tank Foundation |  | 12 | 2026-02-13 | 2026-02-24
CN-CV-2510 | Demin Water Tank Foundation - Install Rebar | 3 | 2026-02-13 | 2026-02-15
CN-CV-2140 | Demin Water Tank Foundation - Install Forms | 2 | 2026-02-14 | 2026-02-16
CN-CV-2710 | Demin Water Tank Foundation - Install Anchor Bolts | 2 | 2026-02-16 | 2026-02-18
CN-CV-2930 | Demin Water Tank Foundation - Pour Concrete | 2 | 2026-02-18 | 2026-02-20
CN-CV-3210 | Demin Water Tank Foundation - Finish Concrete + 3d Cure | 4 | 2026-02-20 | 2026-02-24
Raw Water Tank Foundation |  | 13 | 2026-02-13 | 2026-02-25
CN-CV-2400 | Raw Water Tank Foundation - Install Forms | 2 | 2026-02-13 | 2026-02-14
CN-CV-2720 | Raw Water Tank Foundation - Install Rebar | 3 | 2026-02-15 | 2026-02-17
CN-CV-2940 | Raw Water Tank Foundation - Install Anchor Bolts | 2 | 2026-02-18 | 2026-02-19
CN-CV-3100 | Raw Water Tank Foundation - Pour Concrete | 2 | 2026-02-20 | 2026-02-21
CN-CV-3300 | Raw Water Tank Foundation - Finish Concrete + 3d Cure | 4 | 2026-02-22 | 2026-02-25
Waste Water Tank Foundation |  | 9 | 2026-02-13 | 2026-02-21
CN-CV-1030 | Waste Water Tank Foundation - Install Forms | 1 | 2026-02-13 | 2026-02-13
CN-CV-1100 | Waste Water Tank Foundation - Install Rebar | 2 | 2026-02-14 | 2026-02-15
CN-CV-1520 | Waste Water Tank Foundation - Install Anchor Bolts | 1 | 2026-02-16 | 2026-02-16
CN-CV-1620 | Waste Water Tank Foundation - Pour Concrete | 1 | 2026-02-17 | 2026-02-17
CN-CV-1750 | Waste Water Tank Foundation - Finish Concrete + 3d Cure | 4 | 2026-02-18 | 2026-02-21
Helical Pile and Pedestals |  | 0 | 11-Nov-25 A | 19-Dec-25 A
CN-1975 | Installation of Helical Piles - Piperack | 0 | 11-Nov-25 A | 25-Nov-25 A
CN-CV-1010 | Installation of Helical Piles - Turbines | 0 | 09-Dec-25 A | 10-Dec-25 A
CN-CV-1000 | Survey | 0 | 11-Nov-25 A | 11-Dec-25 A
CN-CV-1040 | Installation of Helical Piles - Tempering Air Supports | 0 | 11-Dec-25 A | 11-Dec-25 A
CN-CV-1020 | Pedestal Formwork | 0 | 12-Nov-25 A | 14-Dec-25 A
CN-CV-1120 | Concrete Placement | 0 | 15-Nov-25 A | 19-Dec-25 A
Steel Supports |  | 48 | 06-Jan-26 A | 2026-03-04
CN-CS-1000 | Pre-Assemble Bridges | 9 | 06-Jan-26 A | 2026-01-24
CN-CS-1030 | Erect Misc PIpe and Electrical Supports | 18 | 2026-02-15 | 2026-03-04
East West PipeRack |  | 20 | 2026-01-16 | 2026-02-04
CN-CS-1050 | East-West Piperack Sec1 | 5 | 2026-01-16 | 2026-01-20
CN-CS-1060 | East-West Piperack Se 2 (Bent 01-108 thru 01-114) | 5 | 2026-01-21 | 2026-01-25
CN-CS-1070 | East-West Piperack Se 3 (Bent 01-115 thru 01-121) | 5 | 2026-01-26 | 2026-01-30
CN-CS-1040 | East-West Piperack Se 4 (Bent 01-122 thru 01-128) | 5 | 2026-01-31 | 2026-02-04
East West Pipe Bridge |  | 5 | 2026-01-25 | 2026-01-29
A2740 | East West Pipe Bridge 1 (PB 01-101 Thru 01-102) | 2 | 2026-01-25 | 2026-01-26
A2750 | East West Pipe Bridge 2 (PB 02-101 Thru 02-102) | 2 | 2026-01-26 | 2026-01-28
A2760 | East West Pipe Bridge 3 (PB 03-101 Thru 03-103) | 2 | 2026-01-28 | 2026-01-29
MCC Building PipeRack |  | 2 | 2026-02-05 | 2026-02-06
A2770 | North South Bridge 1 (PB 04-201 Thru 04-202) | 2 | 2026-02-05 | 2026-02-06
North South PipeRack |  | 14 | 2026-01-21 | 2026-02-03
A2780 | North South Piperack Sec 1 (Bent 02-201 Thru 02-203) | 2 | 2026-01-21 | 2026-01-23
A2790 | North South Piperack Sec 2 (Bent 01-201 Thru 02-206) | 3 | 2026-01-23 | 2026-01-26
A2800 | North South Piperack Sec 3 (Bent 01-207 Thru 02-217) | 2 | 2026-01-26 | 2026-01-28
A2810 | North South Piperack Sec 1 (Bent 02-301 Thru 04-202) | 4 | 2026-01-28 | 2026-02-01
A2820 | North South Piperack Sec2 (Bent 02-301 Thru 01-303) | 2 | 2026-02-01 | 2026-02-03
Nort South Bridge |  | 2 | 2026-02-03 | 2026-02-05
A2830 | North South Pipe Bridge 1 (PB 05-301 Thru 05-302) | 2 | 2026-02-03 | 2026-02-05
Equipment |  | 83 | 2026-01-20 | 2026-04-13
CN-EQ-1030 | Field Erect Tank - Demin Tank | 18 | 2026-02-26 | 2026-03-15
CN-EQ-1040 | Field Erect Tank - Raw Water Tank | 18 | 2026-02-26 | 2026-03-15
CN-EQ-1050 | Field Erect Tank - Slop Tank | 18 | 2026-03-16 | 2026-04-02
CN-EQ-1060 | Field Erect Tank - Waste Water Tank | 18 | 2026-03-16 | 2026-04-02
GT #3 |  | 83 | 2026-01-20 | 2026-04-13
CN-EQ-1070 | Set and Install GT #3 Control Room / Building | 24 | 2026-01-20 | 2026-02-13
CN-EQ-1010 | Set and Install GT #3 Water Injection Skid | 6 | 2026-02-15 | 2026-02-21
CN-EQ-1020 | Set and Install GT #3 MEE Fog Skid | 4 | 2026-02-18 | 2026-02-22
CN-EQ-1000 | Set and Install GT #3 - Inlet Air Filter | 2 | 2026-03-15 | 2026-03-16
GT #3 Main Component Installation |  | 30 | 2026-03-15 | 2026-04-13
CN-HPI-100 | Install Turbine GT#3 - Mobilize & Site Setup | 1 | 2026-03-15 | 2026-03-15
CN-HPI-105 | Install Turbine GT#3 - Set Frame on Fixtures - Level & Align | 3 | 2026-03-16 | 2026-03-18
CN-HPI-110 | Install Turbine GT#3 - Set Accessory Cab & Starting Package - Align | 5 | 2026-03-19 | 2026-03-23
CN-HPI-115 | Install Turbine GT#3 - Set Load Gear / Reduction Gearbox & Cab | 5 | 2026-03-24 | 2026-03-28
CN-HPI-120 | Install Turbine GT#3 - Set Generator Skid & Perform Alignment | 5 | 2026-03-29 | 2026-04-02
CN-HPI-125 | Install Turbine GT#3 - Set GAC & Exciter Skid | 5 | 2026-04-03 | 2026-04-07
CN-HPI-130 | Install Turbine GT#3 - Final Alignment & Data Package | 2 | 2026-04-08 | 2026-04-09
CN-HPI-135 | Install Turbine GT#3 - Oil & Water Piping (Connection at Skid) | 2 | 2026-04-10 | 2026-04-11
CN-HPI-140 | Install Turbine GT#3 - Punchlist / Turnover | 1 | 2026-04-12 | 2026-04-12
CN-HPI-145 | Install Turbine GT#3 - Mechanical Completion | 0 |  | 2026-04-12
CN-HPI-150 | Install Turbine GT#3 - Demobilize | 1 | 2026-04-13 | 2026-04-13
GT #1 |  | 83 | 2026-01-20 | 2026-04-13
CN-EQ-1110 | Set and Install GT #1 Control Room / Building | 24 | 2026-01-20 | 2026-02-13
CN-EQ-1090 | Set and Install GT #1 Water Injection Skid | 6 | 2026-02-15 | 2026-02-21
CN-EQ-1080 | Set and Install GT #1 - Inlet Air Filter | 2 | 2026-03-15 | 2026-03-16
CN-EQ-1100 | Set and Install GT #1 MEE Fog Skid | 4 | 2026-03-15 | 2026-03-18
GT #1 Main Component Installation |  | 30 | 2026-03-15 | 2026-04-13
CN-HPI-155 | Install Turbine GT#1 - Mobilize & Site Setup | 1 | 2026-03-15 | 2026-03-15
CN-HPI-160 | Install Turbine GT#1 - Set Frame on Fixtures - Level & Align | 3 | 2026-03-16 | 2026-03-18
CN-HPI-165 | Install Turbine GT#1 - Set Accessory Cab & Starting Package - Align | 5 | 2026-03-19 | 2026-03-23
CN-HPI-170 | Install Turbine GT#1 - Set Load Gear / Reduction Gearbox & Cab | 5 | 2026-03-24 | 2026-03-28
CN-HPI-175 | Install Turbine GT#1 - Set Generator Skid & Perform Alignment | 5 | 2026-03-29 | 2026-04-02
CN-HPI-180 | Install Turbine GT#1 - Set GAC & Exciter Skid | 5 | 2026-04-03 | 2026-04-07
CN-HPI-185 | Install Turbine GT#1 - Final Alignment & Data Package | 2 | 2026-04-08 | 2026-04-09
CN-HPI-190 | Install Turbine GT#1 - Oil & Water Piping (Connection at Skid) | 2 | 2026-04-10 | 2026-04-11
CN-HPI-195 | Install Turbine GT#1 - Punchlist / Turnover | 1 | 2026-04-12 | 2026-04-12
CN-HPI-200 | Install Turbine GT#1 - Mechanical Completion | 0 |  | 2026-04-12
CN-HPI-205 | Install Turbine GT#1 - Demobilize | 1 | 2026-04-13 | 2026-04-13
GT #2 |  | 83 | 2026-01-20 | 2026-04-13
CN-EQ-1150 | Set and Install GT #2 Control Room / Building | 24 | 2026-01-20 | 2026-02-13
CN-EQ-1130 | Set and Install GT #2 Water Injection Skid | 6 | 2026-02-15 | 2026-02-21
CN-EQ-1140 | Set and Install GT #2 MEE Fog Skid | 4 | 2026-02-21 | 2026-02-25
CN-EQ-1120 | Set and Install GT #2 - Inlet Air Filter | 2 | 2026-03-15 | 2026-03-16
GT #2 Main Component Installation |  | 30 | 2026-03-15 | 2026-04-13
CN-HPI-210 | Install Turbine GT#2 - Mobilize & Site Setup | 1 | 2026-03-15 | 2026-03-15
CN-HPI-215 | Install Turbine GT#2 - Set Frame on Fixtures - Level & Align | 3 | 2026-03-16 | 2026-03-18
CN-HPI-220 | Install Turbine GT#2 - Set Accessory Cab & Starting Package - Align | 5 | 2026-03-19 | 2026-03-23
CN-HPI-225 | Install Turbine GT#2 - Set Load Gear / Reduction Gearbox & Cab | 5 | 2026-03-24 | 2026-03-28
CN-HPI-230 | Install Turbine GT#2 - Set Generator Skid & Perform Alignment | 5 | 2026-03-29 | 2026-04-02
CN-HPI-235 | Install Turbine GT#2 - Set GAC & Exciter Skid | 5 | 2026-04-03 | 2026-04-07
CN-HPI-240 | Install Turbine GT#2 - Final Alignment & Data Package | 2 | 2026-04-08 | 2026-04-09
CN-HPI-245 | Install Turbine GT#2 - Oil & Water Piping (Connection at Skid) | 2 | 2026-04-10 | 2026-04-11
CN-HPI-250 | Install Turbine GT#2 - Punchlist / Turnover | 1 | 2026-04-12 | 2026-04-12
CN-HPI-255 | Install Turbine GT#2 - Mechanical Completion | 0 |  | 2026-04-12
CN-HPI-260 | Install Turbine GT#2 - Demobilize | 1 | 2026-04-13 | 2026-04-13
Wet Surface Air Cooler |  | 12 | 2026-03-06 | 2026-03-17
CN-EQ-1160 | Set and Install Wet Surface Air Cooler Unit 3 | 6 | 2026-03-06 | 2026-03-11
CN-EQ-1430 | Set and Install Wet Surface Air Cooler Units 1 & 2 | 6 | 2026-03-12 | 2026-03-17
Tempering Fan - (6) Total |  | 6 | 2026-02-16 | 2026-02-22
CN-EQ-1320 | Set and Install Tempering Fan #6 | 2 | 2026-02-16 | 2026-02-18
CN-EQ-1340 | Set and Install Tempering Fan #5 | 2 | 2026-02-16 | 2026-02-18
CN-EQ-1300 | Set and Install Tempering Fan #4 | 2 | 2026-02-16 | 2026-02-18
CN-EQ-1290 | Set and Install Tempering Fan #3 | 2 | 2026-02-16 | 2026-02-18
CN-EQ-1250 | Set and Install Tempering Fan #1 | 2 | 2026-02-18 | 2026-02-20
CN-EQ-1270 | Set and Install Tempering Fan #2 | 2 | 2026-02-20 | 2026-02-22
SCR Ammonia Injection Skid |  | 9 | 2026-02-08 | 2026-02-17
CN-EQ-1230 | Set and Install Ammonia Injection Skid #2 | 2 | 2026-02-08 | 2026-02-10
CN-EQ-1240 | Set and Install Ammonia Injection Skid #3 | 2 | 2026-02-10 | 2026-02-12
CN-EQ-1210 | Set and Install Ammonia Injection Skid #1 | 2 | 2026-02-15 | 2026-02-17
SCR CEMS - (3) Total |  | 6 | 2026-03-15 | 2026-03-20
CN-EQ-1220 | Set and Install SCR CEMS #3 | 2 | 2026-03-15 | 2026-03-16
CN-EQ-1280 | Set and Install SCR CEMS #2 | 2 | 2026-03-17 | 2026-03-18
CN-EQ-1310 | Set and Install SCR CEMS #1 | 2 | 2026-03-19 | 2026-03-20
SCR Ammonia Forwarding Skid |  | 2 | 2026-03-05 | 2026-03-06
CN-EQ-1330 | Set and Install SCR Ammonia Forwarding Skid | 2 | 2026-03-05 | 2026-03-06
Wash Water Skid |  | 2 | 2026-03-13 | 2026-03-14
CN-EQ-1360 | Set and Install Wash Water Skid | 2 | 2026-03-13 | 2026-03-14
Demin Water Mobile Trailer System - (4) Total |  | 8 | 2026-02-25 | 2026-03-04
CN-EQ-1370 | Set and Install Demin Water Trailer System #1 | 2 | 2026-02-25 | 2026-02-26
CN-EQ-1390 | Set and Install Demin Water Trailer System #2 | 2 | 2026-02-27 | 2026-02-28
CN-EQ-1410 | Set and Install Demin Water Trailer System #3 | 2 | 2026-03-01 | 2026-03-02
CN-EQ-1420 | Set and Install Demin Water Trailer System #4 | 2 | 2026-03-03 | 2026-03-04
Air Compressor Package |  | 2 | 2026-03-09 | 2026-03-10
CN-EQ-1170 | Set and Install Air Compressor Package | 2 | 2026-03-09 | 2026-03-10
CT Control Modules - (3) Total |  | 8 | 2026-03-18 | 2026-03-25
CN-EQ-1180 | Set and Install CT Control Module #1 | 2 | 2026-03-18 | 2026-03-19
CN-EQ-1190 | Set and Install CT Control Module #2 | 2 | 2026-03-22 | 2026-03-23
CN-EQ-1200 | Set and Install CT Control Module #3 | 2 | 2026-03-24 | 2026-03-25
Area Sump and Sump Pump - (4) Total |  | 5 | 2026-02-21 | 2026-02-25
CN-EQ-1260 | Set and Install Area Sump and Sump Pump #1 | 2 | 2026-02-21 | 2026-02-22
CN-EQ-1350 | Set and Install Area Sump and Sump Pump #2 | 2 | 2026-02-22 | 2026-02-23
CN-EQ-1380 | Set and Install Area Sump and Sump Pump #3 | 2 | 2026-02-23 | 2026-02-24
CN-EQ-1400 | Set and Install Area Sump and Sump Pump #4 | 2 | 2026-02-24 | 2026-02-25
Load Break Switch 1,2,3 |  | 6 | 2026-02-14 | 2026-02-19
CN-EQ-1440 | Set and Install Load Break Switch 1 | 2 | 2026-02-14 | 2026-02-15
CN-EQ-1450 | Set and Install Load Break Switch 2 | 2 | 2026-02-16 | 2026-02-17
CN-EQ-1460 | Set and Install Load Break Switch 3 | 2 | 2026-02-18 | 2026-02-19
SCR Ammonia Storage Tank |  | 2 | 2026-02-26 | 2026-02-27
CN-EQ-1470 | Set and Install - SCR Ammonia Storage Tank | 2 | 2026-02-26 | 2026-02-27
SCR Ammonia Truck Unloading |  | 2 | 2026-03-05 | 2026-03-06
CN-EQ-1480 | Set and Install - SCR Ammonia Truck Unloading | 2 | 2026-03-05 | 2026-03-06
Service Water Pumps P-600 A/B |  | 2 | 2026-03-03 | 2026-03-04
CN-EQ-1490 | Set and Install - Service Water Pumps P-600 A/B | 2 | 2026-03-03 | 2026-03-04
Waste Water Loading Pumps P-300 A/B |  | 2 | 2026-03-04 | 2026-03-05
CN-EQ-1500 | Set and Install - Waste Water Loading Pumps P-300 A/B | 2 | 2026-03-04 | 2026-03-05
Demin Water Pumps P-400 A/B |  | 2 | 2026-03-04 | 2026-03-05
CN-EQ-1510 | Set and Install - Demin Water Pumps P-400 A/B | 2 | 2026-03-04 | 2026-03-05
WSAC Waste Water Pumps P-201 A/B |  | 2 | 2026-03-04 | 2026-03-05
CN-EQ-1520 | Set and Install - WSAC Waste Water Pumps P-201 A/B | 2 | 2026-03-04 | 2026-03-05
MEE Fog Pump 1,2,3 |  | 2 | 2026-02-15 | 2026-02-17
CN-EQ-1530 | Set and Install - MEE Fog Pump 1 | 2 | 2026-02-15 | 2026-02-17
CN-EQ-1540 | Set and Install - MEE Fog Pump 2 | 2 | 2026-02-15 | 2026-02-17
CN-EQ-1550 | Set and Install - MEE Fog Pump 3 | 2 | 2026-02-15 | 2026-02-17
Piping |  | 103 | 2026-01-16 | 2026-04-28
Underground Piping |  | 81 | 2026-01-16 | 2026-04-06
Piping Milestones |  | 81 | 2026-01-16 | 2026-04-06
A2720 | UG Piping Start | 0 | 2026-01-16
A2730 | UG Piping Finish | 0 |  | 2026-04-06
Carbon Steel Piping |  | 65 | 2026-01-19 | 2026-03-24
Fuel Gas Piping |  | 65 | 2026-01-19 | 2026-03-24
P1-402-009 | Install WP-P1-402-009 | 5 | 2026-01-31 | 2026-02-04
PRT-P1-402-009 | Pressure Test WP-P1-402-009 | 2 | 2026-02-05 | 2026-02-06
P1-403-009 | Install WP-P1-403-009 | 5 | 2026-02-07 | 2026-02-11
PRT-P1-403-009 | Pressure Test WP-P1-403-009 | 2 | 2026-02-12 | 2026-02-13
P1-402-003 | Install WP-P1-402-003 | 28 | 2026-01-24 | 2026-02-20
PRT-P1-402-003 | Pressure Test WP-P1-402-003 | 2 | 2026-02-21 | 2026-02-22
P1-401-016 | Install WP-P1-401-016 | 60 | 2026-01-19 | 2026-03-19
PRT-P1-401-016 | Pressure Test WP-P1-401-016 | 5 | 2026-03-20 | 2026-03-24
Instrument Air Piping |  | 25 | 2026-02-09 | 2026-03-05
P1-401-013 | Install WP-P1-401-013 | 10 | 2026-02-09 | 2026-02-18
PRT-P1-401-013 | Pressure Test WP-P1-401-013 | 2 | 2026-02-19 | 2026-02-20
P1-402-007 | Install WP-P1-402-007 | 12 | 2026-02-15 | 2026-02-26
PRT-P1-402-007 | Pressure Test WP-P1-402-007 | 2 | 2026-02-27 | 2026-02-28
P1-403-007 | Install WP-P1-403-007 | 11 | 2026-02-21 | 2026-03-03
PRT-P1-403-007 | Pressure Test WP-P1-403-007 | 2 | 2026-03-04 | 2026-03-05
HDPE Piping |  | 77 | 2026-01-20 | 2026-04-06
Drain Piping |  | 52 | 2026-01-20 | 2026-03-12
P1-401-006 | Install WP-P1-401-006 | 5 | 2026-01-25 | 2026-01-29
PRT-P1-401-006 | Pressure Test WP-P1-401-006 | 2 | 2026-01-30 | 2026-01-31
P1-401-005 | Install WP-P1-401-005 | 28 | 2026-01-20 | 2026-02-16
P1-401-007 | Install WP-P1-401-007 | 20 | 2026-01-30 | 2026-02-18
PRT-P1-401-007 | Pressure Test WP-P1-401-007 | 2 | 2026-02-19 | 2026-02-20
P1-403-003 | Install WP-P1-403-003 | 13 | 2026-02-14 | 2026-02-26
PRT-P1-401-005 | Pressure Test WP-P1-401-005 | 2 | 2026-02-27 | 2026-02-28
PRT-P1-403-003 | Pressure Test WP-P1-403-003 | 2 | 2026-02-27 | 2026-02-28
P1-402-002 | Install WP-P1-402-002 | 28 | 2026-02-04 | 2026-03-03
PRT-P1-402-002 | Pressure Test WP-P1-402-002 | 4 | 2026-03-04 | 2026-03-07
P1-403-002 | Install WP-P1-403-002 | 28 | 2026-02-09 | 2026-03-08
PRT-P1-403-002 | Pressure Test WP-P1-403-002 | 4 | 2026-03-09 | 2026-03-12
Fire Water Piping |  | 30 | 2026-01-26 | 2026-02-24
P1-000-003 | Install WP-P1-000-003 | 20 | 2026-01-26 | 2026-02-14
PRT-P1-000-003 | Pressure Test WP-P1-000-003 | 2 | 2026-02-15 | 2026-02-16
P1-000-001 | Install WP-P1-000-001 | 12 | 2026-02-11 | 2026-02-22
P1-000-002 | Install WP-P1-000-002 | 20 | 2026-02-03 | 2026-02-22
PRT-P1-000-001 | Pressure Test WP-P1-000-001 | 2 | 2026-02-23 | 2026-02-24
PRT-P1-000-002 | Pressure Test WP-P1-000-002 | 2 | 2026-02-23 | 2026-02-24
Glycol Cooling Water Piping |  | 64 | 2026-02-02 | 2026-04-06
P1-401-009 | Install WP-P1-401-009 | 10 | 2026-02-02 | 2026-02-11
P1-401-010 | Install WP-P1-401-010 | 5 | 2026-02-07 | 2026-02-11
PRT-P1-401-009 | Pressure Test WP-P1-401-009 | 2 | 2026-02-12 | 2026-02-13
PRT-P1-401-010 | Pressure Test WP-P1-401-010 | 2 | 2026-02-12 | 2026-02-13
P1-401-011 | Install WP-P1-401-011 | 8 | 2026-02-13 | 2026-02-20
PRT-P1-401-011 | Pressure Test WP-P1-401-011 | 2 | 2026-02-21 | 2026-02-22
P1-401-015 | Install WP-P1-401-015 | 9 | 2026-02-19 | 2026-02-27
PRT-P1-401-015 | Pressure Test WP-P1-401-015 | 2 | 2026-02-28 | 2026-03-01
P1-402-004 | Install WP-P1-402-004 | 9 | 2026-02-25 | 2026-03-05
PRT-P1-402-004 | Pressure Test WP-P1402--004 | 2 | 2026-03-06 | 2026-03-07
P1-402-005 | Install WP-P1-402-005 | 9 | 2026-03-03 | 2026-03-11
PRT-P1-402-005 | Pressure Test WP-P1-402-005 | 2 | 2026-03-12 | 2026-03-13
P1-402-006 | Install WP-P1-401-006 | 6 | 2026-03-09 | 2026-03-14
PRT-P1-402-006 | Pressure Test WP-P1-402-006 | 2 | 2026-03-15 | 2026-03-16
P1-403-005 | Install WP-P1-403-005 | 5 | 2026-03-21 | 2026-03-25
P1-403-004 | Install WP-P1-403-004 | 12 | 2026-03-15 | 2026-03-26
PRT-P1-403-005 | Pressure Test WP-P1-403-005 | 2 | 2026-03-26 | 2026-03-27
PRT-P1-403-004 | Pressure Test WP-P1-403-004 | 2 | 2026-03-27 | 2026-03-28
P1-403-006 | Install WP-P1-403-006 | 9 | 2026-03-27 | 2026-04-04
PRT-P1-403-006 | Pressure Test WP-P1-403-006 | 2 | 2026-04-05 | 2026-04-06
Service Air Piping |  | 23 | 2026-02-16 | 2026-03-10
P1-402-008 | Install WP-P1-402-008 | 9 | 2026-02-22 | 2026-03-02
P1-401-014 | Install WP-P1-401-014 | 16 | 2026-02-16 | 2026-03-03
PRT-P1-402-008 | Pressure Test WP-P1-402-008 | 2 | 2026-03-03 | 2026-03-04
PRT-P1-401-014 | Pressure Test WP-P1-401-014 | 2 | 2026-03-04 | 2026-03-05
P1-403-008 | Install WP-P1-403-008 | 9 | 2026-02-28 | 2026-03-08
PRT-P1-403-008 | Pressure Test WP-P1-403-008 | 2 | 2026-03-09 | 2026-03-10
Ammonia Piping |  | 42 | 2026-01-30 | 2026-03-12
PI-401-004 | Install WP-P1-401-004 | 5 | 2026-02-04 | 2026-02-08
PI-401-003 | Install WP-P1-401-003 | 38 | 2026-01-30 | 2026-03-08
PRT-P1-401-003 | Pressure Test WP-P1-401-003 | 2 | 2026-03-09 | 2026-03-10
PRT-P1-401-004 | Pressure Test WP-P1-401-004 | 2 | 2026-03-11 | 2026-03-12
Potable Water Piping |  | 44 | 2026-01-30 | 2026-03-14
PI-401-002 | Install WP-P1-401-002 | 5 | 2026-03-01 | 2026-03-05
PRT-P1-401-002 | Pressure Test WP-P1-401-002 | 2 | 2026-03-06 | 2026-03-07
PI-401-001 | Install WP-P1-401-001 | 38 | 2026-01-30 | 2026-03-08
PI-402-001 | Install WP-P1-402-001 | 5 | 2026-03-05 | 2026-03-09
PRT-P1-401-001 | Pressure Test WP-P1-401-001 | 2 | 2026-03-09 | 2026-03-10
PRT-P1-402-001 | Pressure Test WP-P1-402-001 | 2 | 2026-03-10 | 2026-03-11
PI-403-001 | Install WP-P1-403-001 | 4 | 2026-03-09 | 2026-03-12
PRT-P1-403-001 | Pressure Test WP-P1-403-001 | 2 | 2026-03-13 | 2026-03-14
Service Water Piping |  | 40 | 2026-01-30 | 2026-03-10
P1-401-012 | Install WP-P1-401-012 | 38 | 2026-01-30 | 2026-03-08
PRT-P1-401-012 | Pressure Test WP-P1-401-012 | 2 | 2026-03-09 | 2026-03-10
Demin Water Piping |  | 17 | 2026-02-25 | 2026-03-13
P1-401-008 | Install WP-P1-401-008 | 15 | 2026-02-25 | 2026-03-11
PRT-P1-401-008 | Pressure Test WP-P1-401-008 | 2 | 2026-03-12 | 2026-03-13
Pipe Testing - Underground Piping |  | 7 | 2026-01-16 | 2026-01-23
Pipe Testing - Carbon Steel |  | 7 | 2026-01-16 | 2026-01-23
CN-PP-1260 | Pressure Test Carbon Steel Piping and Restoration After Testing Complete | 7 | 2026-01-16 | 2026-01-23
Pipe Testing - HDPE |  | 4 | 2026-01-16 | 2026-01-19
CN-PP-1270 | Pressure Test HDPE Piping and Restoration After Testing Complete | 4 | 2026-01-16 | 2026-01-19
Aboveground Piping |  | 85 | 2026-02-03 | 2026-04-28
AG Pipe Installation |  | 61 | 2026-02-03 | 2026-04-04
BOP Piping |  | 55 | 2026-02-03 | 2026-03-29
CN-PP-225 | BOP Pipe Install - Pipe Rack Headers | 12 | 2026-02-03 | 2026-02-14
CN-PP-230 | BOP Pipe Install - Drops to BOP Equipment | 12 | 2026-03-18 | 2026-03-29
Unit 1 Process and Utility Piping |  | 22 | 2026-02-06 | 2026-02-27
CN-PP-235 | Unit 1 Pipe Install - Water Injection | 18 | 2026-02-06 | 2026-02-23
CN-PP-240 | Unit 1 Pipe Install - MEE Fog | 18 | 2026-02-07 | 2026-02-24
CN-PP-245 | Unit 1 Pipe Install - SCR | 18 | 2026-02-08 | 2026-02-25
CN-PP-250 | Unit 1 Pipe Install - Turbine / Generator Cooling | 18 | 2026-02-09 | 2026-02-26
CN-PP-255 | Unit 1 Pipe Install - Fuel Gas Tie In | 18 | 2026-02-10 | 2026-02-27
Unit 2 Process and Utility Piping |  | 22 | 2026-02-24 | 2026-03-17
CN-PP-260 | Unit 2 Pipe Install - Water Injection | 18 | 2026-02-24 | 2026-03-13
CN-PP-265 | Unit 2 Pipe Install - MEE Fog | 18 | 2026-02-25 | 2026-03-14
CN-PP-270 | Unit 2 Pipe Install - SCR | 18 | 2026-02-26 | 2026-03-15
CN-PP-275 | Unit 2 Pipe Install - Turbine / Generator Cooling | 18 | 2026-02-27 | 2026-03-16
CN-PP-280 | Unit 2 Pipe Install - Fuel Gas Tie In | 18 | 2026-02-28 | 2026-03-17
Unit 3 Process and Utility Piping |  | 22 | 2026-03-14 | 2026-04-04
CN-PP-285 | Unit 3 Pipe Install - Water Injection | 18 | 2026-03-14 | 2026-03-31
CN-PP-290 | Unit 3 Pipe Install - MEE Fog | 18 | 2026-03-15 | 2026-04-01
CN-PP-295 | Unit 3 Pipe Install - SCR | 18 | 2026-03-16 | 2026-04-02
CN-PP-300 | Unit 3 Pipe Install - Turbine / Generator Cooling | 18 | 2026-03-17 | 2026-04-03
CN-PP-305 | Unit 3 Pipe Install - Fuel Gas Tie In | 18 | 2026-03-18 | 2026-04-04
Pipe Testing - Above Ground Piping |  | 60 | 2026-02-28 | 2026-04-28
CN-PP-110 | Pipe Testing - Pre Test Punch #1 | 12 | 2026-02-28 | 2026-03-11
CN-PP-140 | Pipe Testing - Test #1 | 6 | 2026-03-12 | 2026-03-17
CN-PP-170 | Pipe Testing - Restoration #1 | 4 | 2026-03-18 | 2026-03-21
CN-PP-200 | Pipe Testing - Sell-Off #1 | 2 | 2026-03-22 | 2026-03-23
CN-PP-120 | Pipe Testing - Pre Test Punch #2 | 12 | 2026-03-18 | 2026-03-29
CN-PP-150 | Pipe Testing - Test #2 | 6 | 2026-03-30 | 2026-04-04
CN-PP-180 | Pipe Testing - Restoration #2 | 4 | 2026-04-05 | 2026-04-08
CN-PP-210 | Pipe Testing - Sell-Off #2 | 2 | 2026-04-09 | 2026-04-10
CN-PP-130 | Pipe Testing - Pre Test Punch #3 | 12 | 2026-04-05 | 2026-04-16
CN-PP-160 | Pipe Testing - Test #3 | 6 | 2026-04-17 | 2026-04-22
CN-PP-190 | Pipe Testing - Restoration #3 | 4 | 2026-04-23 | 2026-04-26
CN-PP-220 | Pipe Testing - Sell-Off #3 | 2 | 2026-04-27 | 2026-04-28
Electrical & Instrumentation |  | 84 | 26-Nov-25 A | 2026-04-09
Ductbanks |  | 48 | 2026-01-16 | 2026-03-04
CN-EI-1270 | Install Ductbanks | 48 | 2026-01-16 | 2026-03-04
Grounding |  | 54 | 2026-01-16 | 2026-03-10
CN-EI-1190 | Install UG Grounding | 12 | 2026-01-16 | 2026-01-27
CN-EI-1380 | Install Bonding | 18 | 2026-02-21 | 2026-03-10
Cable Tray |  | 28 | 2026-02-15 | 2026-03-14
CN-EI-1340 | Install Cable Tray | 28 | 2026-02-15 | 2026-03-14
Conduit and Cable |  | 18 | 2026-03-15 | 2026-04-01
CN-EI-1410 | Pull / Terminate Power and Control Cable | 18 | 2026-03-15 | 2026-04-01
CN-EI-1420 | Install Bonding | 18 | 2026-03-15 | 2026-04-01
LIghting and Receptacles |  | 12 | 2026-03-15 | 2026-03-26
CN-EI-1390 | Install / Terminate Lighting and Receptacles | 12 | 2026-03-15 | 2026-03-26
Electrical Equipment Installation |  | 65 | 2026-01-21 | 2026-03-27
CN-EI-1230 | Set and Install Step Down Transformer AT-EM | 12 | 2026-01-21 | 2026-02-02
CN-EI-1300 | Set and Install Step Down Transformer AT-12 (Existing from NJ) | 12 | 2026-02-20 | 2026-03-04
CN-EI-1180 | Set and Install MCC Building | 2 | 2026-03-08 | 2026-03-09
CN-EI-1260 | Set and Install Step Up Transformer GTs - T1 / T2 / T3 | 12 | 2026-03-01 | 2026-03-12
CN-EI-1220 | Set and Install MCCs (New) | 6 | 2026-03-10 | 2026-03-15
CN-EI-1240 | Set and Install MCCs (from NJ) | 12 | 2026-03-10 | 2026-03-21
CN-EI-1280 | MCC Building Integration | 18 | 2026-03-10 | 2026-03-27
Step-Down Transformers - #1 - (West) |  | 22 | 2026-02-25 | 2026-03-19
CN-EI-1320 | Set and Install Step Down Transformer AT- 3 | 12 | 2026-02-25 | 2026-03-09
CN-EI-1350 | Set and Install Step Down Transformer AT-2 | 12 | 2026-03-02 | 2026-03-14
CN-EI-1370 | Set and Install Step Down Transformer AT-1 | 12 | 2026-03-07 | 2026-03-19
Step Down Transformers - #2 - (East) |  | 22 | 2026-02-20 | 2026-03-14
CN-EI-1290 | Set and Install Step Down Transformer AT-11 | 12 | 2026-02-20 | 2026-03-04
CN-EI-1330 | Set and Install Step Down Transformer AT-21 | 12 | 2026-02-25 | 2026-03-09
CN-EI-1360 | Set and Install Step Down Transformer AT-22 | 12 | 2026-03-02 | 2026-03-14
Electrical Testing |  | 6 | 2026-04-04 | 2026-04-09
CN-EI-1430 | Motor Run-Ins / Electrical Testing GT #2 | 2 | 2026-04-04 | 2026-04-05
CN-EI-1440 | Motor Run-Ins / Electrical Testing GT #3 | 2 | 2026-04-06 | 2026-04-07
CN-EI-1450 | Motor Run-Ins / Electrical Testing GT #1 | 2 | 2026-04-08 | 2026-04-09
Turbine Controls (Petrotech) |  | 52 | 26-Nov-25 A | 2026-03-08
CN-EI-1160 | Petrotech Procurement | 5 | 04-Dec-25 A | 2026-01-20
CN-EI-1200 | Petrotech Programming | 5 | 2026-01-16 | 2026-01-20
CN-EI-1210 | Petrotech Fabrication | 5 | 2026-01-16 | 2026-01-20
CN-EI-1170 | Petrotech Engineering | 7 | 26-Nov-25 A | 2026-01-22
CN-EI-1250 | Petrotech Field Documentation | 1 | 2026-01-29 | 2026-01-29
CN-EI-1310 | Petrotech Factory Testing | 14 | 2026-01-29 | 2026-02-11
CN-EI-1400 | Petrotech Field Work | 27 | 2026-02-10 | 2026-03-08
Commissioning |  | 45 | 2026-04-14 | 2026-05-28
CM-1000 | Commissioning GT#1 | 24 | 2026-04-14 | 2026-05-07
CM-1005 | Commissioning GT#2 | 24 | 2026-04-14 | 2026-05-07
CM-1010 | Commissioning GT#3 | 24 | 2026-04-29 | 2026-05-22
CM-1015 | Startup, functional testing and commissioning review of documentation | 20 | 2026-05-09 | 2026-05-28
Start-up (First Fire) |  | 19 | 2026-05-08 | 2026-05-26
SU-1000 | Start-Up (First Fire) GT#1 | 4 | 2026-05-08 | 2026-05-11
SU-1005 | Start-Up (First Fire) GT#2 | 4 | 2026-05-08 | 2026-05-11
SU-1010 | Start-Up (First Fire) GT#3 | 4 | 2026-05-23 | 2026-05-26